## Status
Interface | Comment Date | Comment
Avalara | 2025-06-06 | Geocode lookup code being removed for web orders
Bank of America | 2025-06-06 | Bill from address missing name, review line 1/2/3 on supplier address
Bartender | 2025-06-06 | Waiting for Infor developers to test
CenPOS | 2025-06-06 | No issues reported
Curbstone | 2025-06-06 | Waiting for migrated open orders to test
Concur Invoice | 2025-06-06 | Meeting with Shared services today to confirm any open issues
Concur Travel & Expense | 2025-06-06 | Kevin sent request to Dan Tuller and Jesse Keech for test data to be submitted on Jun-05
Data Warehouse / Power BI | 2025-06-06 | Loading sales account mapping and setting up test environment
High Radius (Cforia) | 2025-06-06 | Meeting with Shared services today to confirm any open issues
Optimizely | 2025-06-06 | Stock logic being updated and Avalara issue discussed above
PNC | 2025-06-06 | Meeting with Shared services today to confirm any open issues
Salesforce | 2025-06-06 | Meeting Monday to have a first review with team
SPS Commerce (EDI) | 2025-06-06 | Test data provided, customer service team will be testing
UPS | 2025-06-06 | No feedback
FedEx | 2025-06-06 | No feedback

## Servers
Enterprise Connector Server | Used to exchage files and data with Infor M3 (BODs, flat files, etc.)
Test Server name: | RAUSMSRV0002.RA.BG1857.NET
Concur Invoice | \\RAUSMSRV0002.RA.BG1857.NET\asr\Concur\IN
Production Server name: | RAUSMSRV0001.RA.BG187.NET
Concur Invoice Production: | \\RAUSMSRV0001.RA.BG1857.NET\asr\Concur_Invoice\IN | \\RAUSMSRV0001.RA.BG1857.NET\asr\Concur\IN
Concur Travel Expense Production | \\RAUSMSRV0001.RA.BG1857.NET\asr\Concur_TE\IN
Database Server
Test Server | ngeumsmi0001.382a44b6e9bc.database.windows.net
Test Database | DI_STAGING_W8DY5WFWZLXDHJPA_TST
Admin Login: | azure_admin
Admin Password: | NGEU01D > ngeumrsg0003d > ngeumkva0003 > Secrets > ngeumsmi0001
Production Server: | ngeumsmi0002.d44d2f32ac81.database.windows.net
Production Database: | di_staging_prd_us
Admin Login: | azure_admin
Admin Password: | NGEU01 > ngeumrsg0003 > ngeumkva0004 > Secrets > M3-SQL-ngeumsmi0002-sysadmin

## Service Accounts-Emails
Application | Account/Email | Password | Note
CenPos Credit Card | DL_ASR_CenPos_Admin@onebarnes.com |  | Used on CenPos integration account for MFA, currently damo and jfinch are members
RA\M0010 |  | MibyncOF3g13sa1Q2yu2 | Used for Barnes processes (Continous lock from Ivanti server??)
RA\M0011 |  | rAdr2wFFKqkrlJqhrFhp | M3 Enterprise connector file share access account
RA\M0012 |  | #2@xM's@oeMvHgD0£8zlxc5]a6 | Used for Barnes processes

## PNC
Test DB: | ngeumsmi0001.382a44b6e9bc.database.windows.net |  | Data Source=ngeumsmi0001.382a44b6e9bc.database.windows.net;User ID=SM0005;Initial Catalog=M3_Extension;
SQL Account | SM0005
Password: | #DTRdxHtx3lbE1U0Dtnvv |  |  | #DTRdxHtx3lbE1U0Dtnvv
PNC SFTP
Host: | efx-uat.pnc.com
User: | asrymond0t | (case sensitive)
Password: | gsnnz2f-
Filename: | vic.778905.asr.in.yyyymmdd.hhmmss
Production Server: | ngeumsmi0002.d44d2f32ac81.database.windows.net
Production Database: | di_staging_prd_us

## Optimizely
Sites
Integration | https://stab01mstrj2g84inte.dxcloud.episerver.net/
Pre-Production | https://stab01mstrj2g84prep.dxcloud.episerver.net/
Optimizely Storage Account | Used to exchange data with Optimizely
Storage account: | rausmsta0004
Test Drop Off | \\RAUSMSRV0002.RA.BG1857.NET\asr\eCommerce-Orders\IN
Production Drop Off | \\RAUSMSRV0001.RA.BG1857.NET\asr\eCommerce-Orders\IN

## UPS-FedEx
Both reachable from bgusmsrv0032
UPS Test PC | RAUSC1473.ra.bg1857.net
FedEx Test PC
FedEx / UPS ODBC Test
Server: | ngeumsmi0001.382a44b6e9bc.database.windows.net
Database: | M3_Extension
SQL User: | SM0004
Password: | R0HbkqKcHOWyPC2xOHds
UPS Shipments XML: | \\RAUSMSRV0002.RA.BG1857.NET\asr\UPS\IN
FedEx Shipments XML: | \\RAUSMSRV0002.RA.BG1857.NET\asr\FedEx\IN
FedEx / UPS ODBC Production
Server: | ngeumsmi0002.d44d2f32ac81.database.windows.net
Database: | M3_Extension
SQL User: | SM0004
Password: | U91cq1MplG3cp1QNgF3h
UPS Shipments XML: | \\RAUSMSRV0001.RA.BG1857.NET\asr\UPS\IN
FedEx Shipments XML: | \\RAUSMSRV0001.RA.BG1857.NET\asr\FedEx\IN

## Concur Env Switch
Concur Invoice To M3 Prod
Steps | To Do | Server | Process | Note
1 | Enable | BGUSMSRV0030 | SQL JOB : _ConcurImport-InvoicePost_ASRM3
2 | Enable | BGUSMSRV0030 | SQL JOB : _ConcurExtracts-ASRM3
3 | Enable | BGUSMSRV0019 | Schedule Task : ASRM3-ConcurInvoice_SendXML
4 | Enable | BGUSMSRV0019 | Schedule Task : ASRM3-ConcurInvoice_SendCSV
5 | *Disable* | BGUSMSRV0019 | Schedule Task : Concur-ImportInvoice | Copies production files to dev environment(BGUSMSRV0019-TE) [keep enabled if further testing is needed]
6 | *Disable* | BGUSMSRV0019 | Schedule Task : ConcurTravelAndExpenseFileCopy | Copies Concur T&E to Development Sever BGUSMSRV0019-TE [keep enabled if futher testing is needed]
7 | Disable | BGUSMSRV0031 | SQL JOB : _ConcurImport-InvoiceImport
8 | Disable | BGUSMSRV0031 | SQL JOB : _ConcurExtracts-ASRM3
9 | Disable | BGUSMSRV0019-TE | Schedule Task : ASRM3-ConcurInvoice_SendXML
10 | Disable | BGUSMSRV0019-TE | Schedule Task : ASRM3-ConcurInvoice_SendCSV
Concur Invoice To M3 Test
Steps | To Do | Server | Process | Note
1 | Enable | BGUSMSRV0031 | SQL JOB : _ConcurImport-InvoiceImport | To manually run jobs can be executed using SQL JOB : _ConcurImport-InvoicePost_ASRM3
2 | Enable | BGUSMSRV0031 | SQL JOB : _ConcurExtracts-ASRM3
3 | Enable | BGUSMSRV0019-TE | Schedule Task : ASRM3-ConcurInvoice_SendXML
4 | Enable | BGUSMSRV0019-TE | Schedule Task : ASRM3-ConcurInvoice_SendCSV
5 | Enable | BGUSMSRV0019 | Schedule Task : Concur-ImportInvoice | Copies Production Invoice Header and Invoice Detail files to Development Server BGUSMSRV0019-TE
6 | Enable | BGUSMSRV0019 | Schedule Task : ConcurTravelAndExpenseFileCopy | Copies Concur T&E to Development Sever BGUSMSRV0019-TE
7 | Disable | BGUSMSRV0030 | SQL JOB : _ConcurImport-InvoicePost_ASRM3
8 | Disable | BGUSMSRV0030 | SQL JOB : _ConcurExtracts-ASRM3
9 | Disable | BGUSMSRV0019 | Schedule Task : ASRM3-ConcurInvoice_SendXML
10 | Disable | BGUSMSRV0019 | Schedule Task : ASRM3-ConcurInvoice_SendCSV

## SIT Info
Integration | Step | Test Server | Test Description | Production Server | Production Description | Apr-End-To-End Pointed to PRD | Production Owner
Bank of America | SQL Job | bgusmsrv0031 | _23:00_Wednesday_ASRM3BoA | bgusmsrv0030 | _21:35_Wednesday_ASR_M3_BoA_CheckRun | Complete | Jane
Bank of America | SSIS Package | bgusmsrv0031 | /ASR BoA/ASR M3 BoA/ASR M3 APCheckACH.dtsx | bgusmsrv0030 | /ASR BoA/ASR M3 BoA/ASR M3 APCheckACH.dtsx | Complete | Jane
Bank of America | Source Location | DevOps | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/FMC_ASR_M3_CheckRun | DevOps | FMC_ASR_M3_CheckRun - Repos | Complete | Jane
Bank of America | Validation | bgusmsrv0031 | App_Monitor | Validation | App_Monitor | Complete | Jane
CenPOS | Credit Card Processing |  | See doc CenPOS - Infor Test Site Setup
Cforia | SQL Job | bgusmsrv0031 | _04:55_CForiaExtracts_Raymond | bgusmsrv0030 | _04:52_CforiaExtracts_ASR_M3_Prod |  | Kevin
Cforia | SSIS Package | bgusmsrv0031 | BGI Packages/Cforia Extracts/RaymondExtracts.dtsx | bgusmsrv0030 | BGI Packages\ASR_M3_CforiaExtracts\RaymondExtracts.dtsx |  | Kevin
Cforia | Source Location | bgusmsrv0031 | CforiaExtracts - Repos |  |  |  | Kevin
Cforia | RoboFTP Script Task | bgusmsrv0019 | Dev-CforiaExtracts | bgusmsrv0019 | \\bgusmsrv0019.bg.bg1857.net\Stage\CForia\GPCOMP4\ |  | Kevin
Concur Invoice (Extract) | SQL Job | bgusmsrv0031 | ConcurExtracts-ASRM3 | bgusmsrv0030 | ConcurExtracts-ASRM3 |  | Kevin
Concur Invoice (Extract) | SSIS Package | bgusmsrv0031 | BGI Packages/ConcurExtracts/ASRM3Extracts.dtsx | bgusmsrv0030 |  |  | Kevin
Concur Invoice (Extract) | Extract Drop Off | bgusmsrv0019-te |  | bgusmsrv0019 | \\bgusmsrsv0019\Concur Import Aurora
Concur Invoice (Extract) | DataSource | bgusmsmi0004 | DW_BGI_OpData -> App_Concur | bguss0012 |  |  | Kevin
Concur Invoice (Extract) | Source Control | bgusmsrv0031 | ConcurExtracts - Repos | DevOps |  |  | Kevin
Concur Invoice (Inbound) | SQL Job | bgusmsrv0031 | ConcurImport-InvoicePost_ASRM3 | bgusmsrv0030 | ConcurImport-InvoicePost_ASRM3 |  | Kevin
Concur Invoice (Inbound) | SSIS Package | bgusmsrv0031 | BGI Packages/ConcurImport/InvoicePost_ASRM3.dtsx | ConcurImport |  |  | Kevin
Concur Invoice (Inbound) | DataSource | ngeumsmi0001 |  | ngeumsmi0002 |  |  | Kevin
Concur Invoice (Inbound) | Source Control | bgusmsrv0031 | ConcurImport - Repos | Devops |  |  | Kevin
Concur Invoice (Inbound) | Powershell Scheduled Task | bgusmsrv0019 | ConcurImportInvoice - Copies production files to 19-te for SSIS | (not needed in production) |  |  | Kevin
Concur Invoice (Inbound) | Powershell Scheduled Task |  | SendXml | bgusmsrv0019 | E:\AppScripts\asrm3-concurinvoice_sendxml.ps1
Concur T&E | SQL Job | bgusmsrv0031 | ConcurImport-TravelAndExpense_Distribution | bguss0014 | Concur_SSIS |  | Kevin | **Jesse provides file with test data manually
Concur T&E | SSIS Package | bgusmsrv0031 | TravelAndExpense_Distribution.dtsx | bguss0014 | Concur Data Import Redist.dtsx |  | Kevin
Concur T&E | Source Location | bgusmsrv0031 | ConcurImport - Repos |  |  |  | Kevin
Concur T&E | Powershell Scheduled Task | bgusmsrv0019 | ConcurTravelandExpenseFileCopy | (not needed in production) |  |  | Kevin
Concur T&E | Powershell Scheduled Task |  | SendCSV | bgusmsrv0019 | E:\AppScripts\asrm3-concurinvoice_sendcsv.ps1 |  | Kevin
Concur T&E | Dropoff Folder | rausmsrv0002 | \\RAUSMSRV0002.ra.bg1857.net\ASR\Concur_TE\IN | rausmsrv0001 |  |  | Kevin
Data Warehouse | SQL Job | bgusmsrv0031 | _02:00_BGIDW_ASRM3_Daily | bgusmsrv0030 | _23:45_BGIDW_ASR_M3 | Complete | Dean - BGUSS0012
Data Warehouse | SSIS Package | bgusmsrv0031 | BGIDW\BGI_DW_M3\BGIDW_ASR_M3_Daily.dtsx | bgusmsrv0030 | /SSISDB/BGI_DW/BGIDW_ASR_M3\BGIDW_ASR_M3_Daily.dtsx |  | Dean - BGUSS0030 | ** JOE PUSHING LATEST VERSION
Data Warehouse | Source Location | DevOps | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/BGI_DW_M3 | DevOps | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/BGI_DW_M3 | Complete | Dean
FedEx | SQL Job | bgusmsrv0031 | FedEx_Shipment_Processing | bgusmsrv0030 | FedEx_Shipment_Processing | Complete | Jerry
FedEx | SSIS Package | bgusmsrv0031 | FedEx_Shipment_Processing | bgusmsrv0030 | FedEx_Shipment_Processing | Complete | Jerry
FedEx | Source Location | DevOps | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/Fed_Ex_Shipment_Processing | bgusmsrv0030 | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/Fed_Ex_Shipment_Processing | Complete | Jerry
UPS |  |  | \\RAUSMSRV0002.ra.bg1857.net\ASR\UPS\IN |  | \\RAUSMSRV0001.ra.bg1857.net\ASR\UPS\IN | Complete | Dean
Optimizely | SQL Job | bgusmsrv0031 | _05:30_Monday_Optimizely_ASR_M3 | bgusmsrv0030 | system_id=33, system_entity_id = 910088, entity_id='0088T' | Complete | Jane
Optimizely | SSIS Package | bgusmsrv0031 | Optimizely_Extract_Full_ASR_M3.dtsx | bgusmsrv0030 | bguss0012 | Complete | Jane
Optimizely | SSIS Target Azure File Storage | rausmsta0004 | Optimizely/DEV/ | rausmsta0004 | Optimizely/DEV/
Optimizely | SSIS Package | bgusmsrv0031 | _09:10-17:10_Optimizely_ASR_M3_InventoryUpdate
Optimizely | Source Location | DevOps | Optimizely_ASR - Repos |  |  | Complete | Jane
Optimizely | Python Order Intake | bgusmsrv0019-te | Scheduled task (Every 10 minutes) | bgusmsrv0019 |  |  | Don
Optimizely | Python Order Intake - File dropoff | bgusmsrv0019-te | \\RAUSMSRV0002.ra.bg1857.net\ASR\eCommerce_Orders\IN | bgusmsrv0019 | \\RAUSMSRV0001.ra.bg1857.net\ASR\eCommerce_Orders\IN |  | Don
Optimizely | Web Site |  | https://stab01mstrj2g84inte.dxcloud.episerver.net/ |  | https://www.asraymond.com/
PNC Bank - Matcher | SQL Job | bgusmsrv0031 | _15:40 PNC_Bank-ASR M3-Matcher_File | bgusmsrv0030 | _15:40 PNC_Bank-ASR M3-Matcher_File | Complete | Dean
PNC Bank - Matcher | SSIS Package | bgusmsrv0031 | BGI Packages/ASR_M3_ARMatcher/ASR_M3_ARMatcher.dtsx | bgusmsrv0030 | BGI Packages/ASR_M3_ARMatcher/ASR_M3_ARMatcher.dtsx | Complete | Dean
PNC Bank - Matcher | Source Location | DevOps | M3_ARMatcher - Repos | DevOps | M3_ARMatcher - Repos | Complete | Dean
PNC Bank - Matcher | Dropoff Folder | bgusmsrv0019 | \\bgusmsrv0019\PncBank\dev\barnesasraymondM3 | bgusmsrv0019 | \\bgusmsrv0019\PncBank\dev\barnesasraymondM3 | Complete | Dean
PNC Bank - Matcher | RoboFTP Script Task | bgusmsrv0019 |  |  |  |  | Dean
Salesforce
SPS Commerce
High Radius | [6 empty] | Kevin
CurbStone |  |  |  | bgusmsrv0030 | _Curbstone_M3_Process |  | Jane

## GO LIVE
Integration | Step | Test Server | Test Description | Production Server | Production Description | Apr-End-To-End Pointed to PRD | Production Owner
Bank of America | SQL Job | bgusmsrv0031 | _23:00_Wednesday_ASRM3BoA | bgusmsrv0030 | _3:00_ASR_M3_BoA_CheckRun_Daily | Complete | Jane
Bank of America | SSIS Package | bgusmsrv0031 | /ASR BoA/ASR M3 BoA/ASR M3 APCheckACH.dtsx | bgusmsrv0030 | /ASR BoA/ASR M3 BoA/ASR M3 APCheckACH.dtsx | Complete | Jane
Bank of America | Source Location | DevOps | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/FMC_ASR_M3_CheckRun | DevOps | FMC_ASR_M3_CheckRun - Repos | Complete | Jane
Bank of America | Validation | bgusmsrv0031 | App_Monitor | Validation | App_Monitor | Complete | Jane
CenPOS | Credit Card Processing |  | See doc CenPOS - Infor Test Site Setup
Cforia | SQL Job | bgusmsrv0031 | _04:55_CForiaExtracts_Raymond | bgusmsrv0030 | _04:52_CforiaExtracts_ASR_M3_Prod |  | Kevin
Cforia | SSIS Package | bgusmsrv0031 | BGI Packages/Cforia Extracts/RaymondExtracts.dtsx | bgusmsrv0030 | BGI Packages\ASR_M3_CforiaExtracts\RaymondExtracts.dtsx |  | Kevin
Cforia | Source Location | bgusmsrv0031 | CforiaExtracts - Repos |  |  |  | Kevin
Cforia | RoboFTP Script Task | bgusmsrv0019 | Dev-CforiaExtracts | bgusmsrv0019 | \\bgusmsrv0019.bg.bg1857.net\Stage\CForia\GPCOMP4\ |  | Kevin
Concur Invoice (Extract) | SQL Job | bgusmsrv0031 | ConcurExtracts-ASRM3 | bgusmsrv0030 | ConcurExtracts-ASRM3 |  | Kevin
Concur Invoice (Extract) | SSIS Package | bgusmsrv0031 | BGI Packages/ConcurExtracts/ASRM3Extracts.dtsx | bgusmsrv0030 |  |  | Kevin
Concur Invoice (Extract) | Extract Drop Off | bgusmsrv0019-te |  | bgusmsrv0019 | \\bgusmsrsv0019\Concur Import Aurora
Concur Invoice (Extract) | DataSource | bgusmsmi0004 | DW_BGI_OpData -> App_Concur | bguss0012 |  |  | Kevin
Concur Invoice (Extract) | Source Control | bgusmsrv0031 | ConcurExtracts - Repos | DevOps |  |  | Kevin
Concur Invoice (Inbound) | SQL Job | bgusmsrv0031 | ConcurImport-InvoicePost_ASRM3 | bgusmsrv0030 | ConcurImport-InvoicePost_ASRM3 |  | Kevin
Concur Invoice (Inbound) | SSIS Package | bgusmsrv0031 | BGI Packages/ConcurImport/InvoicePost_ASRM3.dtsx | ConcurImport |  |  | Kevin
Concur Invoice (Inbound) | DataSource | ngeumsmi0001 |  | ngeumsmi0002 |  |  | Kevin
Concur Invoice (Inbound) | Source Control | bgusmsrv0031 | ConcurImport - Repos | Devops |  |  | Kevin
Concur Invoice (Inbound) | Powershell Scheduled Task | bgusmsrv0019 | ConcurImportInvoice - Copies production files to 19-te for SSIS | (not needed in production) |  |  | Kevin
Concur Invoice (Inbound) | Powershell Scheduled Task |  | SendXml | bgusmsrv0019 | E:\AppScripts\asrm3-concurinvoice_sendxml.ps1
Concur T&E | SQL Job | bgusmsrv0031 | ConcurImport-TravelAndExpense_Distribution | bguss0014 | Concur_SSIS |  | Kevin | **Jesse provides file with test data manually
Concur T&E | SSIS Package | bgusmsrv0031 | TravelAndExpense_Distribution.dtsx | bguss0014 | Concur Data Import Redist.dtsx |  | Kevin
Concur T&E | Source Location | bgusmsrv0031 | ConcurImport - Repos |  |  |  | Kevin
Concur T&E | Powershell Scheduled Task | bgusmsrv0019 | ConcurTravelandExpenseFileCopy | (not needed in production) |  |  | Kevin
Concur T&E | Powershell Scheduled Task |  | SendCSV | bgusmsrv0019 | E:\AppScripts\asrm3-concurinvoice_sendcsv.ps1 |  | Kevin
Concur T&E | Dropoff Folder | rausmsrv0002 | \\RAUSMSRV0002.ra.bg1857.net\ASR\Concur_TE\IN | rausmsrv0001 |  |  | Kevin
Data Warehouse | SQL Job | bgusmsrv0031 | _18:30_BGIDW_ASRM3_Daily | bgusmsrv0030 | _23:45_BGIDW_ASR_M3 | Complete | Dean - BGUSS0012
Data Warehouse | SSIS Package | bgusmsrv0031 | BGIDW\BGI_DW_M3\BGIDW_ASR_M3_Daily.dtsx | bgusmsrv0030 | /SSISDB/BGI_DW/BGIDW_ASR_M3\BGIDW_ASR_M3_Daily.dtsx |  | Dean - BGUSS0030 | ** JOE PUSHING LATEST VERSION
Data Warehouse | Source Location | DevOps | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/BGI_DW_M3 | DevOps | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/BGI_DW_M3 | Complete | Dean
FedEx | SQL Job | bgusmsrv0031 | FedEx_Shipment_Processing | bgusmsrv0030 | FedEx_Shipment_Processing | Complete | Jerry
FedEx | SSIS Package | bgusmsrv0031 | FedEx_Shipment_Processing | bgusmsrv0030 | FedEx_Shipment_Processing | Complete | Jerry
FedEx | Source Location | DevOps | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/Fed_Ex_Shipment_Processing | bgusmsrv0030 | https://dev.azure.com/bgi-corporate/SSIS_Integrations/_git/Fed_Ex_Shipment_Processing | Complete | Jerry
UPS |  |  | \\RAUSMSRV0002.ra.bg1857.net\ASR\UPS\IN |  | \\RAUSMSRV0001.ra.bg1857.net\ASR\UPS\IN | Complete | Dean
Optimizely | SQL Job | bgusmsrv0031 | _05:30_Monday_Optimizely_ASR_M3 | bgusmsrv0030 | system_id=33, system_entity_id = 910088, entity_id='0088T' | Complete | Jane
Optimizely | SSIS Package | bgusmsrv0031 | Optimizely_Extract_Full_ASR_M3.dtsx | bgusmsrv0030 | bguss0012 | Complete | Jane
Optimizely | SSIS Target Azure File Storage | rausmsta0004 | Optimizely/DEV/ | rausmsta0004 | Optimizely/DEV/
Optimizely | SSIS Package | bgusmsrv0031 | _09:10-17:10_Optimizely_ASR_M3_InventoryUpdate
Optimizely | Source Location | DevOps | Optimizely_ASR - Repos |  |  | Complete | Jane
Optimizely | Python Order Intake | bgusmsrv0019-te | Scheduled task (Every 10 minutes) | bgusmsrv0019 |  |  | Don
Optimizely | Python Order Intake - File dropoff | bgusmsrv0019-te | \\RAUSMSRV0002.ra.bg1857.net\ASR\eCommerce_Orders\IN | bgusmsrv0019 | \\RAUSMSRV0001.ra.bg1857.net\ASR\eCommerce_Orders\IN |  | Don
Optimizely | Web Site |  | https://stab01mstrj2g84inte.dxcloud.episerver.net/ |  | https://www.asraymond.com/
Optimizely Orders In
PNC Bank - Matcher | SQL Job | bgusmsrv0031 | _15:40 PNC_Bank-ASR M3-Matcher_File | bgusmsrv0030 | _15:40 PNC_Bank-ASR M3-Matcher_File | Complete | Dean
PNC Bank - Matcher | SSIS Package | bgusmsrv0031 | BGI Packages/ASR_M3_ARMatcher/ASR_M3_ARMatcher.dtsx | bgusmsrv0030 | BGI Packages/ASR_M3_ARMatcher/ASR_M3_ARMatcher.dtsx | Complete | Dean
PNC Bank - Matcher | Source Location | DevOps | M3_ARMatcher - Repos | DevOps | M3_ARMatcher - Repos | Complete | Dean
PNC Bank - Matcher | Dropoff Folder | bgusmsrv0019 | \\bgusmsrv0019\PncBank\dev\barnesasraymondM3 | bgusmsrv0019 | \\bgusmsrv0019\PncBank\dev\barnesasraymondM3 | Complete | Dean
PNC Bank - Matcher | RoboFTP Script Task | bgusmsrv0019 |  |  |  |  | Dean
Salesforce
SPS Commerce
High Radius | [6 empty] | Kevin
CurbStone |  |  |  | bgusmsrv0030 | _Curbstone_M3_Process |  | Jane

## UAT Action List
Integration | Step | Test Server | Test Description | Production Server | Production Description | Production Owner | UAT 1 - May | End to End | Apr-End-To-End Pointed to PRD
Bank of America | SQL Job | bgusmsrv0031 | _23:00_Wednesday_ASRM3BoA | bgusmsrv0030 | _3:00_ASR_M3_BoA_CheckRun_Daily | Jane | Ready | Complete | Complete
CenPOS | Credit Card Processing |  | See doc CenPOS - Infor Test Site Setup |  |  | Dean/Joe | Ready
Cforia | SQL Job | bgusmsrv0031 | _04:55_CForiaExtracts_Raymond | bgusmsrv0030 | _04:52_CforiaExtracts_ASR_M3_Prod | Kevin | N/A
Concur Invoice (Extract) | SQL Job | bgusmsrv0031 | ConcurExtracts-ASRM3 | bgusmsrv0030 | _ConcurExtracts-ASRM3 | Kevin | Ready
Concur Invoice (Extract) | Extract Drop Off | bgusmsrv0019-te |  | bgusmsrv0019 | \\bgusmsrsv0019\Concur Import Aurora | Kevin | Ready
Concur Invoice (Inbound) | SQL Job | bgusmsrv0031 | ConcurImport-InvoicePost_ASRM3 | bgusmsrv0030 | _ConcurImport-InvoicePost_ASRM3 | Kevin | Ready
Concur T&E | SQL Job | bgusmsrv0031 | ConcurImport-TravelAndExpense_Distribution | bguss0014 | Concur_SSIS | Kevin | Ready |  |  | **Jesse provides file with test data manually
Concur T&E | Dropoff Folder | rausmsrv0002 | \\RAUSMSRV0002.ra.bg1857.net\ASR\Concur_TE\IN | rausmsrv0001 |  | Kevin | Ready
Data Warehouse | SQL Job | bgusmsrv0031 | _02:00_BGIDW_ASRM3_Daily | bgusmsrv0030 | _23:45_BGIDW_ASR_M3 | Dean/Joe | Ready | Complete | Complete
FedEx | SQL Job | bgusmsrv0031 | FedEx_Shipment_Processing | bgusmsrv0030 | FedEx_Shipment_Processing | Jerry | Ready |  | Complete
UPS |  |  | \\RAUSMSRV0002.ra.bg1857.net\ASR\UPS\IN |  | \\RAUSMSRV0001.ra.bg1857.net\ASR\UPS\IN | Dean | Ready |  | Complete
Optimizely | SQL Job | bgusmsrv0031 | _05:30_Monday_Optimizely_ASR_M3 | bgusmsrv0030 | system_id=33, system_entity_id = 910088, entity_id='0088T' | Jane | Ready | Complete | Complete
PNC Bank - Matcher | SQL Job | bgusmsrv0031 | _15:40 PNC_Bank-ASR M3-Matcher_File | bgusmsrv0030 | _15:40 PNC_Bank-ASR M3-Matcher_File | Dean | Turn on job |  | Complete
PNC Bank - Matcher | Dropoff Folder | bgusmsrv0019 | \\bgusmsrv0019\PncBank\dev\barnesasraymondM3 | bgusmsrv0019 | \\bgusmsrv0019\PncBank\dev\barnesasraymondM3 | Dean |  |  | Complete
PNC Bank - Matcher | RoboFTP Script Task | bgusmsrv0019 |  |  |  | Dean
Salesforce | [5 empty] | ? | ?
SPS Commerce | [5 empty] | ? | ?
High Radius (Invoice) |  |  |  | bgusmsrv0030 | _02:30_HighRadius-InvoiceExtract | Kevin | Not ready to test based on Ellen Style | N/A
High Radius |  |  |  | bgusmsrv0030 | _02:30_HighRadius-Extracts | Kevin |  | N/A
CurbStone | SQL Job |  | remaining open orders needs | bgusmsrv0030 | _Curbstone_M3_Process | Jane | Manual
Bartender | bgusmsrv0019 |  | Automated integration printing |  |  | Shaun

## DropDowns
Status
Open
In Progress
Complete