## Status (hidden)
W=Working, C=Complete, R=Risk
Target | 2024-04-26 | 2024-04-26 | 2024-05-31 | 2024-06-17 | 2024-06-17 | 2024-10-21
INTERFACE | ANA-50 Functional Spec | TAR-040 Technical Spec | DES-020 Test Env. Ready | TES-070 Test Plan/Script | TES-070 Test Data | Test Signoff | Latest Comment | Next Steps(s)
Concur Invoice | W | W | W | Laying out unit tests |  |  | [Jun-7] We have 3 test POs. Need the business to enter and receive the POs. Then Shared Services will enter the vendor invoice to complete the 3-way match to test the XML BOD back to M3. [Jun-13] Sent email to team asking them to complete test
Concur Travel & Expense
Salesforce | C | C | W | W | W |  | [Jun-14] Next step is to review test plan with Torborjn
SPS Commerce EDI | W | W | W |  |  |  | [Jun-14] Rich Ospry engaged to assist with technical information, has already started providing information needed to SPS Commerce. [June28 Matt] ANA ready for Barnes review/approval. | [Apr-26] - Kick off meeting with SPS Commerce Apr-30 10:30a EDT. Cheska set up weekly meetings.
PNC Bank (AR) | R | W |  |  |  |  | [Jun-14] Meeting scheduled Mon Jun 17 to see what additional is needed to complete the ANA and begin setup of test enironement | [Apr-26] Meeting scheduled for May-1 8a EDT with Shared Service, JBA ERP, Infor to discuss process detail
Shared Service (AP) Bank of America | R | W |  |  |  |  | [Jun-14] Meeting scheduled Mon Jun 17 to see what additional is needed to complete the ANA and begin setup of test enironement | [Apr-26] Meeting scheduled for May-1 8a EDT with Shared Service, JBA ERP, Infor to discuss process detail
Cforia | R | W | W |  |  |  | [Jun-14] Kevin has started query to provide open A/R balance. Amy McGuire to run open balance out of M3. We may need to get Kevin/Dean access to run report out of M3 as open balance can change | [Apr-26] Kevin to refine queries for output files. Work with Cforia to send to test environment.
Fedex | C | W | W |  |  |  | [Jun-14] Jack Adoline reviewing in place of Aaron departure. | [Apr-26] Connectivity to test/prod workstations | Export to correct location, FEDEX>IN, UPS>IN. Can we send prod to both current ERP and M3
UPS | C | W | W |  |  |  | [Jun-14] Jack Adoline reviewing in place of Aaron departure. | [Apr-26] Connectivity to test/prod workstations
Credit Card Processing - CenPOS | W | W | W |  |  |  | [May-15] Uploaded demo environment connection information from CenPOS to Infor site and notified team. Next step is to plug into interface and verify works with M3 test environment. Need to meet with Optimziely vendor CONSID to determine steps needed to connect to e-commerce/Optimizely | [Apr-26] Seems we're already an Evalon\US Bank customer. Work with reps to get gateway access. | CenPOS setup screen from Daniel. Test account setup.
Optimizely | C | W | W |  |  |  | [May-15] ANA under review, questions being answered. Test environment for data feeds to be setup early June. ANA for orders was written. ANA [June28 Matt] Optimizely ANA approved by Amy B. | [Apr-26] Dean to put updated specification on Infor sharepoint.

## Sheet1 (hidden)
Count of Interface ID | Column Labels
Row Labels | 3 - Speccing (ANA-050) | 4 - Tech Spec (TAR-040) | 5 - Development | 6 - Development Testing | Business Testing | (blank) | Grand Total
BoA Shared Service (AP) |  |  | 2 |  |  |  | 2
CenPos |  |  |  |  | 2 |  | 2
Cforia | 5 | [5 empty] | 5
Concur | 2 | 3 |  | 1 |  |  | 6
Fedex |  | 2 |  |  |  |  | 2
Optimizely | 5 | 1 |  |  |  |  | 6
Salesforce |  |  |  |  | 2 |  | 2
SPS Commerce EDI | 1 | 4 |  | 1 |  | 1 | 7
UPS |  | 2 |  |  |  |  | 2
(SPS) PNC Bank (AR) | 2 | [5 empty] | 2
PNC Bank (AR) (SPS) | 1 | [5 empty] | 1
Grand Total | 16 | 12 | 2 | 2 | 4 | 1 | 37
| m | t | w | th | f
| BoA | SPS | ups | optimizely
| Cforia |  | fedex | CenPos
Concur
(SPS) PNC Bank (AR)
PNC Bank (AR) (SPS)

## List
Partner/System | Interface ID | Interface | 100% Complete | Stream | Accountable | Barnes Functional | Barnes technical | Status | Action | Process Status | SPS Status | SPS Variable | Totals # of days | SPS + Status | Estimated Completion Date | Infor FC | 3P Development | Functional Spec ANA-050 | Action - Approved | ANA-050 Date Due | Date Complete | Infor Tech Consultant | Interface spec TAR-040 | Action | Date Approved | Date Due | Date Completed | Dev Start | Dev Complate | TES-070 | Testing | Action | Testing Start | Testing Completed | DES-030 Deployment | DES-030 Notes | Comment/Notes | Next action, who and date
(SPS) PNC Bank (AR) | FIN001 | PNC Lockbox EDI 823 checks | No | Finance | Infor | Kim | Jeff | Pre Development | SPS | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Dennis |  | WIP | Kim | 2024-09-27 |  | TBD | [14 empty] | 09/16 Dennis to completing review of EDI 823 and 820 mappings by EOD 09/20. ANA-050 to follow completion approx 09/25. 08/27 Dennis had a meeting with PNC and Barnes and SPS. PNC Bank discussed the scope with Barnes 08/08 Dennis initiated weekly recurring calls to track progress. Dean to get the JBA and PNC together to discuss the current process and required specs. | PNC Bank(Wendella) & SPS Commerce (Courney/Zach) +Dennis for ANA-050 | Testing in progress by Barnes | FIN001 (SPS) PNC Bank (AR) PNC Lockbox EDI 823 checks Finance | CON001 Concur SupplierInvoice Finance
(SPS) PNC Bank (AR) | FIN005 | PNC Lockbox EDI820 flat file ACH ad wires | No | Finance | Infor | Kim | Jeff | Pre Development | SPS | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Dennis |  | WIP |  | 2024-09-27 |  | TBD | [14 empty] | 09/16 Dennis to completing review of EDI 823 and 820 mappings by EOD 09/20. ANA-050 to follow completion approx 09/25. 08/27 Dennis had a meeting with PNC and Barnes and SPS. PNC Bank discussed the scope with Barnes New file that we found out 20230123, sample file in share point, modified for barnes, we should get stdEDI 820 from bank. Via SPS Commerce? | PNC Bank(Wendella) & SPS Commerce (Courney/Zach) +Dennis for ANA-050 |  | FIN005 (SPS) PNC Bank (AR) PNC Lockbox EDI820 flat file ACH ad wires Finance | CON002 Concur Goods Receipts Finance
BoA Shared Service (AP) | FIN003 | Check Run Header | No | Finance | Infor | Kim | Jeff | Pending Approval | Finance | Development |  |  | 15 | 15 | 2026-10-15 | Carlo |  | Completed |  |  |  | Isaiah John Tolentino | Completed |  |  |  |  | 2024-09-13 | 2024-10-11 | [7 empty] | September 25. Dev almost complete. Sent to Carlo for validation. Carlo need to reply ASAP for dev to continue. Sep 13. Dev started. Redy by Oct 11 8/27 - Carlo sent ANA-50 for approval to Finance 20 Aug - Dean needs to approve Ahmed start func spec after PNC | Carlo Alcazar |  | FIN003 BoA Shared Service (AP) Check Run Header Finance | CON003 Concur PO Header Finance
BoA Shared Service (AP) | FIN004 | Check Run Details | No | Finance | Infor | Kim | Jeff | Pending Approval | Finance | Development |  |  | 15 | 15 | 2026-10-15 | Carlo |  | Completed |  |  |  | Isaiah John Tolentino | Completed |  |  |  |  | 2024-09-13 | 2024-10-11 | [7 empty] | September 25. Dev almost complete. Sent to Carlo for validation. Carlo need to reply ASAP for dev to continue. Sep 13. Dev started. Redy by Oct 11 8/27 - Carlo sent ANA-50 for approval to Finance 20 Aug - Dean needs to approve Ahmed start func spec after PNC | Carlo Alcazar |  | FIN004 BoA Shared Service (AP) Check Run Details Finance | CON004 Concur PO Lines Finance
CenPos | CNP001 | Payment Authorization | Yes | OTC | Infor | Amy B / Louis | Dean | Testing | Finance | Business Testing |  |  | 2 | 2 | 2026-10-02 | Hubert |  | NA |  |  |  | N/A | NA | [12 empty] | NA | August - Infor Standard Integration (OOB) Unknown date > existing Infor CenPos code. this team to verify that it works for Barnes. Hubert/Cheska to test CenPos. 7/18. only Dev person is needed if Hubert/Cheska see need for a change. Unknown date > H5 script, manage in UI. Waiting for contact at Barnes and Worldpay | Infor (Hubert/Daniel) |  | CNP001 CenPos Payment Authorization OTC | CON005 Concur Vendor Infor Finance
CenPos | CNP002 | Payment Capture | Yes | OTC | Infor | Amy B / Louis | Dean | Testing | Finance | Business Testing |  |  | 2 | 2 | 2026-10-02 | Hubert |  | NA |  |  |  | N/A | NA | [12 empty] | NA | August - Infor Standard Integration (OOB) Unknown date > existing Infor CenPos code. this team to verify that it works for Barnes. Hubert/Cheska to test CenPos. 7/18. only Dev person is needed if Hubert/Cheska see need for a change. H5 script, manage in UI. Waiting for contact at Barnes and Worldpay | Infor (Hubert/Daniel) | Testing in progress by Barnes | CNP002 CenPos Payment Capture OTC | SFDC01 Salesforce Item OTC
Salesforce | SFDC02 | Customer |  | OTC | Barnes | Robert | Torbjörn | Out of Scope |  | Out of Scope |  |  | 60 | 60 | 2026-11-29 |  |  | NA | 2024-02-27 |  |  | Martin |  | Martin | [8 empty] | Daniel/Martin |  |  | Martin | ANA-050 started ready for review Feb 2 20240126: Meeting anc coclusion is no integration between M3 ans SF. All is going between SF _ Azure •3/20 no longer needed | Martin |  | SFDC02 Salesforce Customer OTC | SFDC02 Salesforce Customer OTC
Salesforce | SFDC03 | ShipToPartyMaster / Addresses |  | OTC | Barnes | Robert | Torbjörn | Out of Scope |  | Out of Scope |  |  | 60 | 60 | 2026-11-29 |  |  | NA | 2024-02-27 |  |  | Martin |  | Martin | [8 empty] | Daniel/Martin |  |  | Martin | Credti limit was Removed from scope during CRP. Payment terms on Customer is enought, replaced by ShipToPartyMaster / Addresses. Martin start ANA-050 Jan 29 20240126: Meeting and conclusion is this will not be done in M3CE. Barnes handle the int between SF- AZureDB •3/20 no longer needed | Martin |  | SFDC03 Salesforce ShipToPartyMaster / Addresses OTC | SFDC03 Salesforce Customer Credit OTC
Cforia | CFO001 | Customer Payments & Credits | No | Finance | Barnes | Kim | Dean | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Rachelle |  | WIP |  | 2024-09-30 |  | Martin |  | Dean | [11 empty] | Dean | 09/16 New Infor finance resource Rachelle Malahito onboarded this week to start work on CFORIA ANA-050 Barnes Kevin Alexander starting on this. Barnes Cforia test environment |  | Testing in progress by Barnes | CFO001 Cforia Customer Payments & Credits Finance | SFDC04 Salesforce Item Pricing OTC
Cforia | CFO002 | Customer Order | No | Finance | Barnes | Kim | Dean | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Rachelle |  | WIP |  | 2024-09-30 |  | Martin |  | Dean | [11 empty] | Dean | 09/16 New Infor finance resource Rachelle Malahito onboarded this week to start work on CFORIA ANA-050 Barnes Kevin Alexander starting on this |  |  | CFO002 Cforia Customer Order Finance | EDI001 SPS Commerce EDI EDI Sales Order OTC
Cforia | CFO003 | Customer Master | No | Finance | Barnes | Kim | Dean | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Rachelle |  | WIP |  | 2024-09-30 |  | Martin |  | Dean | [11 empty] | Dean | 09/16 New Infor finance resource Rachelle Malahito onboarded this week to start work on CFORIA ANA-050 Barnes Kevin Alexander starting on this |  |  | CFO003 Cforia Customer Master Finance | EDI002 SPS Commerce EDI EDI Shipment OTC
Cforia | CFO004 | Invoice Payment History | No | Finance | Barnes | Kim | Dean | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Rachelle |  | WIP |  | 2024-09-30 |  | Martin |  | Dean | [11 empty] | Dean | 09/16 New Infor finance resource Rachelle Malahito onboarded this week to start work on CFORIA ANA-050 Barnes Kevin Alexander starting on this |  |  | CFO004 Cforia Invoice Payment History Finance | EDI003 SPS Commerce EDI EDI Sales Order Ack OTC
Cforia | CFO005 | Invoice Copies IDM (PDF) | No | Finance | Barnes | Kim | Dean | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Rachelle |  | WIP |  | 2024-09-30 |  | Martin |  | Karin | [11 empty] | Karin | 09/16 New Infor finance resource Rachelle Malahito onboarded this week to start work on CFORIA ANA-050 Barnes Kevin Alexander starting on this |  |  | CFO005 Cforia Invoice Copies IDM (PDF) Finance | EDI004 SPS Commerce EDI EDI Invoice OTC
Concur | CON002 | Goods Receipts | No | Finance | Barnes | Kim | Kevin | Pre Development |  | Development Testing |  |  | 12 | 12 | 2026-10-12 | Dennis |  | WIP |  | 2024-09-20 |  | Martin |  | Dean | [6 empty] | Business |  |  |  |  | Dean | 09/16 Dennis to complete re-write of ANA-050 by 09/20. This ANA-050 consolidates CON001 002 003 004 and 005 into one document. 8/27 - Currently being tested by Amy/Kimberly Aug 20 Jimmy asked Dean for a test meeting. Metrics from Kim on current ASR match rate (cases we can improve in M3). Unit test plan - try full cycle. Dean to setup meeting Kim/Kevin 8/23: Meeting scheduled for 8/26 | Start week feb 5 |  | CON002 Concur Goods Receipts Finance | EDI005 SPS Commerce EDI EDI Shipment Schedule EDI 862 OTC
Concur | CON003 | PO Header | No | Finance | Barnes | Kim | Kevin | Pre Development |  | Tech Spec (TAR-040) |  |  | 25 | 25 | 2026-10-25 | Dennis |  | WIP |  | 2024-09-20 |  | Martin |  | Dean | [6 empty] | Business |  |  |  |  | Dean | 09/16 Dennis to complete re-write of ANA-050 by 09/20. This ANA-050 consolidates CON001 002 003 004 and 005 into one document. 8/27 - Currently being tested by Amy/Kimberly Aug 20 Jimmy asked Dean for a test meeting. Metrics from Kim on current ASR match rate (cases we can improve in M3). Unit test plan - try full cycle. Dean to setup meeting Kim/Kevin 8/23: Meeting scheduled for 8/26
Concur | CON004 | PO Lines | No | Finance | Barnes | Kim | Kevin | Pre Development |  | Tech Spec (TAR-040) |  |  | 25 | 25 | 2026-10-25 | Dennis |  | WIP |  | 2024-09-20 |  | Martin |  | Dean | [6 empty] | Business |  |  |  |  | Dean | 09/16 Dennis to complete re-write of ANA-050 by 09/20. This ANA-050 consolidates CON001 002 003 004 and 005 into one document. 8/27 - Currently being tested by Amy/Kimberly Aug 20 Jimmy asked Dean for a test meeting. Metrics from Kim on current ASR match rate (cases we can improve in M3). Unit test plan - try full cycle. Dean to setup meeting Kim/Kevin 8/23: Meeting scheduled for 8/26 |  |  | CON004 Concur PO Lines Finance | EDI006 SPS Commerce EDI Planning Schedule EDI 830 OTC
SPS Commerce EDI | EDI007 | Application Advice EDI 824 |  | OTC | Infor | Melissa | Jeff | Out of Scope |  | Out of Scope |  |  | 60 | 60 | 2026-11-29 | Cheska |  | N/A | N/A | N/A | N/A | Martin | N/A |  | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | 8/6/24: this is not part of the SPS Contract so no dev on any side. Review 824, 860 and 997 and in SPS Commerce Portal so no DEV on infor side •Barnes working to get contract with SPS | N/A |  | EDI007 SPS Commerce EDI Application Advice EDI 824 OTC | EDI007 SPS Commerce EDI Application Advice EDI 824 OTC
Concur | CON005 | Vendor Infor | No | Finance | Barnes | Kim | Kevin | Pre Development |  | Tech Spec (TAR-040) |  |  | 25 | 25 | 2026-10-25 | Dennis |  | WIP |  | 2024-09-20 |  | Martin |  | Dean | [6 empty] | Business |  |  |  |  | Dean | 09/16 Dennis to complete re-write of ANA-050 by 09/20. This ANA-050 consolidates CON001 002 003 004 and 005 into one document. 8/27 - Currently being tested by Amy/Kimberly Aug 20 Jimmy asked Dean for a test meeting. Metrics from Kim on current ASR match rate (cases we can improve in M3). Unit test plan - try full cycle. Dean to setup meeting Kim/Kevin 8/23: Meeting scheduled for 8/26 |  | PNC to provide a PM and Resource. Create Scope of Work, Send Approval to Barnes. | CON005 Concur Vendor Infor Finance | FIN001 PNC Bank (AR) PNC Lockbok Finance
Concur | CON001 | SupplierInvoice | Yes | Finance | Infor | Kim | Kevin | Testing |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Dennis |  | WIP |  | 2024-09-20 |  | Jen | Completed |  | Completed |  |  | Completed | 2024-05-03 |  | Business | Amy Kimberly |  |  |  |  | 09/16 Dennis to complete re-write of ANA-050 by 09/20. This ANA-050 consolidates CON001 002 003 004 and 005 into one document. 8/27 - Currently being tested by Amy/Kimberly Aug 20 Jimmy asked Dean for a test meeting. Metrics from Kim on current ASR match rate (cases we can improve in M3). Unit test plan - try full cycle. Dean to setup meeting Kim/Kevin 8/23: Meeting scheduled for 8/26 | Kimberly/Amy +Dennis ANA-050 | -PNC to provide a PM and Resource. Create Scope of Work, Send Approval to Barnes. -Dennis to finalize field mappings for ANA-50 | CON001 Concur SupplierInvoice Finance | FIN002 PNC Bank (AR) PNC Matcher file Finance
Concur | CONO06 | T&E expense posting | No | Finance | Infor | Kim | Kevin | Pre Development |  | Speccing (ANA-050) | [5 empty] | Rachelle |  | WIP |  | 2024-09-30 |  | Martin | [14 empty] | 09/16 New Infor finance resource Rachelle Malahito onboarded this week to start work on CONCUR Expenses ANA-050 | Rachelle ANA-050 | PNC to provide a PM and Resource. Create Scope of Work, Send Approval to Barnes. | CONO06 Concur T&E expense posting Finance
Fedex | FED001 | FedEx Tracking Number Update | No | Supply chain | Infor | Lori | Jeff | Pre Development |  | Tech Spec (TAR-040) |  |  | 25 | 25 | 2026-10-25 | Cheska | WIP | Completed | 2024-06-14 | Completed | 2024-04-25 | Martin | Pending Approval | Dean | [6 empty] | Business | Dean |  |  |  |  | 9/25 - Sample File provided by Dean, Cheska to update ANA-50. Questions: Where is the Custom PO Number in the sample file? it is missing. We begin development once ANA-50 is updated for FedEx and Question answered 9/18 - open questions re database pull from Dean, cheska to reply 8/29 - Daniel has replied that there is only a configuration in both systems to convert the files from CSV to XML, awaiting dean's reply 8/27 - Sent follow up to Dean for the requested connection details. Dean will try to do it next week if not busy. Aug 20 Martin have tested but need test data and test from server 8/6/24: need to have the picking list editted to reflect the barcode scan, will follow up with Peter and Karin for their time | Barnes (Dean) | Need to approve ANA-50 | FED001 Fedex FedEx Tracking Number Update Supply chain | FIN003 Shared Service (AP) Check Run Header Finance
Fedex | FED002 | FedEx Shipping information | Yes | Supply chain | Barnes | Dan | Jeff | Pre Development |  | Tech Spec (TAR-040) |  |  | 25 | 25 | 2026-10-25 |  |  |  | to Sonja, review 3/26 |  |  |  |  | Jeff | [11 empty] | Jeff |  |  | Need to approve ANA-50 | FED002 Fedex FedEx Shipping information Supply chain | FIN004 Shared Service (AP) Check Run Details Finance
Optimizely | OPT006 | Order (email) | No | OTC | Infor | Amy B / Beth W | Dean | Pre Development |  | Tech Spec (TAR-040) |  |  | 25 | 25 | 2026-10-25 | Cheska | WIP | Completed | 2024-06-27 | Completed | 2024-05-18 | Martin | Completed |  |  |  |  | Completed |  |  | Business | [5 empty] | 9/18/ - ready to test, consid to transform file to xml 8/29/24: build from infor side done, ready to test as long as there is an XML file ready to be ingested. 8/20/24: low prioirty on the list, but ready to test as long as consid can map to the XML 8/6/24: no work needed from Infor end, the work is on Consid. Shall we bring Order in Scope or stick to email? possible BODs usage? | Barnes |  | OPT006 Optimizely Order (email) OTC | CFO001 Cforia Customer Payments & Credits Finance
Optimizely | OPT001 | Customer and Addresses | No | OTC | Barnes | Amy B / Beth W | Jeff | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Hubert |  | Completed | [5 empty] | Dean | [11 empty] | Dean | extract azure data for use in optimizely, working call 3/25 |  |  | OPT001 Optimizely Customer and Addresses OTC | CFO002 Cforia Customer Order Finance
Optimizely | OPT002 | Items | No | OTC | Barnes | Amy B / Beth W | Jeff | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Hubert |  | Completed | [5 empty] | Dean | [11 empty] | Dean | ANA050 ready Sep 4 working call 3/25 |  |  | OPT002 Optimizely Items OTC | CFO003 Cforia Customer Master Finance
Optimizely | OPT003 | Std Price, Cust price, Disc | No | OTC | Barnes | Amy B / Beth W | Jeff | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Hubert |  | Completed | [5 empty] | Dean | [11 empty] | Dean | ANA050 ready Sep 4 working call 3/25 |  |  | OPT003 Optimizely Std Price, Cust price, Disc OTC | CFO004 Cforia Invoice Payment History Finance
Optimizely | OPT004 | Tax exemption | No | OTC | Barnes | Amy B / Beth W | Jeff | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Hubert |  | Completed | [5 empty] | Dean | [11 empty] | Dean | ANA050 ready Sep 4 working call 3/25 |  |  | OPT004 Optimizely Tax exemption OTC | CFO005 Cforia Invoice Copies IDM (PDF) Finance
Optimizely | OPT005 | Stock | No | OTC | Barnes | Amy B / Beth W | Jeff | Not Started |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Hubert |  | Completed | [5 empty] | Dean | [11 empty] | Dean | ANA050 ready Sep 4 Sent sample of M3_InventoryCountReport to Dean 240201, working call 3/25 | Can we use BOD? | Dean will try provide mappings for FedEx next week. Currently busy this week. Dean to provide connection details for shared folder | OPT005 Optimizely Stock OTC | FED001 Fedex FedEx Tracking Number Update Supply chain
PNC Bank (AR) (SPS) | FIN002 | PNC Matcher file | No | Finance | Infor | Kim | Jeff | Pre Development |  | Speccing (ANA-050) |  |  | 30 | 30 | 2026-10-30 | Dennis |  | WIP |  | 2024-09-27 |  | Martin | [14 empty] | 09/16 Dennis to complete ANA-050 draft by 09/25 08/27 Dennis had a meeting with PNC and Barnes and SPS. PNC Bank discussed the scope with Barnes 08/08 Dennis initiated weekly recurring calls to track progress. Dean to get the JBA and PNC together to discuss the current process and required specs. | PNC Bank & Infor(Dennis) |  | FIN002 PNC Bank (AR) (SPS) PNC Matcher file Finance | FED002 Fedex FedEx Shipping information Supply chain
Salesforce | SFDC01 | Item | No | OTC | Infor | Torbjörn | Torbjörn | Testing |  | Business Testing |  |  | 2 | 2 | 2026-10-02 | Jen |  | Completed | 2024-02-27 |  |  | Jen | Completed |  | Completed | [5 empty] | Business | Torbjorn |  | Pending Confirmation |  |  | DES-030 ready. DEVFMC should be ready Sep 27 and PartCopy Oct 04 Sept 13 - setting up a new Salesforce environment for testing. Also changing Dev environment, which is the last step. August 27 - Successful Testing with Torbjorn. Testing session planned for Aug 27 with Torbjorn Aug 8 issue fixed and new test session with Torbjörn this week. April 11 - Torbjorn for validation Apri 10 - doc this week, Jen tested Wednesday | Torbjorn | Dean to provide connection details for shared folder | SFDC01 Salesforce Item OTC | UPS001 UPS UPS Tracking Number Update Supply chain
Salesforce | SFDC04 | Item Pricing | No | OTC | Infor | Torbjörn | Torbjörn | Testing |  | Business Testing |  |  | 2 | 2 | 2026-10-02 | Jen |  | Completed | 2024-02-27 |  |  | Jen | Completed |  | Completed | [5 empty] | Business | Torbjorn |  | Pending Confirmation |  |  | DES-030 Ready. DEVFMC should be ready Sep 27 and PartCopy Oct 04 Sept 13 - setting up a new Salesforce environment for testing. Also changing Dev environment, which is the last step. August 27 - Successful Testing with Torbjorn. Testing session planned for Aug 27 with Torbjorn Aug 8 issue fixed and new test session with Torbjörn this week. July 30 -0 pending further testing by Torbjorn April 28 - TST070. Then Hubert to test afert getting access. April 11 - Torbjorn for validate 4/11 April 10 doc this week, jen test wed 4/10 2 Feb - ANA-050 started ready for review Feb 2 | Torbjorn |  | SFDC04 Salesforce Item Pricing OTC | UPS002 UPS UPS Shipping Information Supply chain
SPS Commerce EDI | EDI001 | EDI Sales Order 850 | No | OTC | Infor | Melissa | Jeff | Testing |  | Development Testing | Testing | 10 | 12 | 22 | 2026-10-22 | Cheska | Complete | Completed | 2024-06-17 | Completed | 2024-05-18 | Martin |  |  |  |  | 2024-06-17 |  |  |  | Technical |  | 2024-06-18 |  |  |  | 9/18/24: tested Grainger, SPS to send down MSC and PACCAR 8/29/24: asked SPS commerce to send down one trading partner for testing, cheska to check if there are any issues and process file until invoice. 8/20/24: paased initial test ready to test for SIT 8/16/24: ready to test we need raw files we need more raw files to drop 8/7/24:: infor mec mapping changes done, Infor functional to test 8/6/24: build completed from SPS commerce side, a few mapping needs to be done from infor tech Jeff has a quote from SPS Commerce, need to schedule follow up meeting to review details with Daniel and team •Barnes working to get contract with SPS | SIT | Contact Hubert Santos on updates from testing the standard implementation | EDI001 SPS Commerce EDI EDI Sales Order 850 OTC | WOR001 Worldpay Payment Authorization OTC
SPS Commerce EDI | EDI002 | EDI Shipment 856 | No | OTC | Infor | Melissa | Jeff | Pre Development |  | Tech Spec (TAR-040) |  | 20 | 25 | 45 | 2026-11-14 | Cheska | Complete | Completed | Complete | Completed |  | Martin | WIP | [13 empty] | 9/18/24: tested Grainger, SPS to send down MSC and PACCAR 8/29/24: asked SPS commerce to send down one trading partner for testing, cheska to check if there are any issues and process file until invoice 8/20/24: waiting for SPS commerce to give feedback on structure 8/16/24: completed build from SPS, infor sent out a test xml, waiting for SPS to validate if it passed through or not. 8/9/24: ANA050 uploaded to be reviewed by Barnes 8/6/24: currently with SPS commerce development. This EDI 856 would need to make use of dummy standard packaging to work, this has been agreed on with Sonja, Amy and Melissa. May want to add FYX consultant to team •Barnes working to get contract with SPS | Infor | Contact Hubert Santos on updates from testing the standard implementation | EDI002 SPS Commerce EDI EDI Shipment 856 OTC | WOR002 Worldpay Payment Capture OTC
SPS Commerce EDI | EDI003 | EDI Sales Order Ack | No | OTC | Infor | Melissa | Jeff | Development |  | Speccing (ANA-050) |  | 20 | 30 | 50 | 2026-11-19 | Cheska | Complete | Completed | Complete | Completed |  | Martin | [14 empty] | 9/18/24: tested Grainger, SPS to send down MSC and PACCAR 8/29/24: finished development from SPS end, WIP development from Infor. 8/20/24: need to align development from Infor end 8/7/24: meeting with barnes finished, need to send acknowledgement codes. need to validate with Martin if the current standard bod is using the newest version of the 855 mapping uploaded in concierge. 8/6/24: to be discussed on 8/7/24 with Barnes •Barnes working to get contract with SPS | Infor |  | EDI003 SPS Commerce EDI EDI Sales Order Ack OTC | OPT001 Optimizely Customer and Addresses OTC
SPS Commerce EDI | EDI004 | EDI Invoice | No | OTC | Infor | Melissa | Jeff | Development |  | Tech Spec (TAR-040) |  | 20 | 25 | 45 | 2026-11-14 | Cheska | Complete | Completed | 2024-08-15 | Completed |  | Martin | [14 empty] | 9/18/24: tested Grainger, SPS to send down MSC and PACCAR 8/29/ 24: development done from SPS, testing in progress. asked SPS commerce to send down one trading partner for testing, cheska to check if there are any issues and process file until invoice 8/20/24: SPS to confirm if build is done 8/16/24: ANA050 approved 8/12/24: ANA050 completed, current build is with SPS Commerce 8/6/24: SPS commerce is doing the build as of today •Barnes working to get contract with SPS | Infor |  | EDI004 SPS Commerce EDI EDI Invoice OTC | OPT002 Optimizely Items OTC
SPS Commerce EDI | EDI005 | EDI Shipment Schedule EDI 862 | No | OTC | Infor | Melissa | Jeff | Pre Development |  | Tech Spec (TAR-040) |  | 20 | 25 | 45 | 2026-11-14 | Cheska | Complete | Completed | 2024-06-17 | Completed | 2024-07-01 | Martin | [14 empty] | 9/18/24: tested Grainger, SPS to send down MSC and PACCAR 8/29/24: asked SPS commerce to send down one trading partner for testing, cheska to check if there are any issues and process file until invoice 8/20/24: SPS clarifications cleared, need to send down test data 8/16/24: need more raw data to test 8/7/24:: infor mec mapping changes done, Infor functional to test SPS to send more data for more customers 8/6/24: SPS dev completed, SPS commerce to send in more data for more testing Barnes working to get contract with SPS | Infor |  | EDI005 SPS Commerce EDI EDI Shipment Schedule EDI 862 OTC | OPT003 Optimizely Std Price, Cust price, Disc OTC
SPS Commerce EDI | TBD | DSV | [37 empty] | TBD SPS Commerce EDI DSV | OPT004 Optimizely Tax exemption OTC
SPS Commerce EDI | EDI006 | Planning Schedule EDI 830 | No | OTC | Infor | Melissa | Jeff | Pre Development |  | Tech Spec (TAR-040) | Testing | 10 | 25 | 35 | 2026-11-04 | Cheska | Complete | Completed | 2024-06-17 | Completed | 2024-07-10 | Martin | [10 empty] | 2024-07-19 |  |  |  | 9/18/24: tested Grainger, SPS to send down MSC and PACCAR 8/29/24: asked SPS commerce to send down one trading partner for testing, cheska to check if there are any issues and process file until invoice 8/20/24: SPS clarifications cleared, need to send down test data 8/16/24: need more raw data to test 8/7/24:: infor mec mapping changes done, Infor functional to test SPS to send more data for more customers 8/6/24: SPS dev completed, SPS commerce to send in more data for more testing , only firmed orders are integrated. •Barnes working to get contract with SPS | Infor |  | EDI006 SPS Commerce EDI Planning Schedule EDI 830 OTC | OPT005 Optimizely Stock OTC
UPS | UPS002 | UPS Shipping Information | No | Supply chain | Barnes | Dan | Jeff | Pre Development |  | Tech Spec (TAR-040) |  |  | 25 | 25 | 2026-10-25 | Cheska | WIP | Completed | 2024-06-14 | Completed | 2024-04-25 |  | Completed | [12 empty] | Jeff |  |  | Contact Cheska(Infor) for latest updates | UPS002 UPS UPS Shipping Information Supply chain | OPT006 Optimizely Order (email) OTC
UPS | UPS001 | UPS Tracking Number Update | No | Supply chain | Infor | Lori | Jeff | Pre Development |  | Tech Spec (TAR-040) |  |  | 25 | 25 | 2026-10-25 | Cheska | WIP | Completed | 2024-06-14 | Completed | 2024-04-25 | Martin | Completed | [13 empty] | 9/25 - UPS to M3 Integration Interface is completed, ANA-50 and TAR-40 in Sharepoint under "UPS_FedEx" folder 9/18 - open questions re database pull from Dean, cheska to reply 8/29 - Daniel has replied that there is only a configuration in both systems to convert the files from CSV to XML, awaiting dean's reply 8/27 - Sent follow up to Dean for the requested shared folder connection details. Dean will try to do it next week if not busy. Aug 20 Martin have tested but need test data and test from server 8/6/24: need to have the picking list editted to reflect the barcode scan will follow up with Peter and Karin for their time | Barnes (Dean) |  | UPS001 UPS UPS Tracking Number Update Supply chain
Formulas:
Estimated Completion Date = TODAY()+[SPS + Status]
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This has to be confirmed by Barnes
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be confirmed by Barnes

## Action Items (hidden)
Date Added | Integration | Priority | Action | Owner | Due Date | Status | Comment | 2026-09-30
2024-01-12 | SPS Commerce EDI |  | Determine if need to add FYX to project team 1/19: Jeff determined not needed | Jeff | 2024-01-19 | Closed
2024-01-12 | Optimizely |  | Add Petter E to weekly meetings? | Petter S | 2024-01-19 | Closed
2024-01-12 | Worldpay |  | Should Petter be added to Worldpay integration? He was working on Worldpay account creation | Petter S | 2024-01-19 | Closed
2024-01-12 | SPS Commerce EDI |  | Jeff has a quote from SPS Commerce, need to schedule follow up meeting to review details with Daniel and team | Jeff | 2024-01-26 | Closed
2024-01-19 | Concur |  | Schedule Barnes/Infor Meeting for week of 1/22 to align team | Daniel | 2024-01-26 | Closed
2024-03-15 | All |  | Switch testing to 910 | Daniel | 2024-04-05 | Closed | All, Switch testing to 910, Daniel
2024-03-15 | All |  | Need service account created in M3 for file drop | Jeff | 2024-03-22 | closed | All, Need service account created in M3 for file drop, Jeff
2024-01-19 | Worldpay |  | Need info from Erik on contact info within Barnes/Worldpay | Jeff | 2024-01-26 | Closed
2024-01-26 | PNC Lockbox EDI820 flat file ACH ad wires |  | Can we add PNC lockbox 820 to SPS commerce - Add Kim and Dean 2/2: Jeff will instruct SPS to include this | Jeff | 2024-02-02 | closed
2024-02-02 | Concur |  | Emailed Steve to add to packaging standard / packing slip | Sonja | 2024-02-23 | closed | Concur, Emailed Steve to add to packaging standard / packing slip , Sonja
2024-02-02 | Concur |  | Sync of data to Azure | Petter | 2024-02-08 | Closed
2024-08-23 | Concur |  | Create Deployment Spec | Dean | 2024-12-01
2024-08-23 | Salesforce |  | Need to assign Torbjorn and Martin for Deployment | Martin/Torbjorn | 2024-12-01
2024-02-02 | Concur |  | Need to specify which fields from supplier invoice need to match (Delivery note field - PPS300) | Daniel | 2024-02-09 | closed
2024-01-19 | Fedex / UPS |  | Need sample files to test 2/16: Jeff will send files going up today. | Jeff | 2024-01-26 | Closed | Fedex / UPS, Need sample files to test 2/16: Jeff will send files going up today. , Jeff
2024-08-23 | Concur |  | Need test script for integration | Dan Tuller | 2024-10-01
2024-01-19 | Fedex / UPS | 1 | Draft functional spec ready to review with Barnes | Cheska | 2024-03-15 | closed | Fedex / UPS, Draft functional spec ready to review with Barnes, Cheska
2024-08-23 | (SPS) PNC Bank (AR) |  | Need to complete ANA-050 | Dennis | 2024-09-03
2024-02-23 | Concur |  | Setup SFTP for data transfer | Karin | 2024-03-01 | Closed | Concur, Setup SFTP for data transfer, Karin
2024-08-26 | (SPS) PNC Bank (AR) |  | Complete TAR |  | 2024-09-03
2024-03-08 | Fedex / UPS |  | Need to review mapping to/from JBA | Cheska | 2024-03-15 | closed | Fedex / UPS, Need to review mapping to/from JBA, Cheska
2024-01-19 | Salesforce |  | Martin working on specs, will review with functional team when ready with Barnes | Martin | 2024-02-16 | closed
2024-02-02 | Salesforce | 1 | Need to review with Torbjörn when he returns | Martin | 2024-02-20 | closed | Salesforce, Need to review with Torbjörn when he returns, Martin
2024-02-16 | Salesforce | 1 | Daniel sent out functional spec, need Barnes review/approval | Dean | 2024-02-23 | closed | Salesforce, Daniel sent out functional spec, need Barnes review/approval, Dean
2024-08-26 | BoA Shared Service (AP) |  | Complete TAR | Isaiha | 2024-09-13
2024-08-23 | BoA Shared Service (AP) (details |  | Need to complete ANA-050 | Dennis | 2024-09-03
2024-03-22 | Optimizely |  | Send M3 Project Timeline to Optimizely | Sonja | 2024-03-28 | closed
2024-01-19 | Worldpay |  | Need a call with Worldpay to understand technical details & setup account - Jeff, Amy B, Daniel, Catherine L, Sonja | Annastasia | 2024-02-23 | closed | Worldpay, Need a call with Worldpay to understand technical details & setup account - Jeff, Amy B, Daniel, Catherine L, Sonja, Annastasia
2024-02-16 | Worldpay |  | functional spec | Daniel | 2024-03-15 | closed | Worldpay, functional spec, Daniel
2024-01-19 | BoA Shared Service (AP) (header) | 3 | Will start functional spec after Cforia | Dennis | 2024-09-03
2024-08-26 | BoA Shared Service (AP) (header) |  | Complete TAR | isiaha | 2024-09-03
2024-08-26 | CenPos |  | ready for testing | Hubert | 2024-09-03
2024-03-15 | Fedex / UPS |  | Schedule functional spec review 4/12 was reviewed, but need functional Barnes approval. Will add Lori to meeting | Sonja | 2024-04-19 | closed | Dean to get signoff from Aaron
2024-03-08 | Salesforce |  | Identify new functional lead to replace lindsey listing Robert as replacement until another is identified | Sonja | 2024-03-15 | closed
2024-01-19 | Cforia | 4 | Start functional spec in Feb, not started, will start after Concur & PNC | Dennis | 2024-09-03 | Not Started | Cforia, Start functional spec in Feb, not started, will start after Concur & PNC, Dennis
2024-03-15 | Fedex / UPS |  | Jeff to set up test machine with both UPS and Fedex, send machine name to Dean 8/26: Dean has machine name and IP address | Jeff | 2024-03-22 | closed | UPS - Jeff - Still in registration process, Jeff will send IP
2024-01-26 | Cforia | 4 | Kevin is starting the technical spec, next step to find missing fields | Kevin | 2024-09-03 | Started | Cforia, Kevin is starting the technical spec, next step to find missing fields, Kevin
2024-01-26 | Concur | 1 | Jane W is starting technical spec, mapping in process | Jane | 2024-09-03 | Started | Concur, Jane W is starting technical spec, mapping in process, Jane
2024-03-15 | SPS Commerce EDI |  | Finalize agreement with SPS | Sonja | 2024-03-22 | Closed
2024-02-23 | Worldpay |  | Getting transaction & value info from Maumee. Qty sent, waiting on $ | Annastasia | 2024-03-22 | Closed
2024-02-16 | Concur | 1 | functional spec - schedule review for week of 3/18 4/12 - did this happen last week? 8/26: Schedule approval/review of ANA-050 | Kim | 2024-09-03 |  | Concur, functional spec - schedule review for week of 3/18 4/12 - did this happen last week? 8/26: Schedule approval/review of ANA-050, Kim
2024-02-16 | Optimizely | 1 | Sales order automation option? follow up sent 3/8 3/22: Glenn will be sending Europe setup to model the same | Annastasia | 2024-04-05 | closed | Optimizely, Sales order automation option? follow up sent 3/8 3/22: Glenn will be sending Europe setup to model the same, Annastasia
2024-08-26 | Fedex / UPS |  | Schedule separate meeting with Dean, Jeff, Daniel, Cheska, Petter, cc Sonja | Jeff | 2024-09-03
2024-01-19 | Optimizely | 1 | Start on extracts / technical spec | Dean | 2024-09-03 | working through current bugs | Optimizely, Start on extracts / technical spec, Dean
2024-01-19 | Optimizely | 1 | Start on functional spec 3/22: Need more info on how new customers are handled (dummy acct or all new?) | Hubert | 2024-09-03 |  | Optimizely, Start on functional spec 3/22: Need more info on how new customers are handled (dummy acct or all new?), Hubert
2024-03-15 | Optimizely |  | Need test environment setup | Robert Thompson | 2024-09-03
2024-08-23 | PNC Bank (AR) |  | Need to complete ANA-050 | Dennis | 2024-09-03
2024-08-26 | PNC Bank (AR) |  | Complete TAR | Martin | 2024-09-03
2024-08-26 | SPS Commerce EDI |  | Need data files | Jeff | 2024-09-03
2024-08-26 | SPS Commerce EDI |  | Need approval/review of ANA-050 | Melissa/Jeff | 2024-09-03
2024-03-08 | Salesforce |  | Need to create connection from Salesforce and Azure, low priority | Dean | 2024-04-12 | closed
2024-08-23 | Salesforce |  | Need to schedule testing with Torbjorn | Torbjorn | 2024-08-30
2024-08-23 | Salesforce |  | Need to approve TAR | Torbjorn | 2024-08-30
2024-08-29 | CenPos |  | Hubert to verify with Daniel if ANA-050 is needed, this is standard for M3 | Hubert | 2024-08-30
2024-01-19 | SPS Commerce EDI |  | Need to start the functional spec | Cheska | 2024-04-12 | closed
2024-03-08 | Salesforce |  | Finalize for testing, Torbjörn requested additional testing Need pricing and products addressed | Martin | 2024-08-27 |  | In process, see List for comments
2024-08-23 | Concur |  | testing scheduled for 8/26 | Sonja | 2024-08-26
2024-02-16 | Fedex / UPS | 1 | Can we connect UPS/Fedex to Azure? - Schedule call with Dean | Dean | 2024-04-05 | Need test machine | Fedex / UPS, Can we connect UPS/Fedex to Azure? - Schedule call with Dean , Dean
2024-06-14 | SPS Commerce EDI |  | Amazon interface today is a homegrown system, need to identify who knows about this interface | Dean

## Sheet2 (hidden)
CON001 Concur SupplierInvoice Finance | CON001
CON001 - ANA-50 - Func Spec | CON002 |  |  | CON001 | - ANA-50 - Func Spec | CON001 - ANA-50 - Func Spec
CON001 - TAR-040 - Tech Spec | CON003 |  |  | CON001 | - TAR-040 - Tech Spec | CON001 - TAR-040 - Tech Spec
CON001 - TES-070 - Tech Spec | CON004 |  |  | CON001 | - TES-070 - Tech Spec | CON001 - TES-070 - Tech Spec
CON001 - DES-030 - Tech Spec | CON005 |  |  | CON001 | - DES-030 - Tech Spec | CON001 - DES-030 - Tech Spec
CON002 Concur Goods Receipts Finance | SFDC01 |  |  | CON002 | - ANA-50 - Func Spec | CON002 - ANA-50 - Func Spec
CON002 - ANA-50 - Func Spec | SFDC02 |  |  | CON002 | - TAR-040 - Tech Spec | CON002 - TAR-040 - Tech Spec
CON002 - TAR-040 - Tech Spec | SFDC03 |  |  | CON002 | - TES-070 - Tech Spec | CON002 - TES-070 - Tech Spec
CON002 - TES-070 - Tech Spec | SFDC04 |  |  | CON002 | - DES-030 - Tech Spec | CON002 - DES-030 - Tech Spec
CON002 - DES-030 - Tech Spec | EDI001 |  |  | CON003 | - ANA-50 - Func Spec | CON003 - ANA-50 - Func Spec
CON003 Concur PO Header Finance | EDI002 |  |  | CON003 | - TAR-040 - Tech Spec | CON003 - TAR-040 - Tech Spec
CON003 - ANA-50 - Func Spec | EDI003 |  |  | CON003 | - TES-070 - Tech Spec | CON003 - TES-070 - Tech Spec
CON003 - TAR-040 - Tech Spec | EDI004 |  |  | CON003 | - DES-030 - Tech Spec | CON003 - DES-030 - Tech Spec
CON003 - TES-070 - Tech Spec |  |  |  | CON004 | - ANA-50 - Func Spec | CON004 - ANA-50 - Func Spec
CON003 - DES-030 - Tech Spec |  |  |  | CON004 | - TAR-040 - Tech Spec | CON004 - TAR-040 - Tech Spec
CON004 Concur PO Lines Finance |  |  |  | CON004 | - TES-070 - Tech Spec | CON004 - TES-070 - Tech Spec
CON004 - ANA-50 - Func Spec |  |  |  | CON004 | - DES-030 - Tech Spec | CON004 - DES-030 - Tech Spec
CON004 - TAR-040 - Tech Spec |  |  |  | CON005 | - ANA-50 - Func Spec | CON005 - ANA-50 - Func Spec
CON004 - TES-070 - Tech Spec |  |  |  | CON005 | - TAR-040 - Tech Spec | CON005 - TAR-040 - Tech Spec
CON004 - DES-030 - Tech Spec |  |  |  | CON005 | - TES-070 - Tech Spec | CON005 - TES-070 - Tech Spec
CON005 Concur Vendor Infor Finance |  |  |  | CON005 | - DES-030 - Tech Spec | CON005 - DES-030 - Tech Spec
CON005 - ANA-50 - Func Spec |  |  |  | SFDC01 | - ANA-50 - Func Spec | SFDC01 - ANA-50 - Func Spec
CON005 - TAR-040 - Tech Spec |  |  |  | SFDC01 | - TAR-040 - Tech Spec | SFDC01 - TAR-040 - Tech Spec
CON005 - TES-070 - Tech Spec |  |  |  | SFDC01 | - TES-070 - Tech Spec | SFDC01 - TES-070 - Tech Spec
CON005 - DES-030 - Tech Spec |  |  |  | SFDC01 | - DES-030 - Tech Spec | SFDC01 - DES-030 - Tech Spec
SFDC01 Salesforce Item OTC |  |  |  | SFDC02 | - ANA-50 - Func Spec | SFDC02 - ANA-50 - Func Spec
SFDC01 - ANA-50 - Func Spec |  |  |  | SFDC02 | - TAR-040 - Tech Spec | SFDC02 - TAR-040 - Tech Spec
SFDC01 - TAR-040 - Tech Spec |  |  |  | SFDC02 | - TES-070 - Tech Spec | SFDC02 - TES-070 - Tech Spec
SFDC01 - TES-070 - Tech Spec |  |  |  | SFDC02 | - DES-030 - Tech Spec | SFDC02 - DES-030 - Tech Spec
SFDC01 - DES-030 - Tech Spec |  |  |  | SFDC03 | - ANA-50 - Func Spec | SFDC03 - ANA-50 - Func Spec
SFDC02 Salesforce Customer OTC |  |  |  | SFDC03 | - TAR-040 - Tech Spec | SFDC03 - TAR-040 - Tech Spec
SFDC02 - ANA-50 - Func Spec |  |  |  | SFDC03 | - TES-070 - Tech Spec | SFDC03 - TES-070 - Tech Spec
SFDC02 - TAR-040 - Tech Spec |  |  |  | SFDC03 | - DES-030 - Tech Spec | SFDC03 - DES-030 - Tech Spec
SFDC02 - TES-070 - Tech Spec |  |  |  | SFDC04 | - ANA-50 - Func Spec | SFDC04 - ANA-50 - Func Spec
SFDC02 - DES-030 - Tech Spec |  |  |  | SFDC04 | - TAR-040 - Tech Spec | SFDC04 - TAR-040 - Tech Spec
SFDC03 Salesforce Customer Credit OTC |  |  |  | SFDC04 | - TES-070 - Tech Spec | SFDC04 - TES-070 - Tech Spec
SFDC03 - ANA-50 - Func Spec |  |  |  | SFDC04 | - DES-030 - Tech Spec | SFDC04 - DES-030 - Tech Spec
SFDC03 - TAR-040 - Tech Spec |  |  |  | EDI001 | - ANA-50 - Func Spec | EDI001 - ANA-50 - Func Spec
SFDC03 - TES-070 - Tech Spec |  |  |  | EDI001 | - TAR-040 - Tech Spec | EDI001 - TAR-040 - Tech Spec
SFDC03 - DES-030 - Tech Spec |  |  |  | EDI001 | - TES-070 - Tech Spec | EDI001 - TES-070 - Tech Spec
SFDC04 Salesforce Item Pricing OTC |  |  |  | EDI001 | - DES-030 - Tech Spec | EDI001 - DES-030 - Tech Spec
SFDC04 - ANA-50 - Func Spec |  |  |  | EDI002 | - ANA-50 - Func Spec | EDI002 - ANA-50 - Func Spec
SFDC04 - TAR-040 - Tech Spec |  |  |  | EDI002 | - TAR-040 - Tech Spec | EDI002 - TAR-040 - Tech Spec
SFDC04 - TES-070 - Tech Spec |  |  |  | EDI002 | - TES-070 - Tech Spec | EDI002 - TES-070 - Tech Spec
SFDC04 - DES-030 - Tech Spec |  |  |  | EDI002 | - DES-030 - Tech Spec | EDI002 - DES-030 - Tech Spec
EDI001 SPS Commerce EDI EDI Sales Order OTC |  |  |  | EDI003 | - ANA-50 - Func Spec | EDI003 - ANA-50 - Func Spec
EDI001 - ANA-50 - Func Spec |  |  |  | EDI003 | - TAR-040 - Tech Spec | EDI003 - TAR-040 - Tech Spec
EDI001 - TAR-040 - Tech Spec |  |  |  | EDI003 | - TES-070 - Tech Spec | EDI003 - TES-070 - Tech Spec
EDI001 - TES-070 - Tech Spec |  |  |  | EDI003 | - DES-030 - Tech Spec | EDI003 - DES-030 - Tech Spec
EDI001 - DES-030 - Tech Spec |  |  |  | EDI004 | - ANA-50 - Func Spec | EDI004 - ANA-50 - Func Spec
EDI002 SPS Commerce EDI EDI Shipment OTC |  |  |  | EDI004 | - TAR-040 - Tech Spec | EDI004 - TAR-040 - Tech Spec
EDI002 - ANA-50 - Func Spec |  |  |  | EDI004 | - TES-070 - Tech Spec | EDI004 - TES-070 - Tech Spec
EDI002 - TAR-040 - Tech Spec |  |  |  | EDI004 | - DES-030 - Tech Spec | EDI004 - DES-030 - Tech Spec
EDI002 - TES-070 - Tech Spec |  |  |  | EDI005 | - ANA-50 - Func Spec | EDI005 - ANA-50 - Func Spec
EDI002 - DES-030 - Tech Spec |  |  |  | EDI005 | - TAR-040 - Tech Spec | EDI005 - TAR-040 - Tech Spec
EDI003 SPS Commerce EDI EDI Sales Order Ack OTC |  |  |  | EDI005 | - TES-070 - Tech Spec | EDI005 - TES-070 - Tech Spec
EDI003 - ANA-50 - Func Spec |  |  | EDI005 | EDI005 | - DES-030 - Tech Spec | EDI005 - DES-030 - Tech Spec
EDI003 - TAR-040 - Tech Spec |  |  | EDI006 | EDI006 | - ANA-50 - Func Spec | EDI006 - ANA-50 - Func Spec
EDI003 - TES-070 - Tech Spec |  |  | EDI007 | EDI006 | - TAR-040 - Tech Spec | EDI006 - TAR-040 - Tech Spec
EDI003 - DES-030 - Tech Spec |  |  | FIN001 | EDI006 | - TES-070 - Tech Spec | EDI006 - TES-070 - Tech Spec
EDI004 SPS Commerce EDI EDI Invoice OTC |  |  | FIN002 | EDI006 | - DES-030 - Tech Spec | EDI006 - DES-030 - Tech Spec
EDI004 - ANA-50 - Func Spec |  |  | FIN003 | EDI007 | - ANA-50 - Func Spec | EDI007 - ANA-50 - Func Spec
EDI004 - TAR-040 - Tech Spec |  |  | FIN004 | EDI007 | - TAR-040 - Tech Spec | EDI007 - TAR-040 - Tech Spec
EDI004 - TES-070 - Tech Spec |  |  | CFO001 | EDI007 | - TES-070 - Tech Spec | EDI007 - TES-070 - Tech Spec
EDI004 - DES-030 - Tech Spec |  |  | CFO002 | EDI007 | - DES-030 - Tech Spec | EDI007 - DES-030 - Tech Spec
EDI005 SPS Commerce EDI EDI Shipment Schedule EDI 862 OTC |  |  | CFO003 | FIN001 | - ANA-50 - Func Spec | FIN001 - ANA-50 - Func Spec
EDI005 - ANA-50 - Func Spec |  |  |  | FIN001 | - TAR-040 - Tech Spec | FIN001 - TAR-040 - Tech Spec
EDI005 - TAR-040 - Tech Spec |  |  |  | FIN001 | - TES-070 - Tech Spec | FIN001 - TES-070 - Tech Spec
EDI005 - TES-070 - Tech Spec |  |  |  | FIN001 | - DES-030 - Tech Spec | FIN001 - DES-030 - Tech Spec
EDI005 - DES-030 - Tech Spec |  |  |  | FIN002 | - ANA-50 - Func Spec | FIN002 - ANA-50 - Func Spec
EDI006 SPS Commerce EDI Planning Schedule EDI 830 OTC |  |  |  | FIN002 | - TAR-040 - Tech Spec | FIN002 - TAR-040 - Tech Spec
EDI006 - ANA-50 - Func Spec |  |  |  | FIN002 | - TES-070 - Tech Spec | FIN002 - TES-070 - Tech Spec
EDI006 - TAR-040 - Tech Spec |  |  |  | FIN002 | - DES-030 - Tech Spec | FIN002 - DES-030 - Tech Spec
EDI006 - TES-070 - Tech Spec |  |  |  | FIN003 | - ANA-50 - Func Spec | FIN003 - ANA-50 - Func Spec
EDI006 - DES-030 - Tech Spec |  |  |  | FIN003 | - TAR-040 - Tech Spec | FIN003 - TAR-040 - Tech Spec
EDI007 SPS Commerce EDI Application Advice EDI 824 OTC |  |  |  | FIN003 | - TES-070 - Tech Spec | FIN003 - TES-070 - Tech Spec
EDI007 - ANA-50 - Func Spec |  |  |  | FIN003 | - DES-030 - Tech Spec | FIN003 - DES-030 - Tech Spec
EDI007 - TAR-040 - Tech Spec |  |  |  | FIN004 | - ANA-50 - Func Spec | FIN004 - ANA-50 - Func Spec
EDI007 - TES-070 - Tech Spec |  |  |  | FIN004 | - TAR-040 - Tech Spec | FIN004 - TAR-040 - Tech Spec
EDI007 - DES-030 - Tech Spec |  |  |  | FIN004 | - TES-070 - Tech Spec | FIN004 - TES-070 - Tech Spec
FIN001 PNC Bank (AR) PNC Lockbok Finance |  |  |  | FIN004 | - DES-030 - Tech Spec | FIN004 - DES-030 - Tech Spec
FIN001 - ANA-50 - Func Spec |  |  |  | CFO001 | - ANA-50 - Func Spec | CFO001 - ANA-50 - Func Spec
FIN001 - TAR-040 - Tech Spec |  |  |  | CFO001 | - TAR-040 - Tech Spec | CFO001 - TAR-040 - Tech Spec
FIN001 - TES-070 - Tech Spec |  |  |  | CFO001 | - TES-070 - Tech Spec | CFO001 - TES-070 - Tech Spec
FIN001 - DES-030 - Tech Spec |  |  |  | CFO001 | - DES-030 - Tech Spec | CFO001 - DES-030 - Tech Spec
FIN002 PNC Bank (AR) PNC Matcher file Finance |  |  |  | CFO002 | - ANA-50 - Func Spec | CFO002 - ANA-50 - Func Spec
FIN002 - ANA-50 - Func Spec |  |  |  | CFO002 | - TAR-040 - Tech Spec | CFO002 - TAR-040 - Tech Spec
FIN002 - TAR-040 - Tech Spec |  |  |  | CFO002 | - TES-070 - Tech Spec | CFO002 - TES-070 - Tech Spec
FIN002 - TES-070 - Tech Spec |  |  |  | CFO002 | - DES-030 - Tech Spec | CFO002 - DES-030 - Tech Spec
FIN002 - DES-030 - Tech Spec |  |  |  | CFO003 | - ANA-50 - Func Spec | CFO003 - ANA-50 - Func Spec
FIN003 Shared Service (AP) Check Run Header Finance |  |  |  | CFO003 | - TAR-040 - Tech Spec | CFO003 - TAR-040 - Tech Spec
FIN003 - ANA-50 - Func Spec |  |  |  | CFO003 | - TES-070 - Tech Spec | CFO003 - TES-070 - Tech Spec
FIN003 - TAR-040 - Tech Spec |  |  |  | CFO003 | - DES-030 - Tech Spec | CFO003 - DES-030 - Tech Spec
FIN003 - TES-070 - Tech Spec |  |  | CFO004 | CFO004 | - ANA-50 - Func Spec | CFO004 - ANA-50 - Func Spec
FIN003 - DES-030 - Tech Spec |  |  | CFO005 | CFO004 | - TAR-040 - Tech Spec | CFO004 - TAR-040 - Tech Spec
FIN004 Shared Service (AP) Check Run Details Finance |  |  | FED001 | CFO004 | - TES-070 - Tech Spec | CFO004 - TES-070 - Tech Spec
FIN004 - ANA-50 - Func Spec |  |  | FED002 | CFO004 | - DES-030 - Tech Spec | CFO004 - DES-030 - Tech Spec
FIN004 - TAR-040 - Tech Spec |  |  | UPS001 | CFO005 | - ANA-50 - Func Spec | CFO005 - ANA-50 - Func Spec
FIN004 - TES-070 - Tech Spec |  |  | UPS002 | CFO005 | - TAR-040 - Tech Spec | CFO005 - TAR-040 - Tech Spec
FIN004 - DES-030 - Tech Spec |  |  | WOR001 | CFO005 | - TES-070 - Tech Spec | CFO005 - TES-070 - Tech Spec
CFO001 Cforia Customer Payments & Credits Finance |  |  | WOR002 | CFO005 | - DES-030 - Tech Spec | CFO005 - DES-030 - Tech Spec
CFO001 - ANA-50 - Func Spec |  |  |  | FED001 | - ANA-50 - Func Spec | FED001 - ANA-50 - Func Spec
CFO001 - TAR-040 - Tech Spec |  |  |  | FED001 | - TAR-040 - Tech Spec | FED001 - TAR-040 - Tech Spec
CFO001 - TES-070 - Tech Spec |  |  |  | FED001 | - TES-070 - Tech Spec | FED001 - TES-070 - Tech Spec
CFO001 - DES-030 - Tech Spec |  |  |  | FED001 | - DES-030 - Tech Spec | FED001 - DES-030 - Tech Spec
CFO002 Cforia Customer Order Finance |  |  |  | FED002 | - ANA-50 - Func Spec | FED002 - ANA-50 - Func Spec
CFO002 - ANA-50 - Func Spec |  |  |  | FED002 | - TAR-040 - Tech Spec | FED002 - TAR-040 - Tech Spec
CFO002 - TAR-040 - Tech Spec |  |  |  | FED002 | - TES-070 - Tech Spec | FED002 - TES-070 - Tech Spec
CFO002 - TES-070 - Tech Spec |  |  |  | FED002 | - DES-030 - Tech Spec | FED002 - DES-030 - Tech Spec
CFO002 - DES-030 - Tech Spec |  |  |  | UPS001 | - ANA-50 - Func Spec | UPS001 - ANA-50 - Func Spec
CFO003 Cforia Customer Master Finance |  |  |  | UPS001 | - TAR-040 - Tech Spec | UPS001 - TAR-040 - Tech Spec
CFO003 - ANA-50 - Func Spec |  |  |  | UPS001 | - TES-070 - Tech Spec | UPS001 - TES-070 - Tech Spec
CFO003 - TAR-040 - Tech Spec |  |  |  | UPS001 | - DES-030 - Tech Spec | UPS001 - DES-030 - Tech Spec
CFO003 - TES-070 - Tech Spec |  |  |  | UPS002 | - ANA-50 - Func Spec | UPS002 - ANA-50 - Func Spec
CFO003 - DES-030 - Tech Spec |  |  |  | UPS002 | - TAR-040 - Tech Spec | UPS002 - TAR-040 - Tech Spec
CFO004 Cforia Invoice Payment History Finance |  |  |  | UPS002 | - TES-070 - Tech Spec | UPS002 - TES-070 - Tech Spec
CFO004 - ANA-50 - Func Spec |  |  |  | UPS002 | - DES-030 - Tech Spec | UPS002 - DES-030 - Tech Spec
CFO004 - TAR-040 - Tech Spec |  |  |  | WOR001 | - ANA-50 - Func Spec | WOR001 - ANA-50 - Func Spec
CFO004 - TES-070 - Tech Spec |  |  |  | WOR001 | - TAR-040 - Tech Spec | WOR001 - TAR-040 - Tech Spec
CFO004 - DES-030 - Tech Spec |  |  |  | WOR001 | - TES-070 - Tech Spec | WOR001 - TES-070 - Tech Spec
CFO005 Cforia Invoice Copies IDM (PDF) Finance |  |  |  | WOR001 | - DES-030 - Tech Spec | WOR001 - DES-030 - Tech Spec
CFO005 - ANA-50 - Func Spec |  |  |  | WOR002 | - ANA-50 - Func Spec | WOR002 - ANA-50 - Func Spec
CFO005 - TAR-040 - Tech Spec |  |  |  | WOR002 | - TAR-040 - Tech Spec | WOR002 - TAR-040 - Tech Spec
CFO005 - TES-070 - Tech Spec |  |  |  | WOR002 | - TES-070 - Tech Spec | WOR002 - TES-070 - Tech Spec
CFO005 - DES-030 - Tech Spec |  |  |  | WOR002 | - DES-030 - Tech Spec | WOR002 - DES-030 - Tech Spec
FED001 Fedex FedEx Tracking Number Update Supply chain |  |  |  | OPT001 | - ANA-50 - Func Spec | OPT001 - ANA-50 - Func Spec
FED001 - ANA-50 - Func Spec |  |  |  | OPT001 | - TAR-040 - Tech Spec | OPT001 - TAR-040 - Tech Spec
FED001 - TAR-040 - Tech Spec |  | OPT001 |  | OPT001 | - TES-070 - Tech Spec | OPT001 - TES-070 - Tech Spec
FED001 - TES-070 - Tech Spec |  | OPT002 |  | OPT001 | - DES-030 - Tech Spec | OPT001 - DES-030 - Tech Spec
FED001 - DES-030 - Tech Spec |  | OPT003 |  | OPT002 | - ANA-50 - Func Spec | OPT002 - ANA-50 - Func Spec
FED002 Fedex FedEx Shipping information Supply chain |  | OPT004 |  | OPT002 | - TAR-040 - Tech Spec | OPT002 - TAR-040 - Tech Spec
FED002 - ANA-50 - Func Spec |  | OPT005 |  | OPT002 | - TES-070 - Tech Spec | OPT002 - TES-070 - Tech Spec
FED002 - TAR-040 - Tech Spec |  | OPT006 |  | OPT002 | - DES-030 - Tech Spec | OPT002 - DES-030 - Tech Spec
FED002 - TES-070 - Tech Spec |  |  |  | OPT003 | - ANA-50 - Func Spec | OPT003 - ANA-50 - Func Spec
FED002 - DES-030 - Tech Spec |  |  |  | OPT003 | - TAR-040 - Tech Spec | OPT003 - TAR-040 - Tech Spec
UPS001 UPS UPS Tracking Number Update Supply chain |  |  |  | OPT003 | - TES-070 - Tech Spec | OPT003 - TES-070 - Tech Spec
UPS001 - ANA-50 - Func Spec |  |  |  | OPT003 | - DES-030 - Tech Spec | OPT003 - DES-030 - Tech Spec
UPS001 - TAR-040 - Tech Spec |  |  |  | OPT004 | - ANA-50 - Func Spec | OPT004 - ANA-50 - Func Spec
UPS001 - TES-070 - Tech Spec |  |  |  | OPT004 | - TAR-040 - Tech Spec | OPT004 - TAR-040 - Tech Spec
UPS001 - DES-030 - Tech Spec |  |  |  | OPT004 | - TES-070 - Tech Spec | OPT004 - TES-070 - Tech Spec
UPS002 UPS UPS Shipping Information Supply chain |  |  |  | OPT004 | - DES-030 - Tech Spec | OPT004 - DES-030 - Tech Spec
UPS002 - ANA-50 - Func Spec |  |  |  | OPT005 | - ANA-50 - Func Spec | OPT005 - ANA-50 - Func Spec
UPS002 - TAR-040 - Tech Spec |  |  |  | OPT005 | - TAR-040 - Tech Spec | OPT005 - TAR-040 - Tech Spec
UPS002 - TES-070 - Tech Spec |  |  |  | OPT005 | - TES-070 - Tech Spec | OPT005 - TES-070 - Tech Spec
UPS002 - DES-030 - Tech Spec |  |  |  | OPT005 | - DES-030 - Tech Spec | OPT005 - DES-030 - Tech Spec
WOR001 Worldpay Payment Authorization OTC |  |  |  | OPT006 | - ANA-50 - Func Spec | OPT006 - ANA-50 - Func Spec
WOR001 - ANA-50 - Func Spec |  |  |  | OPT006 | - TAR-040 - Tech Spec | OPT006 - TAR-040 - Tech Spec
WOR001 - TAR-040 - Tech Spec |  |  |  | OPT006 | - TES-070 - Tech Spec | OPT006 - TES-070 - Tech Spec
WOR001 - TES-070 - Tech Spec |  |  |  | OPT006 | - DES-030 - Tech Spec | OPT006 - DES-030 - Tech Spec
WOR001 - DES-030 - Tech Spec
WOR002 Worldpay Payment Capture OTC
WOR002 - ANA-50 - Func Spec
WOR002 - TAR-040 - Tech Spec
WOR002 - TES-070 - Tech Spec
WOR002 - DES-030 - Tech Spec
OPT001 Optimizely Customer and Addresses OTC
OPT001 - ANA-50 - Func Spec
OPT001 - TAR-040 - Tech Spec
OPT001 - TES-070 - Tech Spec
OPT001 - DES-030 - Tech Spec
OPT002 Optimizely Items OTC
OPT002 - ANA-50 - Func Spec
OPT002 - TAR-040 - Tech Spec
OPT002 - TES-070 - Tech Spec
OPT002 - DES-030 - Tech Spec
OPT003 Optimizely Std Price, Cust price, Disc OTC
OPT003 - ANA-50 - Func Spec
OPT003 - TAR-040 - Tech Spec
OPT003 - TES-070 - Tech Spec |  |  | OPT006 - ANA-50 - Func Spec
OPT003 - DES-030 - Tech Spec |  |  | OPT006 - TAR-040 - Tech Spec
OPT004 Optimizely Tax exemption OTC |  |  | OPT006 - TES-070 - Tech Spec
OPT004 - ANA-50 - Func Spec |  |  | OPT006 - DES-030 - Tech Spec
OPT004 - TAR-040 - Tech Spec
OPT004 - TES-070 - Tech Spec
OPT004 - DES-030 - Tech Spec
OPT005 Optimizely Stock OTC
OPT005 - ANA-50 - Func Spec
OPT005 - TAR-040 - Tech Spec
OPT005 - TES-070 - Tech Spec
OPT005 - DES-030 - Tech Spec
OPT006 Optimizely Order (email) OTC
OPT006 - ANA-050 - Func Spec
OPT006 - TAR-040 - Tech Spec
OPT006 - TES-070 - Tech Spec
OPT006 - DES-030 - Tech Spec

## Barnes Project Plan
Interface | Priority | Phase | Category | Task | Status | Due Date | Org | Owner | Note
Bank of America (AP) |  | 0 - Doc | 0 - ANA-050 | ANA-050 - Ready for Review | Complete | 2024-08-30 | I | Carlo Alcazar
Bank of America (AP) | * | 0 - Doc | 1 - ANA-050 | ANA-050 - Signoff | Complete | 2024-09-06 | B | Kim Diorio | Agreed approved in Meeting 9/23/2024
Bank of America (AP) |  | 0 - Doc | 2 - TAR-040 | TAR-040 - Ready for Review | Complete | 2024-09-13 | I | Isaiah Tolentino
Bank of America (AP) |  | 0 - Doc | 3 - TEST-070 | Unit Test Plan | Not Started | 2024-10-18 | B | Kim Diorio
Bank of America (AP) |  | 0 - Doc | 4- DOC COMPLETE |  | In Progress
Bank of America (AP) |  | 1 - Dev | Dev | Header file for checks | Complete |  | I | Isaiah Tolentino | 10/2 Wed - Martin on 9/30 9a call
Bank of America (AP) | * | 1 - Dev | Dev | Detail file for checks | Complete | 2024-09-27 | I | Isaiah Tolentino | 10/2 Wed - Martin on 9/30 9a call
Bank of America (AP) | * | 1 - Dev | Dev | Header file for ACH | Complete | 2024-09-27 | I | Isaiah Tolentino | 10/2 Wed - Martin on 9/30 9a call
Bank of America (AP) | * | 1 - Dev | Dev | Detail file for ACH | Complete | 2024-09-27 | I | Isaiah Tolentino | 10/2 Wed - Martin on 9/30 9a call
Bank of America (AP) |  | 1 - Deb | Dev | Send sample files to Barnes | In Progress | 2024-10-01 | I | Isaiah Tolentino
Bank of America (AP) | * | 1 - Dev | Dev | SSIS: Transfer files to Industrial JBA box for transmission (weekly) | Await files | 2024-10-11 | B | Kevin Alexander
Bank of America (AP) |  | 2 - Test | UAT | UAT Ready | On Track | 2024-10-18 | B | Dean Amo
Bank of America (AP) |  | 2 - Test | Unit Test 001 | Makes it to Barnes Industrial AS/400 - users are able to confirm the details | Not Started | 2024-10-18 | B | Kim Diorio
Bank of America (AP) | Risk | 2 - Test | Unit Test 002 | Test transmission to bank has long lead time | Not Started | 2024-10-18 | B | Kim Diorio
CenPOS |  | 0 - Doc | 0 - ANA-050 | ANA-050 - Ready for Review | Not Required |  | I
CenPOS |  | 0 - Doc | 1 - ANA-050 | ANA-050 - Signoff | Not Required |  | I
CenPOS |  | 0 - Doc | 2 - TAR-040 | TAR-040 Reviewed and approved | Not Required |  | I
CenPOS | * | 0 - Doc | 3 - TEST-070 | Unit Test Plan - CenPOS - contact Hubert for M3 functional questions | Overdue | 2024-09-13 | B | Amy Burgard | *Meeting scheduled Thur 9/26
CenPOS |  | 0 - Doc | 4- DOC COMPLETE
CenPOS | Low | 1 - Dev | Dev | Review test portal login | Complete | 2024-09-27 | B | Dean Amo
CenPOS | Low | 1 - Dev | Dev | Change service account from @infor.com to @asraymond.com | In Progress | 2024-09-27 | B | Dean Amo | Need a DL_CenPos_Administration@onebarnes.com
CenPOS | Low | 1 - Dev | Dev | Update M3 CenPOS connector configuration after account change | Not Started |  |  | Hubert Santos
CenPOS |  | 2 - Test | UAT | Ready for testing | Complete | 2024-06-01 | I | Daniel Lindblad
CenPOS |  | 2 - Test | Unit Test 001 | Charge customer order to test credit card | Complete - Success |  | B | Amy, Melissa
Cforia | * | 0 - Doc | 0 - ANA-050 | ANA-050 - Ready for Review | Overdue | 2024-09-13 | B | Dennis Garrero, Rachelle | 9/30/2024 - New Due Date. 10/9/2024 latest due date from 9/26.
Cforia | * | 0 - Doc | 1 - ANA-050 | ANA-050 - Sign off | Await Dependancy | 2024-10-04 | B | Kim Diorio / Kevin Alexander
Cforia | * | 0 - Doc | 2 - TAR-040 | TAR-040 Reviewed and approved | Await Dependancy | 2024-10-04 | I | Carlo Alcazar | Awaiting ANA-050
Cforia |  | 0 - Doc | 3 - TEST-070 | Unit Test Plan | Not Started | 2024-10-25 | B | Dean / Kim | *Need output of open A/R report from M3 -Dennis tried on call, output not working
Cforia |  | 0 - Doc | 4 - DOC COMPLETE
Cforia |  | 00 - Doc Req | 2 - TAR-040 | Meeting for missing AR details | Complete |  | T | Dennis / Kevin | Search 'Acc Re' in M3 for open A/R screens
Cforia | * | 1 - Dev | Dev | Modify DW Job, BGIDW_M3_ASR to include AR files | In Progress | 2024-10-18 | B | Kevin Alexander
Cforia |  | 1 - Dev | Dev | Contact Cdoria - ensure test environment is ready |  | 2024-10-04 | B | Kevin Alexander
Cforia |  | 1 - Dev | Dev | Build ARCASH.TXT exoport | In Progress | 2024-10-25 | B | Kevin Alexander
Cforia |  | 1 - Dev | Dev | Build ARCUST.TXT exoport | In Progress | 2024-10-25 | B | Kevin Alexander
Cforia |  | 1 - Dev | Dev | Build AREXTI.TXT exoport | In Progress | 2024-10-25 | B | Kevin Alexander
Cforia |  | 1 - Dev | Dev | Build ARMAST.TXT exoport | In Progress | 2024-10-25 | B | Kevin Alexander
Cforia |  | 1 - Dev | Dev | Build ARTRAN.TXT exoport | In Progress | 2024-10-25 | B | Kevin Alexander
Cforia |  | 1 - Dev | Dev - Enahnce | Invoice PDF to archive folder | Not Started |  | B | Karin Fransson
|  | 1 - Dev | Dev | Transmit to Cforia | Not Started | 2024-11-01 | B | Kevin Alexander
Cforia |  | 2 - Test | UAT | UAT Ready | Late | 2024-11-04 | B | Dean Amo
Cforia |  | 2 - Test | Unit Test 001 | Balance to M3 Open A/R report | Not Started
Cforia |  | 2 - Test | Unit Test 001 | View in Cforia for missing details | Not Started
Concur - Invoice | * | 0 - Doc | 0 - ANA-050 | ANA-050 - Payments to M3 - Ready for Review | Overdue | 2024-09-20 | I | Dennis Garrero | 2024-09-24
Concur - Invoice | * | 0 - Doc | 1 - ANA-050 | ANA-050 - Reviewed and approved | Await Dependancy | 2024-09-27 | B | Kim Diorio
Concur - Invoice |  | 0 - Doc | 2 - TAR-040 | TAR-040 Reviewed and approved | Not Started |  |  | Martin
Concur - Invoice |  | 0 - Doc | 3 - TEST-070 | Unit Test Plan | Not Started
Concur - Invoice |  | 0 - Doc | 4 - DOC COMPLETE |  | In Progress
Concur - Invoice |  | 1 - Dev | Dev | OUT: Produce PO Header, Lines, Receipts, Vendor files | Complete | 2024-07-11 | B | Kevin Alexander
Concur - Invoice | * | 1 - Dev | Dev | OUT: Ensure files ingest into Concur | In Progress | 2024-09-27 | B | Dean Amo | Sep-20 - Last import successful, turning on feed Monday (Sep-23) evening run
Concur - Invoice |  | 1 - Dev | Dev | Inbound - Matched Payments to XML BOD drop off | Complete | 2024-07-11 | B | Kevin Alexander
Concur - Invoice |  | 1 - Dev | DEV COMPLETE |  | Complete | 2024-08-22 | B
Concur - Invoice |  | 2 - Test | UAT | UAT Ready | Late | 2024-11-01 | B | Dean Amo
Concur - Invoice |  | 2 - Test | Unit Test 001 | Enter POs in M3 - Compay 910 | Complete |  |  | Kyle Outhouse / Amy McGuire
Concur - Invoice |  | 2 - Test | Unit Test 001 | Receive POs in M3 - Compay 910 | Complete |  |  | Kyle Outhouse / Amy McGuire
Concur - Invoice |  | 2 - Test | Unit Test 001 | Send files to Concur | Complete |  |  | Kevin Alexander
Concur - Invoice |  | 2 - Test | Unit Test 001 | Input simulated vendor Invoice | Complete |  |  | Kim Diorio
Concur - Invoice |  | 2 - Test | Unit Test 001 | Receive matched payments | In Progress | 2024-08-30 | B | Kim Diorio / Keven Alexander
Concur - Invoice |  | 2 - Test | Unit Test 001 | Matched payments to XML BOD in drop off location | Not Started | 2024-08-30 | B | Kevin Alexander
Concur - Invoice |  | 2 - Test | Unit Test 001 | Verify Payments processed into M3 | Not Started | 2024-08-30 | I | Daniel ?
Concur - Invoice |  | 2 - Test | Unit Test 001 | Review Payables | Not Started |  | B | Daniel Tuller
Concur - Invoice |  | 2 - Test | Unit Test 001 COMPLETE |  | In Progress
Concur - Travel & Expense | * | 0 - Doc | 0 - ANA-050 | ANA-050 - Ready for Review | Overdue | 2024-09-30 | I | Dennis Garrero, Rachelle
Concur - Travel & Expense | * | 0 - Doc | 1 - ANA-050 | ANA-050 - Reviewed and approved | Await Dependancy | 2024-09-30 | B | Jesse Keech, Kim Diorio | Review @9a
Concur - Travel & Expense | * | 0 - Doc | 2 - TAR-040 | Concur TAR-040 | In Progress | 2024-10-11 | I | Martin Bautista
Concur - Travel & Expense |  | 0 - Doc | 3 - TEST-070 | Unit Test Plan | Not Started
Concur - Travel & Expense |  | 0 - Doc | 4 - DOC COMPLETE |  | In Progress
Concur - Travel & Expense |  | 00 - Doc Req | 1 - ANA-050 | Schedule overview call with Infor/Finance | Complete |  | B | Dean Amo [Dennis]
Concur - Travel & Expense | * | 00 - Doc Req | 1 - ANA-050 | GLS 840 - Can we use existing format or do we need new? | Not Started | 2024-09-30 | I | Rachelle
Concur - Travel & Expense |  | 00 - Doc Req | 2 - TAR-040 | Sample data with field explainations | Complete |  | B | Kevin Alexander
Concur - Travel & Expense |  | 1 - Dev | Dev | Import flat file into M3 | Not Started |  | I | Rachelle
Concur - Travel & Expense |  | 1 - Dev | Dev | Import flat file into M3 | Not Started |  | B | Kevin Alexander
Concur - Travel & Expense |  | 2 - Test | UAT | UAT Ready | Late | 2024-10-25 | B | Dean Amo
Concur - Travel & Expense |  | 2 - Test | Unit Test 001 | Run production expense through test integration | Not Started |  | B | Kevin Alexander
Concur - Travel & Expense |  | 2 - Test | Unit Test 001 | Validate Process to post data to M3 | Not Started |  | I | ?
Concur - Travel & Expense |  | 2 - Test | Unit Test 001 | Review Payables | Not Started |  | B | Daniel Tuller
FedEx |  | 0 - Doc | 0 - ANA-050 | ANA-050 - Payments to M3 - Ready for Review | Complete | 2024-06-14 | I
FedEx |  | 0 - Doc | 1 - ANA-050 | ANA-050 - Reviewed and approved | Complete | 2024-06-14 | B | Jack Adoline
FedEx |  | 0 - Doc | 2 - TAR-040 | TAR-040 Reviewed and approved | Not Started | 2024-09-06 |  | Martin Bautista
FedEx |  | 0 - Doc | 3 - TEST-070 | Unit Test Plan | Not Started |  | B | Jeff Finch
FedEx |  | 0 - Doc | 4 - DOC COMPLETE |  | In Progress
FedEx | * | 00 - Doc Req | 2 - TAR-040 | Need sample shipments file XML from FedEx production | Complete | 2024-09-27 | B | Dean Amo
FedEx |  | 1 - Dev | Dev | Develop address pull query from data lake | In Progress | 2024-09-20 | B | Dean Amo
FedEx | * | 1 - Dev | Dev | Configure address pull from M3 | In Progress | 2024-09-27 | B | Dean Amo
FedEx | * | 1 - Dev | Dev | Configure XML output and drop off location | In Progress | 2024-10-04 | B | Dean Amo
FedEx |  | 2 - Test | UAT | UAT Ready | On Track - Issue | 2024-10-21 | B | Dean Amo
FedEx |  | 2 - Test | Unit Test 001 | Print pick list from M3 and scan in Ship Manager to pull address/FedEx account | Not Started | 2024-10-11 | B | ?? Process Owner ??
FedEx |  | 2 - Test | Unit Test 002 | Extract XML from shipment of order | Not Started | 2024-10-11 | B | Jeff Finch
FedEx |  | 2 - Test | Unit Test 002 | Load XML into M3 and verify information on order | Not Started | 2024-10-11 | I | Daniel
Optimizely | * | 0 - Doc | 0 - ANA-050 | ANA-050 - Ready for Review | Complete | 2024-09-06 | I | Cheska Acance
Optimizely | * | 0 - Doc | 1 - ANA-050 | ANA-050 - Reviewed and approved | Complete | 2024-09-20 |  | Beth Wilkerson | Approved 9/23/2024 via email
Optimizely |  | 0 - Doc | 2 - TAR-040 | TAR-040 Reviewed and approved | Not Started |  | B | Dean Amo
Optimizely |  | 0 - Doc | 3 - TEST-070 | Unit Test Plan | Not Started |  | B | Beth Wilkerson
Optimizely |  | 0 - Doc | 4 - DOC COMPLETE |  | In Progress
Optimizely |  | 1 - Dev | Dev | OUT: Add price list extract to BGIDW_M3_ASR_Daily.dtsx | Complete | 2024-08-30 | B | Dean Amo
Optimizely | * | 1 - Dev | Dev | OUT: Add inventory extract with gas charge logic | Complete | 2024-09-27 | B | Dean Amo
Optimizely | * | 1 - Dev | Dev | OUT: Produce files from M3 company 910 and load to test | In Progress | 2024-10-04 | B | Dean Amo, Jane Woytach
Optimizely | * | 1 - Dev | Dev | IN: CenPOS integration - schedule CONSID meeting | Overdue | 2024-09-06 | B | Dean Amo, Beth Wilkerson | 9/20 - Discussing requirements
Optimizely |  | 1 - Dev | Dev | IN: CONSID - Update sales order file | In Progress | 2024-10-18 | B |  | 9/20 - Currently analyzing missing data (CC ref. identified)
Optimizely |  | 1 - Dev | Dev | IN: Convert CSV to XML BOD | Not Started | 2024-10-18 | B
Optimizely |  | 1 - Dev | Dev | IN: Verify ingestion of sales order BOD | Not Started | 2024-10-25 | I
Optimizely |  | 1 - Dev | Dev | Contingency - May need to work with CONSID on data load | In Progress | 2024-10-04 | B | Dean Amo
Optimizely - Current State |  | 2 - Test | UAT | UAT Ready | On Track | 2024-10-07 | B | Dean Amo
Optimizely - Order Auto. |  | 2 - Test | UAT | UAT Ready | On Track | 2024-10-28 | B | Dean Amo
Optimizely |  | 2 - Test | Unit Test 001 | Review prices on test web site | Not Started |  | B | Beth Wilkerson
Optimizely |  | 2 - Test | Unit Test 001 | Review stock levels on test web site, check gas spring charge levels | Not Started |  | B | Beth Wilkerson
Optimizely |  | 2 - Test | Unit Test 001 | Credit card process | Not Started |  | B | Beth Wilkerson
Optimizely |  | 2 - Test | Unit Test 001 | Order placement from web to M3 | Not Started |  | B | Beth Wilkerson
PNC Bank (AR) | * | 0 - Doc | 0 - ANA-050 | ANA-050 - Payments to M3 - Ready for Review | In Progress | 2024-09-27 | I | Dennis Garrero
PNC Bank (AR) | * | 0 - Doc | 1 - ANA-050 | ANA-050 - Reviewed and approved | Await Dependancy | 2024-10-04 | B | Kim Diorio
PNC Bank (AR) |  | 0 - Doc | 2 - TAR-040 | TAR-040 Reviewed and approved | In Progress | 2024-10-11 | I | Martin Bautista
PNC Bank (AR) |  | 0 - Doc | 3 - TEST-070 | Unit Test Plan | Not Started
PNC Bank (AR) |  | 0 - Doc | 4 - DOC COMPLETE |  | In Progress
PNC Bank (AR) | ! | 1 - Dev | Dev | Matcher file to CSV | Not Started | 2024-10-11 | I | Dennis Garrero | Open customer invoices
PNC Bank (AR) |  | 1 - Dev | Dev | EDI 820/823 - To SPS Commerce Project Plan | In Progress |  |  |  | **Dean - SPS - Replace Dan with Kim
PNC Bank (AR) |  | 1 - Dev | Dev | Bank test environment | In Progress
Salesforce |  | 0 - Doc | 0 - ANA-050 | ANA-050 - Ready for Review | Complete | 2024-09-06 | I | Martin Bautista
Salesforce |  | 0 - Doc | 1 - ANA-050 | ANA-050 - Reviewed and approved | Complete |  |  | Torbjörn Sundbrandt
Salesforce |  | 0 - Doc | 2 - TAR-040 | TAR-040 Reviewed and approved | Complete |  | I | Martin Bautista
Salesforce | * | 0 - Doc | 3 - TEST-070 | Unit Test Plan | In Progress | 2024-09-27 | B | Torbjörn Sundbrandt
Salesforce |  | 0 - Doc | 4 - DOC COMPLETE |  | In Progress
Salesforce |  | 1 - Dev | Dev | Configure M3 to Salesforce connector | Complete |  | I | Martin Bautista
Salesforce |  | 1 - Dev | Dev | Verify any open items agains ANA/TAR | Not Started | 2024-09-04 | B | Dean, Torborjn, Martin
Salesforce |  | 2 - Test | UAT | UAT Ready | Complete | 2024-09-09 | B | Daniel Lindblad
Salesforce |  | 2 - Test | Unit Test 001 | M3 Items to Salesforce products | In Progress |  | B | Torbjörn Sundbrandt
Salesforce |  | 2 - Test | Unit Test 001 | M3 Pricing to Salesforce | In Progress |  | B | Torbjörn Sundbrandt
SPS Commerce - EDI |  | 0 - Doc | 1 - ANA-050 | ANA-050 - EDI 810 - Reviewed and approved | Complete | 2024-08-16 | I | Cheska Acance
SPS Commerce - EDI |  | 0 - Doc | 1 - ANA-050 | ANA-050 - EDI 850 - Reviewed and approved | Complete | 2024-07-16 | I | Cheska Acance
SPS Commerce - EDI |  | 0 - Doc | 1 - ANA-050 | ANA-050 - EDI 855 - Reviewed and approved | Complete | 2024-08-20 | I | Cheska Acance
SPS Commerce - EDI |  | 0 - Doc | 1 - ANA-050 | ANA-050 - EDI 856 - Reviewed and approved | Complete | 2024-09-06 | B | Melissa Byron
SPS Commerce - EDI |  | 0 - Doc | 1 - ANA-050 | ANA-050 - EDI 830-862 - Reviewed and approved | Complete | 2024-09-06 | B | Melissa Byron
SPS Commerce - EDI | * | 0 - Doc | 2 - TAR-040 | TAR-040 Reviewed and approved | In Progress | 2024-10-11 | I | Cheska Acance | *Sep-20 - Verify Owner
SPS Commerce - EDI |  | 0 - Doc | 3 - TEST-070 | Unit Test Plan | Not Started
SPS Commerce - EDI |  | 1 - Dev | Dev | To SPS Commerce project plan | In Progress |  |  | Courtney Pribyl, Cheska | https://spscommerce.sharepoint.com/sites/EnterpriseImplementationProjectManagement/Courtney%20Pribyl/Associated%20Spring%20Raymond%20Scope%20%26%20Timeline.xlsx?e=4%3atA8y89&web=1&at=9___.YXAzOmJnaW5jOmE6bzo2NjMxMWFkNjA0OTZjYmQ2N2VhOTBjMzJmNjMwZDIxOTo2OjRkMjU6NGFlODQ3NjU5ZjMzOWJiYzg4OGQ2MzJkZGQ3ODA3MmM5NjgyM2I3MTUwM2QwYjBiNTBiYTJjZjA5YTUzYjkyNDpoOlQ6Tg
SPS Commerce - EDI |  | 1 - Dev | Dev | Missing documents focus | In Progress |  |  | Jeff Finch, Rich Ostry, Melissa
SPS Commerce - EDI |  | 2 - Test | UAT | UAT Phase 1 Ready: PACCAR, Granger, Caterpillar, PNC | Late | 2024-11-04 | B | Keith Sims
SPS Commerce - EDI |  | 2 - Test | UAT | UAT Phase 2 Ready: All EDI | Late | 2025-01-06 | B | Keith Sims
SPS Commerce - EDI |  | 2 - Test | Unit Test 001 | To SPS Commerce project plan | In Progress
UPS |  | 0 - Doc | 0 - ANA-050 | ANA-050 - Ready for Review | Complete | 2024-06-14 | I
UPS |  | 0 - Doc | 1 - ANA-050 | ANA-050 - Reviewed and approved | Complete | 2024-06-14 | B | Jack Adoline
UPS |  | 0 - Doc | 2 - TAR-040 | TAR-040 Reviewed and approved | Complete | 2024-09-06 | I | Martin Bautista
UPS |  | 0 - Doc | 3 - TEST-070 | Unit Test Plan | Not Started |  | B | <Shipping / Warehouse>
UPS |  | 0 - Doc | 4 - DOC COMPLETE |  | In Progress
UPS |  | 1 - Dev | Dev | Develop address pull query from data lake | In Progress | 2024-09-20 | B | Dean Amo
UPS | * | 1 - Dev | Dev | Configure address pull from M3 | In Progress | 2024-09-27 | B | Dean Amo | Awaiting network connectivity - CHG
UPS | * | 1 - Dev | Dev | Configure XML output and drop off location | Not Started | 2024-10-04 | B | Dean Amo
UPS |  | 2 - Test | UAT | UAT Ready | On Track - Issue | 2024-10-21 | B | Dean Amo
UPS |  | 2 - Test | Unit Test 001 | Extract XML from shipment of order | Not Started | 2024-10-11 | B | Jeff Finch
UPS |  | 2 - Test | Unit Test 001 | Load XML into M3 and verify information on order | Not Started | 2024-10-11 | I | Daniel
CenPOS |  | 2 - Test | Unit Test 002 | View transactions on CenPOS portal [Needed?] | Not Started |  | B | Kim Diorio
PNC Bank (AR) |  | 2 - Test | UAT | UAT Ready | On Track - Issue | 2024-11-04 | B | Dean Amo

## Barnes UAT Pivot
Phase | 2 - Test
Row Labels | Category | Task | Status | Due Date | Dev Owner | Next Action Due
Bank of America (AP) | UAT | UAT Ready | On Track | 2024-10-18 | Dean Amo | 10/2 - Isiah to deliver 4 files on: ACH header/detail, check header/detail
CenPOS | UAT | Ready for testing | Complete | 2024-06-01 | Daniel Lindblad
Cforia | UAT | UAT Ready | Late | 2024-11-04 | Dean Amo | 10/9 - ANA-050. 10/25 - Kevin - Balance extracts to M3 Open A/R
Concur - Invoice | UAT | UAT Ready | Late | 2024-11-01 | Dean Amo | 9/27 - Dean/Kim/Jesse - Ticket open with Concur, waiting for resource to be assigned. Data not loading under policy.
Concur - Travel & Expense | UAT | UAT Ready | Late | 2024-10-25 | Dean Amo | 9/27 - ANA to be reviewed 9/30 - that could get us back on track. Need to understand schedule.
FedEx | UAT | UAT Ready | On Track - Issue | 2024-10-21 | Dean Amo | 9/27 - FedEx not filling. A. Need production review, B. Call FedEx Support, C. Try another machine.
Optimizely - Current State | UAT | UAT Ready | On Track | 2024-10-07 | Dean Amo
Optimizely - Order Auto. | UAT | UAT Ready | On Track | 2024-10-28 | Dean Amo
PNC Bank (AR) | UAT | UAT Ready | On Track - Issue | 2024-11-04 | Dean Amo | Need matcher file - higher priorty than ANA
Salesforce | UAT | UAT Ready | Complete | 2024-09-09 | Daniel Lindblad
SPS Commerce - EDI | UAT | UAT Phase 1 Ready: PACCAR, Granger, Caterpillar, PNC | Late | 2024-11-04 | Keith Sims | 9/27 - Keith Assessing
|  | UAT Phase 2 Ready: All EDI | Late | 2025-01-06 | Keith Sims | 9/27 - Keith Assessing
UPS | UAT | UAT Ready | On Track - Issue | 2024-10-21 | Dean Amo | 9/27 - Not clear how scanning works
Finance
Sales/Customer Service
Shipping/Warehouse

## Barnes Doc Pivot
Phase | 0 - Doc
Row Labels | Task | Status | Due Date | Owner
Bank of America (AP)
0 - ANA-050 | ANA-050 - Ready for Review | Complete | 2024-08-30 | Carlo Alcazar
1 - ANA-050 | ANA-050 - Signoff | Complete | 2024-09-06 | Kim Diorio
2 - TAR-040 | TAR-040 - Ready for Review | Complete | 2024-09-13 | Isaiah Tolentino
3 - TEST-070 | Unit Test Plan | Not Started | 2024-10-18 | Kim Diorio
CenPOS
0 - ANA-050 | ANA-050 - Ready for Review | Not Required | (blank) | (blank)
1 - ANA-050 | ANA-050 - Signoff | Not Required | (blank) | (blank)
2 - TAR-040 | TAR-040 Reviewed and approved | Not Required | (blank) | (blank)
3 - TEST-070 | Unit Test Plan - CenPOS - contact Hubert for M3 functional questions | Overdue | 2024-09-13 | Amy Burgard
Cforia
0 - ANA-050 | ANA-050 - Ready for Review | Overdue | 2024-09-13 | Dennis Garrero, Rachelle
1 - ANA-050 | ANA-050 - Sign off | Await Dependancy | 2024-10-04 | Kim Diorio / Kevin Alexander
2 - TAR-040 | TAR-040 Reviewed and approved | Await Dependancy | 2024-10-04 | Carlo Alcazar
3 - TEST-070 | Unit Test Plan | Not Started | 2024-10-25 | Dean / Kim
Concur - Invoice
0 - ANA-050 | ANA-050 - Payments to M3 - Ready for Review | Overdue | 2024-09-20 | Dennis Garrero
1 - ANA-050 | ANA-050 - Reviewed and approved | Await Dependancy | 2024-09-27 | Kim Diorio
2 - TAR-040 | TAR-040 Reviewed and approved | Not Started | (blank) | Martin
3 - TEST-070 | Unit Test Plan | Not Started | (blank) | (blank)
Concur - Travel & Expense
0 - ANA-050 | ANA-050 - Ready for Review | Overdue | 2024-09-30 | Dennis Garrero, Rachelle
1 - ANA-050 | ANA-050 - Reviewed and approved | Await Dependancy | 2024-09-30 | Jesse Keech, Kim Diorio
2 - TAR-040 | Concur TAR-040 | In Progress | 2024-10-11 | Martin Bautista
3 - TEST-070 | Unit Test Plan | Not Started | (blank) | (blank)
FedEx
0 - ANA-050 | ANA-050 - Payments to M3 - Ready for Review | Complete | 2024-06-14 | (blank)
1 - ANA-050 | ANA-050 - Reviewed and approved | Complete | 2024-06-14 | Jack Adoline
2 - TAR-040 | TAR-040 Reviewed and approved | Not Started | 2024-09-06 | Martin Bautista
3 - TEST-070 | Unit Test Plan | Not Started | (blank) | Jeff Finch
Optimizely
0 - ANA-050 | ANA-050 - Ready for Review | Complete | 2024-09-06 | Cheska Acance
1 - ANA-050 | ANA-050 - Reviewed and approved | Complete | 2024-09-20 | Beth Wilkerson
2 - TAR-040 | TAR-040 Reviewed and approved | Not Started | (blank) | Dean Amo | XML delivered 9/23
3 - TEST-070 | Unit Test Plan | Not Started | (blank) | Beth Wilkerson
PNC Bank (AR)
0 - ANA-050 | ANA-050 - Payments to M3 - Ready for Review | In Progress | 2024-09-27 | Dennis Garrero
1 - ANA-050 | ANA-050 - Reviewed and approved | Await Dependancy | 2024-10-04 | Kim Diorio
2 - TAR-040 | TAR-040 Reviewed and approved | In Progress | 2024-10-11 | Martin Bautista
3 - TEST-070 | Unit Test Plan | Not Started | (blank) | (blank)
Salesforce
0 - ANA-050 | ANA-050 - Ready for Review | Complete | 2024-09-06 | Martin Bautista
1 - ANA-050 | ANA-050 - Reviewed and approved | Complete | (blank) | Torbjörn Sundbrandt
2 - TAR-040 | TAR-040 Reviewed and approved | Complete | (blank) | Martin Bautista
3 - TEST-070 | Unit Test Plan | In Progress | 2024-09-27 | Torbjörn Sundbrandt
SPS Commerce - EDI
1 - ANA-050 | ANA-050 - EDI 810 - Reviewed and approved | Complete | 2024-08-16 | Cheska Acance
| ANA-050 - EDI 830-862 - Reviewed and approved | Complete | 2024-09-06 | Melissa Byron
| ANA-050 - EDI 850 - Reviewed and approved | Complete | 2024-07-16 | Cheska Acance
| ANA-050 - EDI 855 - Reviewed and approved | Complete | 2024-08-20 | Cheska Acance
| ANA-050 - EDI 856 - Reviewed and approved | Complete | 2024-09-06 | Melissa Byron
2 - TAR-040 | TAR-040 Reviewed and approved | In Progress | 2024-10-11 | Cheska Acance
3 - TEST-070 | Unit Test Plan | Not Started | (blank) | (blank)
UPS
0 - ANA-050 | ANA-050 - Ready for Review | Complete | 2024-06-14 | (blank)
1 - ANA-050 | ANA-050 - Reviewed and approved | Complete | 2024-06-14 | Jack Adoline
2 - TAR-040 | TAR-040 Reviewed and approved | Complete | 2024-09-06 | Martin Bautista
3 - TEST-070 | Unit Test Plan | Not Started | (blank) | <Shipping / Warehouse>
Grand Total

## Barnes Dev Pivot
Phase | 1 - Dev
Row Labels | Task | Status | Due Date | Priority | Owner
Bank of America (AP)
Dev | Detail file for ACH | Complete | 2024-09-27 | * | Isaiah Tolentino
| Detail file for checks | Complete | 2024-09-27 | * | Isaiah Tolentino
| Header file for ACH | Complete | 2024-09-27 | * | Isaiah Tolentino
| Header file for checks | Complete | (blank) | (blank) | Isaiah Tolentino
| SSIS: Transfer files to Industrial JBA box for transmission (weekly) | Await files | 2024-10-11 | * | Kevin Alexander
CenPOS
Dev | Change service account from @infor.com to @asraymond.com | In Progress | 2024-09-27 | Low | Dean Amo
| Review test portal login | Complete | 2024-09-27 | Low | Dean Amo
| Update M3 CenPOS connector configuration after account change | Not Started | (blank) | Low | Hubert Santos
Cforia
Dev | Build ARCASH.TXT exoport | In Progress | 2024-10-25 | (blank) | Kevin Alexander
| Build ARCUST.TXT exoport | In Progress | 2024-10-25 | (blank) | Kevin Alexander
| Build AREXTI.TXT exoport | In Progress | 2024-10-25 | (blank) | Kevin Alexander
| Build ARMAST.TXT exoport | In Progress | 2024-10-25 | (blank) | Kevin Alexander
| Build ARTRAN.TXT exoport | In Progress | 2024-10-25 | (blank) | Kevin Alexander
| Modify DW Job, BGIDW_M3_ASR to include AR files | In Progress | 2024-10-18 | * | Kevin Alexander
| Contact Cdoria - ensure test environment is ready | (blank)
Dev - Enahnce | Invoice PDF to archive folder | Not Started | (blank) | (blank) | Karin Fransson
Concur - Invoice
Dev | Inbound - Matched Payments to XML BOD drop off | Complete | 2024-07-11 | (blank) | Kevin Alexander
| OUT: Produce PO Header, Lines, Receipts, Vendor files | Complete | 2024-07-11 | (blank) | Kevin Alexander
| OUT: Ensure files ingest into Concur | In Progress | 2024-09-27 | * | Dean Amo
DEV COMPLETE | (blank) | Complete | 2024-08-22 | (blank) | (blank)
Concur - Travel & Expense
Dev | Import flat file into M3 | Not Started | (blank) | (blank) | Kevin Alexander
Rachelle
FedEx
Dev | Configure address pull from M3 | In Progress | 2024-09-27 | * | Dean Amo
| Develop address pull query from data lake | In Progress | 2024-09-20 | (blank) | Dean Amo
| Configure XML output and drop off location | In Progress | 2024-10-04 | * | Dean Amo
Optimizely
Dev | OUT: Add price list extract to BGIDW_M3_ASR_Daily.dtsx | Complete | 2024-08-30 | (blank) | Dean Amo
| OUT: Add inventory extract with gas charge logic | Complete | 2024-09-27 | * | Dean Amo
| OUT: Produce files from M3 company 910 and load to test | In Progress | 2024-10-04 | * | Dean Amo, Jane Woytach
| IN: CenPOS integration - schedule CONSID meeting | Overdue | 2024-09-06 | * | Dean Amo, Beth Wilkerson
| IN: CONSID - Update sales order file | In Progress | 2024-10-18 | (blank) | (blank)
| IN: Convert CSV to XML BOD | Not Started | 2024-10-18 | (blank) | (blank)
| IN: Verify ingestion of sales order BOD | Not Started | 2024-10-25 | (blank) | (blank)
| Contingency - May need to work with CONSID on data load | In Progress | 2024-10-04 | (blank) | Dean Amo
PNC Bank (AR)
Dev | Bank test environment | In Progress | (blank) | (blank) | (blank)
| EDI 820/823 - To SPS Commerce Project Plan | In Progress | (blank) | (blank) | (blank)
| Matcher file to CSV | Not Started | 2024-10-11 | ! | Dennis Garrero
Salesforce
Dev | Configure M3 to Salesforce connector | Complete | (blank) | (blank) | Martin Bautista
| Verify any open items agains ANA/TAR | Not Started | 2024-09-04 | (blank) | Dean, Torborjn, Martin
SPS Commerce - EDI
Dev | Missing documents focus | In Progress | (blank) | (blank) | Jeff Finch, Rich Ostry, Melissa
| To SPS Commerce project plan | In Progress | (blank) | (blank) | Courtney Pribyl, Cheska
UPS
Dev | Configure address pull from M3 | In Progress | 2024-09-27 | * | Dean Amo
| Develop address pull query from data lake | In Progress | 2024-09-20 | (blank) | Dean Amo
| Configure XML output and drop off location | Not Started | 2024-10-04 | * | Dean Amo
(blank)
Dev | Transmit to Cforia | Not Started | 2024-11-01 | (blank) | Kevin Alexander
Grand Total

## Pivot (hidden)
Row Labels
Development
SPS Commerce EDI
EDI Invoice
EDI Sales Order Ack
Not Started
Cforia
Customer Master
Customer Order
Customer Payments & Credits
Invoice Copies IDM (PDF)
Invoice Payment History
Optimizely
Customer and Addresses
Items
Std Price, Cust price, Disc
Stock
Tax exemption
Out of Scope
Salesforce
Customer
ShipToPartyMaster / Addresses
SPS Commerce EDI
Application Advice EDI 824
Pending Approval
BoA Shared Service (AP)
Check Run Details
Check Run Header
Pre Development
(SPS) PNC Bank (AR)
PNC Lockbox EDI 823 checks
PNC Lockbox EDI820 flat file ACH ad wires
Concur
Goods Receipts
PO Header
PO Lines
T&E expense posting
Vendor Infor
Fedex
FedEx Shipping information
FedEx Tracking Number Update
Optimizely
Order (email)
PNC Bank (AR) (SPS)
PNC Matcher file
SPS Commerce EDI
EDI Shipment 856
EDI Shipment Schedule EDI 862
Planning Schedule EDI 830
UPS
UPS Shipping Information
UPS Tracking Number Update
Testing
CenPos
Payment Authorization
Payment Capture
Concur
SupplierInvoice
Salesforce
Item
Item Pricing
SPS Commerce EDI
EDI Sales Order 850
(blank)
SPS Commerce EDI
DSV
(blank)
(blank)
Grand Total

## Current Week
Priority | *
Owner/Interface | Task | Due Date | Status | Note
Amy Burgard
CenPOS | Unit Test Plan - CenPOS - contact Hubert for M3 functional questions | 2024-09-13 | Overdue | *Meeting scheduled Thur 9/26
Carlo Alcazar
Cforia | TAR-040 Reviewed and approved | 2024-10-04 | Await Dependancy | Awaiting ANA-050
Cheska Acance
Optimizely | ANA-050 - Ready for Review | 2024-09-06 | Complete | (blank)
SPS Commerce - EDI | TAR-040 Reviewed and approved | 2024-10-11 | In Progress | *Sep-20 - Verify Owner
Dean Amo
Concur - Invoice | OUT: Ensure files ingest into Concur | 2024-09-27 | In Progress | Sep-20 - Last import successful, turning on feed Monday (Sep-23) evening run
FedEx | Configure address pull from M3 | 2024-09-27 | In Progress | (blank)
| Configure XML output and drop off location | 2024-10-04 | In Progress | (blank)
| Need sample shipments file XML from FedEx production | 2024-09-27 | Complete | (blank)
Optimizely | OUT: Add inventory extract with gas charge logic | 2024-09-27 | Complete | (blank)
UPS | Configure address pull from M3 | 2024-09-27 | In Progress | Awaiting network connectivity - CHG
| Configure XML output and drop off location | 2024-10-04 | Not Started | (blank)
Dean Amo, Beth Wilkerson
Optimizely | IN: CenPOS integration - schedule CONSID meeting | 2024-09-06 | Overdue | 9/20 - Discussing requirements
Dean Amo, Jane Woytach
Optimizely | OUT: Produce files from M3 company 910 and load to test | 2024-10-04 | In Progress | (blank)
Dennis Garrero
Concur - Invoice | ANA-050 - Payments to M3 - Ready for Review | 2024-09-20 | Overdue | 2024-09-24
PNC Bank (AR) | ANA-050 - Payments to M3 - Ready for Review | 2024-09-27 | In Progress | (blank)
Isaiah Tolentino
Bank of America (AP) | Detail file for ACH | 2024-09-27 | Complete | 10/2 Wed - Martin on 9/30 9a call
| Detail file for checks | 2024-09-27 | Complete | 10/2 Wed - Martin on 9/30 9a call
| Header file for ACH | 2024-09-27 | Complete | 10/2 Wed - Martin on 9/30 9a call
Kevin Alexander
Bank of America (AP) | SSIS: Transfer files to Industrial JBA box for transmission (weekly) | 2024-10-11 | Await files | (blank)
Cforia | Modify DW Job, BGIDW_M3_ASR to include AR files | 2024-10-18 | In Progress | (blank)
Kim Diorio
Bank of America (AP) | ANA-050 - Signoff | 2024-09-06 | Complete | Agreed approved in Meeting 9/23/2024
Concur - Invoice | ANA-050 - Reviewed and approved | 2024-09-27 | Await Dependancy | (blank)
PNC Bank (AR) | ANA-050 - Reviewed and approved | 2024-10-04 | Await Dependancy | (blank)
Kim Diorio / Kevin Alexander
Cforia | ANA-050 - Sign off | 2024-10-04 | Await Dependancy | (blank)
Martin Bautista
Concur - Travel & Expense | Concur TAR-040 | 2024-10-11 | In Progress | (blank)
Torbjörn Sundbrandt
Salesforce | Unit Test Plan | 2024-09-27 | In Progress | (blank)
Beth Wilkerson
Optimizely | ANA-050 - Reviewed and approved | 2024-09-20 | Complete | Approved 9/23/2024 via email
Jesse Keech, Kim Diorio
Concur - Travel & Expense | ANA-050 - Reviewed and approved | 2024-09-30 | Await Dependancy | Review @9a
Dennis Garrero, Rachelle
Cforia | ANA-050 - Ready for Review | 2024-09-13 | Overdue | 9/30/2024 - New Due Date
Concur - Travel & Expense | ANA-050 - Ready for Review | 2024-09-30 | Overdue | (blank)
Rachelle
Concur - Travel & Expense | GLS 840 - Can we use existing format or do we need new? | 2024-09-30 | Not Started | (blank)
Grand Total

## Drop Down (hidden)
Status |  | Status |  | Sub Category | Days | Days to complete Integration | Deploy
New Interface | Completed | Not Started |  | N-New Interface | 10 | 60 | TST
Not Started | NA | Out of Scope |  | Not Started | 10 | 60 | TRN
Out of Scope | Not Started | Pre Development |  | Out of Scope | 10 | 60 | PRD
Pre Development | Pending Approval |  | Solution Unknown | Solution Unknown | 10 | 60
Development | Pending Confirmation |  | Research | Research | 10 | 35
Testing | WIP |  | Speccing (ANA-050) | Speccing (ANA-050) | 5 | 30
Infor Standard Integration (OOB) |  |  | Tech Spec (TAR-040) | Tech Spec (TAR-040) | 5 | 25
Integration Approved for Deployment |  | Development |  | Development | 10 | 15
|  | Testing |  | Development Testing | 3 | 12
|  |  | Development Testing | Functional Testing | 5 | 7
|  |  | Functional Testing | Business Testing | 5 | 2
|  |  | Business Testing | Break/Fix/Retest | 2 | 0
|  | Integration Approved for Deployment |  | Approved/Complete | 0 | 0
New Interface
Infor Standard Integration (OOB)