## Sheet1
Start Time of Test |  | 11:59 | Date of Test | 2024-12-20 | End Time of Test | 11:59 |  | DATA TO USE for this Script Test
Barnes M3 - Test Script and Scenario
Scenario and Story Lines as a Script for Testing
Version: 1.1
Infor M3 - Script Testing |  | M3 / SalesForce | Script Story Line
Test Company: Barnes |  | Barnes - 810 | Test the Price & ATP call from SalesForce and validate functionality and data accuracy. SalesForce Partcopy (UAT) Environment: https://bginc--partcopy.sandbox.my.salesforce.com
Test Environment Name: |  | CRP1 810/AAA
SCRIPT ID: |  | SCRIPT SFU02
WORK STREAM: |  | SalesForce Integration
Below is a short description of how this testing method will take place at Barnes
The Test Script will be done during normal working hours, we want to make it as reaslistic as possible. Step 1 is the beginning. It has an assigned department. This Script will be sent to that department, and the test begins. That department goes into M3 and completes the assigned task. Documenting the outcome on that line. Enter any Needed Doc#, CO#, PO#, etc. When the department has completed the line assigned, they email this test script to the next department tester on this script. This process continues on until you reach the last step. This is a quick test at each stop of the Script. The Last person on this test script once their task is complete..will email the script document to Sonja Scheuer for evaulation.
*** |  | DOCUMENTATION OF TESTING
Activity | Steps | Expected Outcome | Department | Actual Outcome & DOC#'s | Tester Name | Comments | Pass/ Fail
1 | SF ¦ Follow SFU01 to create a Maumee M3 related Opportunity, Quote and add Quote Line Items to it. | Test data created in SalesForce | Sales
2 | SF ¦ Navigate to the Quote you have created and click the 'Price & ATP Call' | Screen Flow user interface for integration started | Sales
3 | SF ¦ The screen flow presents 3 options on how to target an account. If there is an ERP reference related to the account that can be chosen as a first option trying to use the account number from that reference record. Second option is to pick a 'Price List' as the target. The system will target a dummy account in the ERP tied to this price list. This is useful when quoting a new customer not yet in ERP. Third option is to enter the account number or sequence manually. | Screen Flow layout evaluated | Sales
4 | SF ¦ Pick an option to test and add numbers if needed, related to what test accounts were chosen in step 1. Check the boxes if you are to test a 'Price Call' or 'Stock Call (ATP)', or both. | Test case defined in Screen Flow | Sales
5 | SF ¦ When you click to 'Proceed' a second screen will pop up showing the ERP (Pricebook) you are targeting and the account reference. If it doesn't show up correct this might have to be addressed with the CRM developer to adjust. | Second Screen layout evaluated | Sales
6 | SF ¦ The actual API calls are designed to do maximum 30 items at a time and to trigger the 'Price call' and the 'Stock call' separately. This is to prevent the API to time out or cause other issues with larger batches of items. For each API batch call completed a screen is presented with a status of how many succcessful and failed calls was done. Proceed with the API calls and evaluate any progress screens popping up during the calls. | Progress Screens Evaluated | Sales
7 | SF ¦ When all API calls are done you will get to the final results screen. It can look a little bit as what you see to your right. Remember that 'Lead time' is part of the 'Stock Level Call'. Lead Time is calculated by subtracting today's Date from 'Planning Date' in M3 and converting that into weeks. ATP value is put to 'Stock Level' field as well and 'Stock Level Info' field will show 'In Stock' if quantity is available, otherwise show Lead Time. | Final Results Screen Evaluated | Sales
8 | SF + M3 ¦ Go to the list of Quote Line Items and make sure all values are updated and validate the results with M3 data (if you have access, or can ask someone from the team to support). | Data validated between CRM and M3 | Sales
9 | SF ¦ Make sure to do multiple tests, starting from the beginning of this document to test with different accounts, different items and quantities. Test with bigger batches of items as well as with smaller ones and document the results. | Test finalized | Sales
10
11
12
13
14
15
16