## MNS110
Function | Grp | Description | Workstream (multiple section option) | In scope | Related to | Data Type | M3 Funcational member | HJ Business member | SPRINT | TST<100> GOLD | TST <200> (Config & UT) | TST <300> (Data load test) | Add | Add | Remarks
AAS900 | FAA | Settings - Online Invoicing | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
AAS911 | FAA | Settings - Electronic Bank Reporting | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
ABS010 | ABS | Transaction Type. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ABS020 | ABS | Business Transaction Code. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ABS900 | ABS | Bank Account Identifier. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ABS910 | ABS | Scenario Number. Prioritize | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ABS911 | ABS | Scenario Number. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ABS920 | ABS | Payment Variance Limit. Define | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ABS930 | ABS | Additional Information. Structure | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ABS940 | ABS | Text Identifier. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ABS960 | ABS | Reconciliation Type. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ABS965 | ABS | Reconciliation Search Sequence. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
AHS010 | AHR | Ad Hoc Report Location. Open | Security & Admin | Yes
AHS020 | AHR | Ad Hoc Document Location. Open | Security & Admin | Yes
AMS010 | TAM | Archiving Library. Open
APS005 | APL | AP Statement of Account. Enter Text | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
APS010 | APL | Trade Code. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
APS015 | APL | Suppl Payment. Specify Bank Fee Type | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
APS020 | APL | AP Accounting Option. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
APS025 | APL | Supplier Activity Code. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
APS026 | APL | Offical Service Code. Open | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
APS030 | APL | Bank Quota. Open | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
APS035 | TAX | Settings - Supplier Tax | Finance | Yes |  |  |  |  | Sprint 5 |  | Planned
APS037 | APL | Supplier Tax. Open Exemption Letter | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
APS060 | APL | AP Standard Document. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
APS062 | APL | AP Standard Document Text. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
APS064 | APL | AP Debit Note Reason. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
APS065 | APL | AP Inquiry Column Template. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
APS070 | APL | AP Report Column Template. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
APS080 | APL | Suppl Payment Stop. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
APS085 | APL | Check. Open Void Code | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
APS090 | APL | Bank Account Connection. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
APS098 | APL | Payment Tolerance. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
APS900 | APL | Settings - Supplier Invoice Matching | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
APS905 | APL | Settings - Accounts Payable | Finance | Yes |  | Configuration | Athar |  | Sprint 1 |  | Completed
APS950 | APL | AP Additional Info. Update | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
ARS005 | ARL | AR Statement of Account. Enter Text | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
ARS007 | ARL | Interest ID. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
ARS008 | ARL | Interest Rate per Date. Open | Finance | No |  | Configuration | Athar | Angie Helton | NA | NA | NA | NA
ARS010 | ARL | Payment Reminder Rule. Enter Text | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
ARS015 | ARL | Payment Received. Specify Bank Fee Type | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
ARS016 | ARL | Debit Reason. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
ARS020 | ARL | AR Accounting Option. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ARS025 | ARL | Credit Department Reference. Open | Finance | Yes | CRS610 (If applicable) | Configuration | Athar | Angie Helton | Sprint 2 |  | Planned
ARS030 | ARL | Payment Advice Rule. Open | Finance | Yes | CRS610 (If applicable) | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
ARS035 | ARL | Payment Advice Rule. Enter Text | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
ARS050 | ARL | Payment Received. Open Standard Letter | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
ARS052 | ARL | Bill Back Type. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ARS055 | ARL | Payment Reminder Stop. Open | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
ARS060 | ARL | Doubtful Account. Define Age Range | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
ARS065 | ARL | Doubtful Account. Define Depreciat Pct | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
ARS066 | ARL | AR Inquiry Column Template. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
ARS070 | ARL | AR Report Column Template. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
ARS075 | ARL | Batch Payment Type. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
ARS080 | ARL | Interest Invoicing Rule. Enter Text | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
ARS085 | ARL | Collection. Enter Text | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ARS090 | ARL | Payment Pattern. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
ARS098 | ARL | Payment Tolerance. Open | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
ARS905 | ARL | Settings - Accounts Receivable | Finance | Yes |  | Configuration | Athar |  | Sprint 1 |  | Completed
CRS787 | ATC | Attribute. Open | Manufacturing | Yes |  | Migrated values | Will Bolin | Derek, Jennifer | Sprint 1 |  | Completed
ATS011 | ATC | Attribute. Enter Names/Language
ATS012 | ATC | Attribute Group. Open
ATS014 | ATC | Display Group. Open
ATS020 | ATC | Attribute Matrix. Open
ATS030 | ATC | Attribute Matrix. Enter Default Values
ATS035 | ATC | Receiving Attribute Values. Override
ATS040 | ATC | Attribute-Dependent Objects. Open
ATS050 | ATC | Attribute Model. Open | Manufacturing | Yes |  | Migrated values | Will Bolin | Derek, Jennifer | Sprint 1 |  | Completed
ATS051 | ATC | Attribute Model. Connect Attributes
ATS053 | ATC | Attribute Model. Enter Names/Language
ATS060 | ATC | Information Group. Open
ATS061 | ATC | Default Information Group. Open
ATS070 | ATC | Attribute Model Table. Open
ATS071 | ATC | Attribute Model Selection Table. Open
BUS001 | BUD | Budget Calculation Template. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
BUS005 | BUD | Budget Allocation Template. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
BUS010 | BUD | Budget Activity. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
BUS015 | BUD | Budget Resource. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
BUS030 | BUD | Budget Template. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
BUS035 | BUD | Budget Officer. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CAS005 | CAC | Resource Driver Rate Type. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CAS006 | CAC | Resource Driver Unit Version. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CAS007 | CAC | Resource Driver Rate Version. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CAS010 | CAC | Cost of Capital Calculation Rule. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CAS020 | CUR | Settings - Inventory Value Variances | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CAS025 | CUR | Settings - Inventory Valuation | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CAS030 | CUR | Settings - WIP Valuation | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
CAS035 | CAC | Settings - Rules for Warranty Fund | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
CAS040 | CAC | Resource Driver. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CAS041 | CAC | Resource Driver. Enter Connection | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CAS050 | CAC | Cost Center Model. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CAS060 | CAC | Order Costing Balance File Key. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CAS065 | CAC | Column Template - Order Costing. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CAS080 | CAC | Analytical Acc Aggr Bal File Key. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CAS085 | CAC | Column Template - Analytical Acc. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CAS390 | CAC | Accounting Model. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CAS900 | CAC | Settings - Cost Accounting | Finance | Yes |  | Configuration | Athar |  | Sprint 1 |  | Completed
CBS001 | CAM | Resources. Open
CBS002 | CAM | Capability per Resource. Open
CBS004 | CAM | Capability. Open
CBS005 | CAM | Capability Type. Open
CBS006 | CAM | Capability Level. Open
CBS010 | CAM | Role Definition. Open
CBS011 | CAM | Employee Role. Open
CBS020 | CAM | Settings - Employee Allocation
CBS700 | CAM | Resource Type. Open
CFS010 | CFM | Conversion Table. Open | Finance | Yes |  |  |  |  | Sprint 5 |  | Planned
CFS015 | CFM | Allocation Table. Open | Finance | Yes |  |  |  |  | Sprint 5 |  | Planned
CFS020 | CFM | Cash Flow Model. Open | Finance | Yes |  |  |  |  | Sprint 5 |  | Planned
CMS003 | CRS | Company Type. Open
CMS004 | OUT | Printer Files XML Variants. Open
CMS005 | CRS | List and Printer programs. Configure
CMS006 | OUT | XML Structure. Open
CMS010 | GBD | Information Browser Category. Open
CMS015 | CRS | Custom List MI. Open
CMS016 | GBD | Available Object Ctrl Parameters. Open
CMS017 | GBD | Generic Object Control Table. Open
CMS018 | OUT | XML Custom Subtotal Fields. Connect
CMS021 | IES | Standard Search. Open
CMS022 | IES | Related Search. Open
CMS025 | OUT | Report Layout. Open
CMS030 | IES | Key Search. Open
CMS031 | IES | Field Alias. Open
CMS033 | OUT | XML Custom Text Section Control. Open
CMS041 | ENV | Event Based API Calls. Open
CMS042 | ENV | Composite Events. Open
CMS045 | ENV | Event Subscription. Open
CMS055 | GBD | Customer. Connect Contact
CMS071 | CRS | Start Day Interval. Open
CMS075 | SEC | Data Subject. Connect Search Field
CMS076 | SEC | Data Subject. Set Action
CMS077 | SEC | Data Subject. Connect Retention Policy
CMS080 | ENV | Customer-Defined Fields. Open
CMS082 | CRS | User-Defined Fields. Open | Customer Order | [5 empty] | Sprint 3 |  | Completed
CMS085 | ENV | Formatting Rules. Define
CMS090 | ARL | Additional Payment Reference. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CMS095 | ENV | NLP Translation. Open
CMS103 | CRS | Finance Reason Code. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CMS200 | COP | Customer Channel. Open
CMS202 | COP | Customer Channel Search Options. Open
CMS205 | COP | Customer Channel ID. Open
CMS206 | COP | Customer Channel Activity. Open
CMS250 | CRS | User Location. Open
CMS325 | ENV | API Calls Log. Open
CMS432 | SEC | Reason Codes. Open
CMS460 | CRS | Interest Rate ID. Open
CMS470 | CRS | Custom Field. Open
CMS471 | CRS | Custom Field Group. Open
CMS472 | CRS | Custom Field Grp. Connect Field
CMS520 | CRS | Settings - E-invoice
CMS530 | CRS | Data Field Name. Open
CMS535 | CRS | SchemeID. Open
CMS540 | CRS | E-invoice format. Open
CMS615 | GBD | Supplier Customer Reference. Open
CMS616 | GBD | Supplier Customer Reference Type. Open
CMS700 | OUT | Settings - Output Management
CMS702 | CRS | Settings - Customer Local Exceptions
CMS730 | CRS | Profile. Open
CMS950 | AUX | Db Update Manager
COS010 | MCO | Maint CO Type. Open
COS430 | MCO | Settings - User-def Maint Agrmt Fields
COS440 | MCO | Settings - User-def MCO Fields
COS822 | MCO | Settings - Maintenance CO Invoicing
COS895 | MCO | Settings - Maintenance Customer Orders
CRS002 | GBD | User-defined Constant. Open
CRS003 | COS | Sales Campaign. Open
CRS004 | GBD | User Group. Open
CRS005 | WHM | Picking Skill. Open
CRS006 | GBD | Object Access Group. Open | Customer Exp | Yes | CRS610 | Configuration | Akhil (Thomas as needed) |  | Sprint 3 |  | Planned
CRS008 | GBD | Facility. Open | Finance | Yes | CRS610 (Default Facility) | Configuration | Athar | Angie Helton | Sprint 1 |  | Completed
CRS011 | MAP | Supplier ABC Code. Open
CRS014 | GBD | Program Start Values. Open
CRS015 | WHM | ABC Class. Open
CRS016 | GBD | View. Select Columns
CRS018 | WHM | Picking Activity. Open
CRS019 | GBD | Event. Open
CRS020 | GBD | View. Open
CRS021 | GBD | M3 File. Create Sorting Options
CRS022 | GBD | Sorting Order. Open
CRS025 | WHM | Item Group. Open
CRS027 | OUT | Standard Document. Open
CRS029 | OUT | Output Control Selection Table. Open
CRS030 | GBD | VAT Code. Open | Finance | No |  |  |  |  | NA |  | NA
CRS033 | OUT | Media Profile. Open
CRS034 | CDS | Packing Instruction. Open per Language
CRS035 | WHM | Product Group. Open
CRS036 | GBD | Business Area. Open
CRS037 | WHM | Procurement Group. Open
CRS038 | WHM | Environment Group. Open
CRS040 | WHM | Item Type. Open
CRS047 | TST | TST Country Code. Open
CRS048 | TST | Customs Procedure. Open for Export
CRS049 | TST | Customs Procedure. Open for Import
CRS050 | WHM | Unit of Measure. Open
CRS051 | WHM | Unit of Measure. Open Conversion Table
CRS053 | GBD | Currency. Connect Rounding-off Rules | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS055 | GBD | Currency. Open | Finance | Yes | CRS610 | Configuration | Athar | Angie Helton | Sprint 1 |  | Completed
CRS056 | GBD | Exchange Rate Type. Open | Finance | Yes | CRS610 | Configuration | Athar | Angie Helton | Sprint 1 |  | Completed
CRS059 | GBD | Exchange Rate Type. Open per Currency | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS060 | GBD | Purchase Price. Enter Text
CRS061 | GBD | Rail station. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
CRS063 | APL | Supplier Service Code. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CRS064 | ARL | Customer Service Code. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CRS065 | GBD | Delivery Term. Open | Customer Exp | Yes | CRS610, OIS002 | Configuration | Akhil |  | Sprint 2 |  | Completed |  |  |  | Akhil to share list with Cassie. We propose to use incoterms
CRS066 | SEP | Meter Entry Source. Open
CRS067 | TST | Extrastat Delivery Term. Open
CRS068 | TST | Sender Location. Open
CRS069 | TST | Receiver Location. Open
CRS070 | GBD | Delivery Method. Open | Customer Exp | Yes | CRS610, OIS002 | Configuration | Akhil + Olivier |  | Sprint 2 |  | Completed |  |  |  | Assign to Olivier
CRS071 | APL | AP Payment Method. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS072 | GLR | Bank Account Indicator. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS073 | TST | Harbor/Airport. Open
CRS075 | GBD | Payment Term. Open | Finance | Yes | CRS610 | Configuration | Athar | Angie Helton | Sprint 1 |  | Completed
CRS076 | ARL | AR Payment Method. Open | Finance | Yes | CRS610 | Configuration | Athar | Angie Helton | Sprint 1 |  | Completed
CRS077 | GBD | Cash Discount Term. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS078 | GLR | Payment Type. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS079 | GLR | Bank Operation. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS081 | TST | Customs Office. Open
CRS082 | GBD | Check Digit Method. Open
CRS083 | GLR | Bank Account Field. Create Additional | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS084 | APL | Image Server ID. Open | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
CRS088 | GBD | Labor Skill. Open
CRS089 | GBD | Inspection Skill. Open
CRS090 | GBD | Rejection Reason. Open
CRS091 | GBD | Milestone Type. Open
CRS092 | GBD | Milestone. Open
CRS093 | GBD | Milestone Template. Open
CRS095 | GBD | Interruption Reason. Open
CRS096 | GBD | Milestone Chain. Open
CRS098 | WHM | Interchangeability. Open
CRS099 | WHM | Product Line. Open
CRS100 | GBD | Salesperson. Open | Customer Exp | Yes | CRS610 - Relates to MNS150 | Migrated values | Akhil + Eric |  | Sprint 2 |  | HJ Task WIP |  |  |  | 8 digit customer #. HJ confirmation awaited
CRS101 | COP | Contact Method. Open | Customer Exp | Yes |  |  |  |  | Sprint 2 |  | Completed |  |  |  | Possible Value: EDI/E-Com/Blank
CRS102 | GBD | Sales Department. Open | Customer Exp | Yes | Relates to CRS100 | Migrated values | Akhil + Eric |  | Sprint 2 |  | HJ Task WIP |  |  |  | Info needed Adam / HJ
CRS103 | GBD | Transaction Reason. Open | Customer Exp | Yes |  |  | In Progress from Sprint 2 |  | Sprint 3 |  | Planned
CRS104 | COP | CO Invoicing Group. Open | Customer Exp | Yes | CRS610 | Configuration | Athar + Akhil |  | Sprint 2 |  | Completed |  |  |  | Assign to Athar. We can probably use Blank for Daily Invoicing, and let say MON for monthly invoiicing.
CRS105 | COP | Assortment. Open
CRS106 | COP | Document Class. Open
CRS107 | WHM | Distribution Group. Open
CRS108 | GBD | Field Group. Open
CRS110 | WHM | Physical Inventory Cycle. Open
CRS111 | GBD | e-mail Address. Open | Customer Exp | Yes |  | Migrated values | Eric + Akhil |  | Sprint 2 |  | HJ Task WIP |  |  |  | Info needed Adam / HJ
CRS113 | COS | Standing CO Group. Open
CRS115 | GBD | Customer Bonus Group. Open | Customer Exp | Yes | CRS610 | Configuration | Assign to Athar |  | Sprint 3 |  | Planned
CRS116 | OUT | Document Media. Open
CRS117 | GBD | Address Formatting Rules. Open | Customer Exp | Yes | Relates ro country CRS045 | Configuration | Akhil. Piyush |  | Sprint 1 |  | Completed
CRS118 | OUT | Email Group. Open
CRS119 | OUT | Email Group. Open Email Address
CRS120 | WHM | Item Bonus Group. Open
CRS121 | MAP | Inventory Segment. Open
CRS122 | TAG | Trade Agreement Class. Open
CRS124 | COP | Packing Instruction. Open
CRS125 | GBD | Packaging Term. Open | Customer Exp | Yes | CRS610 | Migrated values | Olivier + Akhil |  | Sprint 2 |  | Completed
CRS126 | GBD | Freight Term. Open | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS128 | GBD | Customs Statistics Number. Open
CRS130 | GBD | Tax Code. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS132 | GBD | Tax Code. Open Taxable Combinations | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS134 | GBD | Tax Transaction Subtype. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS135 | GBD | Customer Commission Group. Open | Customer Exp | Yes | CRS610 | Configuration | Assign to Athar |  | Sprint 3 |  | Planned
CRS136 | WHM | Item Commission Group. Open
CRS137 | GBD | Geographic Code. Enter Jurisdiction | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS138 | GBD | Geographic Code. Enter Tax Rate | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS139 | GBD | Geographic Code. Enter Exemptions | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS140 | GBD | District. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 4 |  | Planned
CRS143 | COS | Customer Selection Table. Open
CRS145 | GBD | Customer Group. Open | Customer Exp | Yes | CRS610 | Configuration | Athar + Akhil |  | Sprint 2 |  | Completed |  |  |  | Iteration 1 is done. HJ is still deciding the customer groups though
CRS147 | GBD | Customer Document Group. Open | Customer Exp | No | CRS610 |  |  |  | NA | NA | NA | NA |  |  | No need to set up. We will set up blank value in OCUSMA
CRS148 | COS | Item Selection Table. Open
CRS158 | WHM | Physical Inventory Selection Table. Open
CRS160 | GBD | Time Reference. Open
CRS161 | GBD | Core Policy Selection Table. Open
CRS162 | COM | Core Policy. Open
CRS165 | GBD | Number Series. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS166 | WHM | UN Number. Open
CRS167 | CRS | Report Number Series. Open | Finance | Yes |  |  |  |  | Sprint 5 |  | Planned
CRS168 | COM | Core Terms. Open
CRS169 | COM | Acceptance Group. Open
CRS171 | GBD | Salesperson Selection Table. Open
CRS180 | APL | Amount as Text. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
CRS181 | WHM | User-defined Field 1. Open | Procurement | Yes |  | Migrated values | Olivier | Heather King | Sprint 2 |  | Planned
CRS184 | WHM | User-defined Field 4. Open | Procurement | Yes |  | Migrated values | Olivier | Heather King | Sprint 2 |  | Planned
CRS185 | WHM | User-defined Field 5. Open | Procurement | Yes |  | Migrated values | Olivier |  | Sprint 2 |  | Planned
CRS186 | COQ | User-defined Field 1. Open
CRS187 | COQ | User-defined Field 2. Open
CRS188 | COQ | User-defined Field 3. Open
CRS189 | COQ | User-defined Field 4. Open
CRS190 | GBD | User-defined Customer Field 10. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS191 | GBD | User-defined Customer Field 1. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS192 | GBD | Customer Statistics Identity 1. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS193 | GBD | User-defined Customer Field 3. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS194 | GBD | User-defined Customer Field 4. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS195 | GBD | User-defined Customer Field 5. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS196 | GBD | User-defined Customer Field 6. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS197 | GBD | Customer Statistics Identity 2. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS198 | GBD | User-defined Customer Field 8. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS199 | GBD | User-defined Customer Field 9. Open | Customer Exp | Yes | CRS610 | Configuration | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS200 | DOP | Req/Distr Order Type. Open
CRS202 | DOP | Requisition/Distr Order Authority. Open
CRS204 | DOP | Req Order Authority. Open/Danger Class
CRS205 | WHM | Stock Transaction Type. Open
CRS210 | WHM | Danger Class. Open
CRS212 | WHM | Item. Connect Danger Class
CRS220 | GBD | Reason Category. Open
CRS221 | GBD | Reason Category. Connect Reason Codes
CRS222 | GBD | Function. Connect Reason Category
CRS230 | TDO | Document. Open
CRS234 | TDO | Document Media. Open
CRS235 | GBD | Internal Address. Open
CRS236 | TDO | Document Type. Open
ATS051 | ATC | Attribute Model. Lines Open | Manufacturing | Yes |  |  | Will Bolin | Derek, Jennifer | Sprint 1 |  | Completed
FCS300 | FOR | Forecast Method. Open | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 2 |  | Completed
FCS305 | FOR | Forecast Logic. Open | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 2 |  | Completed
CRS237 | TDO | Document Revision Reason. Open
CRS238 | TDO | Document Subtype. Open
CRS239 | TDO | Document. Connect Locations
CRS240 | TST | TST Business Type. Open
FCS800 | FOR | Settings - Forecasting | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 2 |  | Planned
CRS241 | TDO | Document Location. Open
CRS242 | TDO | Document Type. Connect Activities
CRS243 | TST | Customs Preference. Connect to Item
CRS246 | TDO | Document Alias Type. Open
CRS247 | ICC | Standard Numbering System. Open
CRS250 | GBD | General Distribution List. Open
CRS252 | TDO | Document Application. Open
CRS255 | WHM | Statistics Storage Group. Open
CRS256 | GBD | Process Type. Open
CRS260 | GBD | Quotation Reason. Open
CRS010 | GBD | Language. Open | Finance, Distribution | Yes | CRS610 | Configuration | Athar | Angie Helton | Sprint 1 |  | Completed
CRS012 | GBD | Accounting Dimension. Enter Names | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 1 |  | Completed
CRS265 | GBD | Quotation Monitoring Activity. Open
CRS270 | ARL | Quotation Reference Object. Open | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
CRS275 | GBD | Order Line Charge. Open | Customer Exp | Yes | CRS610 | Configuration | Akhil | Betsy | Sprint 2 |  | HJ Task WIP |  |  |  | Doppio to set up internal line charges. Waiting on HJ to finalize external line charges though
CRS276 | GBD | Order Line Charge. Enter Names/Language | Customer Exp | Yes |  |  | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS277 | GBD | Order Line Charge. Enter Amount | Customer Exp | Yes |  |  | Once we know what all line charges are needed, we would work on it |  | Sprint 3 |  | Planned
CRS278 | GBD | Order Ln Charge Model. Open | Customer Exp | Yes |  |  | Once we know what all line charges are needed, we would work on it |  | Sprint 3 |  | Planned
CRS279 | GBD | Order Ln Charge Model. Connect Charge | Customer Exp | Yes |  |  | Once we know what all line charges are needed, we would work on it |  | Sprint 3 |  | Planned
CRS280 | GBD | Order Ln Charge Model. Connect Ctr Value | Customer Exp | Yes |  |  | Once we know what all line charges are needed, we would work on it |  | Sprint 3 |  | Planned
CRS042 | GBD | Work with County. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
CRS045 | GBD | Country. Open | Customer Exp, Distribution | Yes | CRS610, OIS002, CRS620 | Configuration | Akhil (Thomas as needed) |  | Sprint 1 |  | Completed
CRS046 | GBD | States per Country. Open | Customer Exp, Distribution | Yes | CRS610, OIS002 | Configuration | Akhil (Thomas as needed) |  | Sprint 1 |  | Completed
CRS285 | ARL | Payment Instruction. Open | Finance | Yes | CRS610 (If applicable) | Configuration | Athar | Angie Helton | Sprint 2 |  | Planned
CRS290 | OUT | Printer. Open
CRS300 | GBD | Ship-Via Address. Open | Customer Exp | No | CRS610, OIS002 (Or selection table) |  |  |  | NA | NA | NA | NA |  |  | As discussed with Kyle, we don't have ship via address for any customer
CRS310 | GBD | Customer Discount Group. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA |  |  | No pricing in M3. Hence, no discount rules in M3
CRS311 | WHM | Item Discount Group. Open
CRS316 | CRS | Customer Credit Group. Connect
CRS320 | TST | TST Labor Code. Open
CRS330 | TST | TST Consumption Code. Open
CRS335 | GBD | Control Object. Open User-defined | Finance | Yes | CRS610 | Configuration | Athar | Angie Helton | Sprint 3 |  | Planned
CRS080 | GBD | Department. Open | Manufacturing | Yes | Work centers |  | Will Bolin | Jim K, Derek T | Sprint 1 |  | HJ Task WIP
CRS350 | TST | User-defined TST Field 1. Open
CRS085 | GBD | Planning Area. Open | Manufacturing | Yes | Work centers |  | Will Bolin | Jim K, Derek T | Sprint 1 |  | HJ Task WIP
CRS355 | TST | User-defined TST Field 2. Open
CRS360 | TST | User-defined TST Field 3. Open
CRS365 | TST | User-defined TST Field 4. Open
CRS370 | TST | User-defined TST Field 5. Open
CRS375 | ACC | Accounting Event. Open
CRS385 | ACC | Accounting Type. Open
CRS388 | ACC | Field. Update Control Values
CRS390 | POS | User-defined Shop Field. Open
CRS395 | ACC | Accounting Rule. Set
CRS400 | GLR | Journal Number Series. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS405 | GLR | FAM Function. Open | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS409 | GBD | Invoice Class. Open | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
CRS410 | GLR | Voucher Number Series. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS411 | GLR | Settings - Petty Cash | Finance | Yes |  |  |  |  | Sprint 5 |  | Planned
CRS415 | GBD | Distribution Template. Open
CRS416 | GLR | Financial Printout. Open Add Fields | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS418 | GLR | Program Problem. Solve | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS424 |  | Application Message E-mail Param. Open
CRS427 | MSG | Application Message E-mail Param. Open
CRS434 | COP | Credit Card Interface Settings. Open
CRS437 | MSG | User Interface Server. Open
CRS439 | COP | Connect Third-Party ID. Open
CRS443 | COP | Credit Card Translation Table. Open
CRS450 | GLR | Period Accounting Curve. Open | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS455 | GLR | Invoice Accounting Template. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS460 | ARL | Interest Invoicing Rule. Open | Finance | Yes | CRS610 (If applicable) | Configuration | Athar | Angie Helton | Sprint 1 |  | Completed
CRS465 | ARL | Payment Reminder Rule. Open | Finance | Yes | CRS610 (If applicable) | Configuration | Athar | Angie Helton | Sprint 1 |  | Completed
CRS470 | GLR | Payment Forecast. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
CRS475 | ARL | Settings - Gen. Interest Rate Drafts | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
CRS481 | FAS | Index Table. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS485 | APL | Manage Fields in MI Strings. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CRS490 | POS | Shop Category. Open
CRS491 | POS | Shop Volume Class. Open
CRS492 | POS | Shop Class. Open
CRS505 | GBD | Work Hour Definition. Open
CRS506 | GBD | Break. Open Details
CRS507 | GBD | Break. Open
CRS510 | GBD | Employee. Connect Calendar
CRS515 | GBD | Work Schedule. Open
CRS525 | GBD | Flex Schedule. Open
CRS530 | GBD | Person. Open
CRS531 | GBD | Work Group. Open
CRS539 | GBD | Employee. Enter Cost
CRS540 | GLR | Voucher Text. Open Standard | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS545 | GBD | User. Connect Authority
CRS550 | GBD | Object Type. Open
CRS551 | PJP | User-def Project Field 1. Open
CRS552 | PJP | User-def Project Field 2. Open
CRS553 | PJP | User-def Project Field 3. Open
CRS554 | PJP | User-def Project Field 4. Open
CRS555 | PJP | User-def Project Field 5. Open
CRS556 | PJP | User-def Project Field 6. Open
CRS586 | ATC | Settings - Attribute Control
CRS590 | PJP | Settings - Project Management
CRS591 | PJP | Settings - User-def Project Fields
CRS612 | POS | Customer Cards. Open
CRS618 | GBD | Contact Person. Open | Customer Exp | Yes |  |  |  | Adam | Sprint 2 |  | NA |  |  |  | Agreed with Cassie that we don't manage contact person in M3
CRS620 | GBD | Supplier. Open
CRS621 | GBD | Contact Type. Open | Procurement | Yes |  |  | Olivier |  |  |  | Planned
CRS622 | GBD
CRS623 | GBD
CRS624 | GBD | Supplier. Define Purchase & Financial
CRS638 | CRS | Accounting Dim. Define Authorization | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
CRS645 | GLR | Accounting Structure. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS647 | GLR | Accounting Structure. Define Level | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS650 | APL | Authorized User - Suppl Invoice. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CRS651 | APL | Delegation of Authority Code. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CRS652 | APL | Delegation of Authority Group. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CRS663 | APL | Flexible Service Code. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CRS664 | APL | Flexible Service Code. Connect to Suppl | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CRS665 | GBD | Statement Rule. Open | Finance | Yes | CRS610 (If applicable) | Configuration | Athar | Angie Helton | Sprint 3 |  | Planned
CRS680 | GBD | Supplier. Connect Our Customer Number
CRS685 | ICC | Item Owner. Open
CRS690 | GLR | Bank. Open | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS610 | GBD | Customer. Open | Customer Exp | Yes | Akhil + Eric | Migrated values | Eric + Akhil |  | Sprint 2 |  | Config WIP |  |  |  | Clean data needed from HJ
CRS691 | GLR | Bank. Connect Bank Branch Office | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS692 | GLR | Bank Account. Open | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
CRS693 | GLR | Bank Account. Connect Additional Field | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS695 | GLR | Bank Format. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
CRS696 | GLR | Document Format. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
CRS698 | GLR | Bank Group. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
CRS701 | WLA | Settings - Warehouse & Planning Control
CRS702 | GBD | Settings - Delayed Stock Issues
CRS703 | WHM | Settings - User-def Item Fields
CRS704 | WHM | Settings - Item Hierarchy
CRS705 | SEP | Settings - Credit Check for SO
CRS706 | WHM | Settings - Packing
CRS707 | COP | Settings - Customer Promotion Update
CRS708 | ICC | User Defined Field Equipment. Open
CRS709 | MAP | Supply Chain Policy. Open
CRS710 | GBD | Settings - Temporary Customers | Customer Exp | No |  |  |  |  | NA | NA | NA | NA |  |  | NA, since we don't use temporary customer
CRS711 | LIC | Settings - Lab and Inspection Control
CRS712 | GBD | Settings - User-defined Customer Fields | Customer Exp | Yes |  |  | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS713 | GBD | Settings - User-defined Supplier Fields
CRS714 | CRS | Settings - User-Defined Division Fields
CRS715 | SST | Settings - User-defined Stats Fields
CRS716 | WIS | Settings - Summary Inventory Stats
CRS717 | WHM | Settings - Physical Inventory
CRS718 | COS | Settings - Price Lists | Customer Exp | Yes |  |  | Akhil/Gunnar to do it |  | Sprint 3 |  | Planned
CRS719 | COQ | Settings - Sales Quotations | Customer Exp | Yes |  |  | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS720 | COP | Settings - Customer Order Entry | Customer Exp | Yes |  |  | Gunner |  | Sprint 2 |  | Completed
CRS721 | COP | Settings - Deliveries | Customer Exp, Distribution | Yes |  |  | Gunner |  | Sprint 2 |  | Completed
CRS722 | COP | Settings - Customer Order Invoicing | Finance | Yes |  | Configuration | Athar |  | Sprint 1 |  | Completed
CRS723 | COP | Settings - Acquisition
CRS724 | COB | Settings - Bonus & Commission | Customer Exp | Yes |  |  | Assign to Athar |  | Sprint 3 |  | Planned
CRS725 | MAP | Settings - Inventory Cost of Capital
CRS726 | TAX | Settings - Trade Statistics
CRS727 | TPL | Route Selection Field. Enter
CRS728 | TPL | Settings - TPL Standard Values
CRS729 | WHM | Settings - Export Documents
CRS730 | MAP | Settings - Ordering Cost
CRS731 | COP | Settings - Customer Order Copying | Customer Exp | Yes |  |  | Akhil/Gunnar to do it |  | Sprint 3 |  | Planned
CRS732 | EQM | Settings - Quotations |  | No |  |  |  |  | NA | NA | NA | NA
CRS733 | WLA | Settings - Reservation
CRS734 | COP | Settings - Initial Supply Order
CRS735 | CRS | Settings - Field Length
CRS736 | ACC | Settings - Accounting Error Methods
CRS739 | SMS | Settings - SMS
CRS740 | TAG | Settings - Trade Agreements | Customer Exp | Yes |  |  | This is not required as per understanding as of 01/29 |  | Sprint 3 |  | NA
CRS746 | POP | Purchase Agreement Selection Field. Open
CRS750 | GLR | Settings - General Ledger | Finance | Yes |  | Configuration | Athar |  | Sprint 1 |  | Completed
CRS759 | WHM | Settings - User-def Style Fld Headings
CRS630 | GLR | Accounting Identity. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Config WIP
CRS633 | GLR | Account Group. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Config WIP
CRS634 | GLR | Accounting ID. Enter Reconciliation Rule | Finance | Yes |  |  | Athar | Angie Helton | Sprint 2 |  | Config WIP
CRS635 | GLR | Pseudo Identity. Open | Finance | Yes |  |  | Athar | Angie Helton | Sprint 2 |  | Config WIP
CRS767 | GBD | Z Axis Selection Field. Enter
CRS769 | GBD | Distribut Curve Selection Field. Enter
CRS780 | POP | Settings - Purchasing
CRS781 | ICC | Settings - Equipment Alias Category
CRS782 | WHM | Settings - Distr of Nonapproved Bal ID
CRS783 | WHM | Settings - Location Replenishment
CRS786 | CRP | Settings - Capacity Requirements Plannin
CRS788 | WOP | Settings - Maintenance 1
CRS789 | WOP | Settings - Maintenance 2
CRS790 | SEP | Settings - Service Order Invoicing
CRS792 | PJP | Settings - Project Invoicing
CRS793 | GBD | Settings - Sales Tax | Finance | Yes |  | Configuration | Athar |  | Sprint 1 |  | Completed
CRS794 | CRS | Installation Settings - Vertex | Finance | Yes |  | Configuration | Athar |  | Sprint 1 |  | Completed
CRS795 | CRS | Integration Settings. Open
CRS796 | POS | User-defined Field Heading. Open
CRS799 | GBD | Settings - Filing
CRS843 | GLR | Banking Region. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
CRS881 | EDI | Business Message Data Translation. Displ
CRS883 | EDI | Partner Type. Open
CRS884 | EDI | Partner Alias Type. Open
CRS885 | EDI | Partner Repository. Open
CRS900 | GBD | System Calendar. Open | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS907 | CDS | Delivery Schedule Calendar. Open | Customer Exp | No | OIS002 |  |  |  | NA | NA | NA | NA
CRS910 | GBD | System Calendar. Open Period | Finance | Yes |  |  | Athar |  | Sprint 1 |  | Completed
CRS912 | COP | Season. Open
CRS913 | COP | Classification per season. Open
CRS915 | GBD | Seasonal Curve. Open
CRS916 | GBD | Trend Curve. Open
CRS917 | COP | Season. Connect Delivery Windows
CRS928 | OUT | M3 Document. Open
CRS929 | OUT | M3 Document. Connect Media
CRS945 | OUT | Std Document. Connect Media Ctrl Object
CRS947 | OUT | Std Document. Connect Partner Ref Obj
CRS950 | GBD | General Text. Open
CRS998 | ENV | System Diagnostics. Open
CTS020 | CTP | Distribution Chain. Open
CTS025 | CTP | Distribution Chain. Open Line
CTS030 | CTP | Supply Model Selection Table. Open
CTS040 | CTP | Supply Model Information. Open
CTS090 | MAP | Capable-to-Promise Policy. Open
CTS095 | CTP | Safety Stock. Protect at ATP Calculation
DPS001 | DOP | Distribut Relation. Open
DRS005 | TPL | Route. Open | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
DRS006 | TPL | Route. Connect Departures
DRS007 | TPL | Route. Connect Departure Exceptions
DRS011 | TPL | Route Selection Table. Open | Distribution | Yes |  | Configuration | Olivier | Kyle Brown |  |  | Planned
DRS013 | TPL | Transportation Equipment. Open
DRS016 | TPL | Loading Platform. Open
DRS017 | TPL | Free Trade Association. Open
DRS019 | TPL | Unloading Zone. Open | Customer Exp | No | CRS610, OIS002 |  |  |  | NA | NA | NA | NA
DRS028 | TPL | Delivery Doc Nmbr Formatting Rule. Open
DRS029 | TPL | Transportation Interface Indicator. Open
DRS032 | TPL | Freight Cost Zone. Open
DRS034 | TPL | Forward Agent. Connect Freight Cost Zone
DRS045 | TPL | Time Zone. Open
DRS080 | WHM | Packaging Type. Open
ECS001 | CAD | CAD Integration. Open for Product
ECS010 | CAD | CAD Integration. Open for Component
ECS020 | CAD | CAD Integration. Open for Service
ECS030 | CAD | CAD Integration. Open Hist Service
ECS235 | TDO | Document Group. Open
ENS010 | ETM | Eco-organization. Open
ENS015 | ETM | Eco-contribution Code. Open
ENS020 | ETM | Eco-product code. Open
ENS025 | ETM | Eco-product Code. Connect Item
ENS095 | ETM | Eco-Transaction Selection Table. Open
ENS105 | ETM | Eco-Transaction. Submit
MMS037 | MAP | Planning Policy. Open | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 3 |  | Planned
EVS038 | ENV | Remote Server. Open
EVS040 | ENV | Subscriber. Open
FAS025 | FAS | Depr Template. Open for Decl. Depr | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
FAS045 | FAS | Column Template FA Value. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 3 |  | Completed
FAS050 | FAS | FA Depreciation Type. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 3 |  | Completed
FAS055 | FAS | FA Depreciation Plan. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
FAS060 | FAS | FA Value Type. Open | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Config WIP
FAS070 | FAS | FA Location. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
FAS075 | FAS | FA Type. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
FAS080 | FAS | FA Group. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
FAS090 | FAS | Cost of Capital Method. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
FAS900 | FAS | Settings - Fixed Asset Acquisition | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 2 |  | Completed
FAS905 | FAS | Settings - User-defined FA Fields | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
FAS910 | FAS | Settings - Fixed Asset Revaluation | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 3 |  | Completed
FAS915 | FAS | Settings - Cost of Capital Calculation | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
FAS920 | FAS | Settings - Extraordinary Depreciation | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 3 |  | Completed
FAS925 | FAS | Settings - Fixed Asset Sales | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 3 |  | Completed
FAS935 | FAS | Settings - Fixed Asset Phys Inventory | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
FAS940 | FAS | Settings - Activating FA under Constr | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 3 |  | Completed
FAS945 | FAS | Settings - Fixed Asset Disposition | Finance | Yes |  | Configuration | Athar | Angie Helton | Sprint 3 |  | Completed
FCS310 | FOR | Distribution Curve. Open
FCS320 | FOR | Service Level. Open
FCS325 | FOR | Break Date Calendar. Open
FCS330 | FOR | Distribution Table. Open
FLS135 | VOM | Station. Open
FLS140 | VOM | Operation Type. Open
FLS155 | VOM | Concession Type. Open
FLS160 | VOM | Delay Type. Open
FLS161 | VOM | Delay Reason. Open
FLS551 | SPC | Settings - Initial Provisioning
FLS553 | SPC | Settings - Purchase
FLS554 | SPC | Settings - Distribution
FLS788 | VOM | Settings - Operational Log
FLS815 | VOM | Poisson Table. Open
GLS005 | GLR | Settings - Access Authority Check | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GLS010 | GLR | Bank Operation. Define Value Date Method | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
GLS015 | GLR | Standard Voucher. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GLS020 | GLR | Account Addition Table. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GLS030 | GLR | Account Translation Scenario. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
GLS032 | GLS | Acc Translation Scenario. Open Details | Finance | Yes |  |  |  |  | Sprint 5 |  | Planned
CPS940 | MOP | Manufact Order. Update from APP | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
CRS785 | MOP | Settings - Manufacturing Orders | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 2 |  | Completed
CRS797 | MOP | Settings - Parallell Jobs | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
CRS798 | MOP | APS Policy. Open | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
PMS120 | MOP | Manufacturing Order Type. Open | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 1 |  | Completed
PMS490 |  | Settings - MO Reporting | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 1 |  | Completed
GLS060 | GLR | A/C Allocation Base Table. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GLS062 | GLR | A/C Allocation Target Table. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GLS064 | GLR | A/C Allocation Select Table. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GLS070 | GLR | A/C Allocation Template. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GLS080 | GLS | Settings – Corporate Accounting | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GLS085 | GLS | Corporate Accounting. Specify Vo Nbr Ser | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GLS090 | GLR | Line Entry ID. Open | Finance | Yes |  |  |  |  | Sprint 4 |  | Planned
GLS490 | GLR | Settings - Project Accounting per Proj | Finance | Yes |  |  |  |  | Sprint 5 |  | Planned
GLS690 | GLR | GL Balance File Key. Open | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
GLS820 | GLR | Filing Template. Open | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
GLS830 | GLR | Filing Type. Open | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
GLS850 | GLR | FIM Interface. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
GMS010 | GCO | Settings - Subsidiary
GMS015 | GCO | Settings - Transfer of General Ledger
GMS020 | GCO | Settings - Transfer of Budget
GMS090 | GCO | Settings - Parent Company
IMS010 | IMT | Issue Type. Open
IMS020 | IMT | Issue Management Reason Code. Open
IMS030 | IMT | Issue Management Action Code. Open
IMS040 | IMT | Issue Management Action Group. Open
IMS050 | IMT | Action Group Selection Table. Open
IMS060 | IMT | Issue Management Relation Type. Open
IMS700 | IMT | Settings - Issue Management
LIS001 | LIC | Lab Inspection Class. Open
LIS005 | LIC | Measurement Unit of Measure. Open
LIS010 | LIC | Laboratory. Open
LIS015 | LIC | Measurement Method. Open
LIS020 | LIC | Measurement Instrument. Open
LIS030 | LIC | Range Value. Open
LIS035 | LIC | Actual Value. Open
LIS040 | LIC | Result Type. Open
LIS100 | LIC | Lab Inspection Specification. Open
LTS020 | LTR | LTR Agreement Order Type. Open
LTS699 | LTR | Settings - Leasing Agreements
MCS390 | MCM | Settings - Maintenance Statistics
MFS001 | MUC | Internal Transfer Price. Open
MFS010 | MUC | Settings - Internal Invoicing
MFS015 | MUC | Internal Invoice Text. Open
MFS025 | MUC | Cash and Loan Pool ID. Open
MFS165 | MUC | Internal Invoice Series. Open
MFS167 | MUC | Settings - Invoice Numbering Rule
MHS262 | ITI | Settings - Item Import
MHS860 | WHI | Order Init Stock Trans Qualif. Open
MMS001 | WHM | Item. Open | Distribution, Manufacturing | Yes | MDM >M3 data load | Migrated values | Will Bolin, Olivier | Kyle Brown, Adam | Sprint 1 |  | HJ Task WIP
MMS002 | WHM | Item. Connect Warehouse | Manufacturing | Yes | MDM >M3 data load | Migrated values | Will Bolin |  | Sprint 2 |  | HJ Task WIP
MMS003 | WHM | Item. Connect Facility | Manufacturing | Yes | MDM >M3 data load | Migrated values | Will Bolin |  | Sprint 2 |  | HJ Task WIP
MMS004 | WHM | Item. Connect Meter
MMS005 | WHM | Warehouse. Open | Customer Exp, Distribution | Yes | CRS610 (Default warehouse) | Configuration | Akhil + Athar+ Olivier |  | Sprint 2 |  | Completed
MMS006 | WHM | Warehouse Type. Open
MMS007 | WHM | Warehouse Subtype. Open
CRS570 | PCR | Formula. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
CRS580 | PCR | Formula Group. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
CRS581 | PCR | Selection Matrix Group. Open | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
CRS582 | PCR | Feature Group. Open | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
CRS583 | PCR | Drawing Measurement Group. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
CRS584 | PCR | Option Group. Open | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
CRS585 | PCR | Settings - Product Configuration | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
CRS587 | PCR | Settings - PCM Integration | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
CRS760 | PCR | Settings - Create Item | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 2 |  | Completed
CRS761 | PCR | Settings - Options | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
CRS775 | PCR | Settings - Product Variants | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 2 |  | Completed
PDS050 | PCR | Option. Open | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 1 |  | Planned
PDS051 | PCR | Feature/Option Comb. Open Invalid | Manufacturing | No |  |  | Will Bolin |  |  |  | Planned
PDS053 | PCR | Feature. Connect Default Options | Manufacturing | No |  |  | Will Bolin |  |  |  | Planned
PDS054 | PCR | Feature/Option Comb. Open Obligatory | Manufacturing | No |  |  | Will Bolin |  |  |  | Planned
PDS055 | PCR | Feature. Open | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 1 |  | Config WIP
PDS056 | PCR | Feature. Connect Options | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
PDS057 | PCR | Feature. Enter Names/Language | Manufacturing | No |  |  | Will Bolin |  |  |  | Planned
PDS058 | PCR | Option. Enter Names/Language | Manufacturing | No |  |  | Will Bolin |  |  |  | Planned
PDS060 | PCR | Product Variant. Open | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 3 |  | Planned
PDS080 | PCR | Drawing Measurement. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS083 | PCR | Drawing Measurement. Enter Names/Lang | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
CRS086 | PDA | Work Zone. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
CRS087 | PDA | Product Structure Type. Open | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 2 |  | Completed
CRS745 | PDA | Sequencing Code. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
CRS784 | PDA | Product Structure. Connect to Item No | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
CRS787 | PDA | Settings - Product Structures | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 2 |  | Completed
PDS001 | PDA | Product Structure. Open | Manufacturing | Yes |  |  | Will Bolin | Jim K, Derek T | Sprint 1 |  | HJ Task WIP |  |  |  | Completion planned in Sprint 2
PDS010 | PDA | Work Center. Open | Manufacturing | Yes | Work centers |  | Will Bolin | Jim K, Derek T | Sprint 1 |  | HJ Task WIP
PDS011 | PDA | Work Center. Update Relationships | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
PDS014 | PDA | Work Center. Connect Shift | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
PDS015 | PDA | Work Center. Change Capacity | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
PDS023 | PDA | Alternate Structures. Open | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
PDS028 | PDA | Product. Version | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS029 | PDA | Output Items. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS030 | PDA | Shift. Open | Manufacturing | Yes |  |  | Will Bolin | Jim K | Sprint 1 |  | Completed
PDS031 | PDA | Shift Model. Open | Manufacturing | Yes | Work centers |  | Will Bolin | Jim K | Sprint 1 |  | Completed
PDS033 | PDA | Shift Pattern. Open | Manufacturing | Yes | Work centers |  | Will Bolin | Jim K | Sprint 1 |  | Completed
PDS035 | PDA | Alternate Routing. Open | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
PDS036 | PDA | Shift Pattern. Adjust | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
PDS038 | PDA | Work Center. Connect Disturbance Types | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS039 | PDA | Permit Type. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS040 | PDA | Quality Inspection. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS042 | PDA | Quality Inspection Result. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS044 | PDA | Disturbance Type. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS045 | PDA | Work Center. Connect Alt Capacity U/M | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
PDS046 | PDA | Permit. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS048 | PDA | Lock ID. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS049 | PDA | Isolation Point. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
PDS075 | PDA | Product Structure Class. Open | Manufacturing | No |  |  |  |  | NA | NA | NA | NA
MMS008 | GBD | Place. Open | Customer Exp, Distribution | Yes | CRS610, OIS002, | Configuration | Akhil, Olivier |  | Sprint 3 |  | Planned |  |  |  | This drives lead time calculation with routes etc. Move to sprint 3.
MMS009 | WHM | Warehouse. Connect to Whs Group
MMS010 | WHM | Stock Location. Open | Distribution | Yes |  | Migrated values | Olivier | Kyle Brown | Sprint 1 |  | HJ Task WIP
MMS011 | WHM | Stock Location. Connect Location Groups
MMS014 | WHM | Item. Connect Authority
MMS015 | WHM | Item. Connect Alternate U/M
MMS016 | WHM | Style. Open
MMS017 | WHM | Style. Connect Feature
MMS018 | WHM | Style. Connect Composition
MMS020 | WHM | Item. Define Relations
MMS021 | WHM | Item Hierarchy. Open
MMS022 | WHM | Item Search Group. Open
MMS023 | WHM | Item Pack. Connect
MMS024 | WHM | Alias Type. Open
MMS025 | WHM | Item. Connect Alias Number
MMS028 | WHM | Composition. Open
MMS030 | WHM | Item. Enter Names/Language
MMS033 | WHM | Warehouse Selection Table. Open
MMS038 | WHM | Commodity Code Selection Table. Open
MMS041 | WHM | Commodity Code. Open
MMS042 | WHM | Group Technology Class. Open
MMS043 | WHM | Distribution Group Technology. Open
MMS044 | WHM | Package Number. Create Formatting ID
MMS045 | WHM | Weight Limit. Open
MMS046 | WHM | Storage Requirement. Open
MMS047 | WHM | Packaging Group. Open
MMS049 | ICC | Exchange Requirement. Open
MMS050 | WHM | Packaging. Open
MMS055 | WHM | Item. Connect Standard Packaging
MMS056 | CTP | Supply Model. Open | Customer Exp | Yes | CRS610 (Default value) | Configuration | Akhil (Thomas as needed) |  | Sprint 3 |  | Planned
MMS057 | WHM | Item. Connect Location Type | Distribution | Yes |  |  |  |  | Sprint 4 |  | Planned
MMS059 | CTP | Supply Model. Open Lines
MMS083 | WHM | Period Frame. Open
MMS092 | MAP | Safety Stock Reason Code. Open
MMS093 | MAP | Safety Stock Control Table. Open
MMS094 | MAP | Poisson Table. Open
MMS156 | WLA | Settings - Allocation Priority
MMS256 | ICC | Settings - ETR Fields
MMS258 | ICC | Equipment Type. Open
MMS259 | ICC | Equipment Group. Open
MMS309 | WHM | Settings - Physical Inventory Line
MMS310 | WHM | Physical Inventory. Quick Entry | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
MMS499 | WHM | Settings - Delivery Notes
MMS860 | WHI | Internal Stock Trans Qualif. Open
MMS865 | WHI | Stock Msg Partner. Open
MNS050 | ENV | Subsystem. Open
MNS051 | ENV | Subsystem Job. Open
MNS080 | MNU | Menu Version. Open
MNS090 | MNU | System Language. Select
MNS095 | MNU | Company. Open
MNS100 | MNU | Company. Connect Division
MNS102 | MNU | System Configuration. Open
MNS104 | MNU | Configuration Component. Open
MNS105 | MNU | System Language. Open
MNS120 | TAM | Table. Open
MNS150 | MNU | User ID table | N/A | Yes | CRS610 (Responsible) | Migrated values | Eric |  | Sprint 2 |  | HJ Task WIP |  |  |  | Eric P to own it
MNS151 | MNU | User. Access per Company & Division
MNS155 | MNU | User Settings. Open
MNS157 | MNU | PIN Code Authentication Policy. Open
MNS175 | MNU | Table Browse. Open
MNS180 | GBD | Sorting Order in Browse Window. Open
MNS185 | GBD | Browse Definition. Open
MNS204 | OUT | Output Service Selection. Open
MNS205 | OUT | Output Media Selection. Open
MNS207 | OUT | Output. Manage per Partner
MNS210 | OUT | Report Layout Selection. Open
MNS214 | OUT | Output Service Type. Connect Media
MNS216 | OUT | Output Service. Open
MNS217 | OUT | Output Service Type. Open
MNS218 | OUT | Output Server. Open
PMS390 | PST | Settings - Production Statistics | Manufacturing | Yes |  |  | Will Bolin |  |  |  | Planned
MNS220 | ENV | Job Definition. Open
MNS260 | OUT | MBM Initiator. Open Output
MNS300 | ENV | Job Queue. Open
MNS310 | ENV | Job. Connect Job Queue
MNS405 | SEC | Roles. Open
MNS410 | SEC | Roles per User. Connect
MNS415 | SEC | User Class. Open
MNS416 | SEC | Users per User Class. Connect
MNS420 | OUT | Report Configuration Group. Open
MNS425 | OUT | Report User. Open
MOS120 | WOP | Work Order Type. Open
MOS721 | WAM | Warranty Storage Settings. Open
MOS755 | WAM | Settings - Claim Settlements
MOS980 | PRM | Settings - User-def Service Fields
MOS981 | PRM | Settings - User-def Eng Order Fields
MOS983 | WOP | Settings - User-def Work Order Fields
MOS989 | WOP | Settings - Tools Allocation
MOS990 | WOP | Settings - Operation Reporting/Facility
MOS991 | WOP | Settings - WO Operation Reporting
MOS992 | WOP | Settings - Employee Allocation
MWS006 | WHM | Leveling Settings. Open
MWS815 | WHM | Settings - Item Filing/Deletion
MWS068 | WHM | Inventory | Distribution | Yes | WH Org |  | Olivier | Kyle Brown |  |  | Planned
MWS070 | WHM | Inventory transactions | Distribution | Yes | Inv Transaction |  | Olivier | Kyle Brown |  |  | Planned
OIS005 | GBD | Customer. Connect Item | N/A
OIS006 | GBD | Customer Item. Strict Rotation Dates | N/A
OIS007 | COP | Authoriz Group for CO Type. Open |  |  |  |  | This is part of security aspect
OIS009 | COP | Action Reason. Open | Customer Exp |  |  |  | Akhil/Gunnar to do it. One possible of the use is if we receive an order, and the item status = 90, we close the line and set action reason as let say DISCONTINUED |  | Sprint 4
OIS010 | COP | CO Type. Open | Customer Exp | Yes | CRS610 | Configuration | Gunner |  | Sprint 2 |  | Completed
OIS011 | COP | CO Type. Connect Documents | Customer Exp | Yes |  | Configuration | Gunner |  | Sprint 2 |  | Completed
OIS012 | COP | Sales Price List Table. Open | Customer Exp | Yes |  | Configuration |  |  | Sprint 3 |  | Planned
OIS013 | COP | CO Type. Connect Order Charges | Customer Exp | Yes |  | Configuration |  |  | Sprint 3 |  | Planned
OIS014 | COP | CO Type. Update Field Selection | Customer Exp | Yes |  | Configuration | Gunner |  | Sprint 2 |  | Completed
OIS015 | COS | Sales Costing Element. Open | Customer Exp
OIS022 | COS | Sales Costing Model. Open | Customer Exp
OIS028 | COP | CO Type. Connect Group | Customer Exp
OIS029 | COS | CO Charge. Enter Names/Language | Customer Exp
OIS030 | COS | CO Charge. Open | Customer Exp | Yes |  |  | Akhil | Betsy | Sprint 2 |  | HJ Task WIP |  |  |  | Waiting on HJ to finalize the charges
OIS031 | COS | Service Charge. Open | Customer Exp | Yes | CRS610 | Configuration | Akhil (Thomas as needed) |  | Sprint 3 |  | Planned
OIS035 | COP | Document Text. Open | Customer Exp
OIS039 | COS | Business Chain. Connect Customer | Customer Exp
OIS040 | COS | Business Chain. Open | Customer Exp
OIS044 | COP | Price Label Flag. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
OIS051 | GBD | Customer. Connect Nonactivity Period | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
OIS060 | COS | Cust Blanket Agreement. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
OIS063 | COS | Cust Blanket Agreement Type. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
OIS064 | COS | Blanket Agreement Line Sel Field. Enter | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
OIS072 | COS | Assortment. Connect Items | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
OIS225 | COP | Settings - Delivery Windows | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
OIS278 | COP | Settings - Batch Orders | Customer Exp | Yes |  |  |  |  | Sprint 3 |  | Planned
OIS330 | COS | Settings - Sales Price Calculation | Customer Exp | Yes |  |  |  |  | Sprint 3 |  | Planned
OIS347 | COS | Settings – Price Margin Simulate | Customer Exp | Yes |  |  |  |  | Sprint 3 |  | Planned
OIS365 | COS | Pricing Group. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
OIS366 | COS | Pricing Group Selection. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA
OIS390 |  | Customer Return. Open | Procurement | Yes | Return Mgt |  |  | Heather King |  |  | Planned
OIS398 | COP | Settings - Customer Returns/TST | Customer Exp | Yes |  |  |  |  | Sprint 5 |  | Planned
OIS399 | COP | Settings - Customer Returns | Customer Exp | Yes |  |  |  |  | Sprint 5 |  | Planned
OIS405 | COB | Bonus/Comm Item Table. Open | Customer Exp
OIS406 | COB | Bonus/Comm Item Table. Connect Item | Customer Exp
OIS407 | COB | Bonus/Comm Customer Table. Open | Customer Exp
OIS408 | COB | Bonus/Comm Customer Table. Connect Cust | Customer Exp
OIS800 | COS | Discount Model. Open | Customer Exp | Yes |  |  | Gunner |  | Sprint 2 |  | Completed
OIS805 | COS | Discount Model. Connect Disc Number | Customer Exp | Yes |  |  | Gunner |  | Sprint 2 |  | Completed
OIS806 | COS | Discount Model. Enter Disc Names/Lang | Customer Exp | Yes |  |  | Gunner |  | Sprint 2 |  | Completed
OIS810 | COS | Discount Model. Connect Discount Scale | Customer Exp | Yes |  |  | Gunner |  | Sprint 2 |  | Completed
OIS811 | COS | Discount Model. Connect Disc Scale Lines | Customer Exp | Yes |  |  | Gunner |  | Sprint 2 |  | Completed
OIS820 | COS | Discount Campaign. Open | Customer Exp | Yes |  |  | Gunner |  | Sprint 2 |  | Completed
OIS821 | COS | Discount Campaign. Enter Names/Language | Customer Exp | Yes |  |  | Gunner |  | Sprint 2 |  | Completed
OIS831 | COS | Sales Price List Selection Table. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA |  |  | This is not used for sales to customers. But, might be needed for selling raw-material to sub-contractor in case of CO triggered by PO
OIS840 | COS | Promotion. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA |  |  | NA for this project. We don't manage promotions in M3. If E-com passes promotion, we would save in a free field
OIS849 | COS | Promotion Type. Open | Customer Exp | No |  |  |  |  | NA | NA | NA | NA |  |  | NA for this project. We don't manage promotions in M3
OPS020 | POS | Settings - Item Net Transfer Trigger
OPS030 | POS | Settings - Customer Net Transfer Trigger
OPS700 | POS | Settings - POS
PCS001 | PCO | Settings - Product Costing | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
PCS005 | PCO | Costing Type. Open | Finance | Yes |  |  |  |  | Sprint 2 |  | Planned
PCS010 | PCO | Costing Component. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS011 | PCO | Costing Component. Enter Values | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS015 | PCO | Costing Element. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS016 | PCO | Costing Element. Enter Rates | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS020 | PCO | Costing Element. Connect Components | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS025 | PCO | Product Costing Model. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS030 | PCO | Costing Toolbox Model. Open | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS100 | PCO | Costing Component. Enter W/C Rates | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS105 | PCO | Costing Component. Enter Tool Cost | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS115 | PCO | Costing Component. Enter Material O/H | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
PCS120 | PCO | Costing Component. Enter Product O/H | Finance | Yes |  |  |  |  | Sprint 3 |  | Planned
POS001 | PJP | Project Element. Open
POS010 | PJP | Project Type. Open
POS015 | PJP | Project Manager. Open
POS020 | PJP | Service Proj Templ. Connect Templ/Assign
POS030 | PJP | Project Budget Template. Open
POS035 | PJP | Project Budget Item. Open
POS037 | PJP | Accrual Account Templ. Open
POS038 | PJP | Accrual Account Templ. Connect Budg Type
POS039 | PJP | Project Budget Type. Open
POS040 | PJP | Project Checklist. Open
POS042 | PJP | Project Checklist Group. Open
POS060 | PJP | Project Element Type. Open
POS065 | PJP | Region. Open
POS093 | PJP | Project Template. Open
POS094 | PJP | Project Subtemplate. Open
POS800 | PJP | Settings - Projects
POS820 | PJP | Settings - Recognition
POS830 | PJP | Settings - User-def Mtrl Budget Fields
POS831 | PJP | User-def Mtrl Budget Field 1. Open
POS832 | PJP | User-def Mtrl Budget Field 2. Open
POS833 | PJP | User-def Mtrl Budget Field 3. Open
POS834 | PJP | User-def Mtrl Budget Field 4. Open
POS835 | PJP | User-def Mtrl Budget Field 5. Open
POS836 | PJP | User-def Mtrl Budget Field 6. Open
POS840 | PJP | Settings - User-def Budget Item Fields
POS841 | PJP | User-def Budget Item Field 1. Open
POS842 | PJP | User-def Budget Item Field 2. Open
POS843 | PJP | User-def Budget Item Field 3. Open
POS844 | PJP | User-def Budget Item Field 4. Open
POS845 | PJP | User-def Budget Item Field 5. Open
POS846 | PJP | User-def Budget Item Field 6. Open
PPS015 | POP | Agreement Priority. Open
PPS025 | POP | Quality Audit Type. Open
PPS032 | POP | Invoicing Frequency. Open
PPS033 | POP | PO Delivery Method Selection. Open
PPS038 | POP | Costing Model Sel Table. Open
PPS040 | GBD | Supplier. Connect Item
PPS090 | POB | Purchase Order Batch Origin. Open
PPS095 | POP | Purchase Order Type. Open
PPS098 | POP | e-Procurement Order Type. Open |  | No |  |  |  |  | NA | NA | NA | NA
PPS099 | POP | Purchase Organization. Open |  | No |  |  |  |  | NA | NA | NA | NA
PPS114 | GBD | Supplier. Connect FAM Function | Finance | Yes |  |  |  |  | Sprint 6 |  | Planned
PPS200 |  | Purchase Order. Open | Procurement | Yes | CRS620 |  | Olivier | Heather King |  |  | Planned
PPS280 | POP | Costing Element. Open
PPS285 | POP | Purchase Costing Model. Open
PPS345 | POP | Goods Receiving Method | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS398 | MAP | Surplus Return Settings. Open
PPS430 | PSS | Settings - Supplier Statistics
QMS001 | QMS | Qualitative Values. Open
QMS002 | QMS | Numeric Qualitative Header. Open
QMS004 | QMS | Test Classification. Open
QMS005 | QMS | Sample Type. Open
QMS006 | QMS | Industry Standard. Open
QMS007 | QMS | Quality Group. Open
QMS008 | QMS | Quality Reason Code. Open
QMS009 | QMS | Quality Plan. Open
QMS011 | QMS | Laboratory. Open
QMS012 | QMS | Measurement Method. Open
QMS013 | QMS | Measurement Instrument. Open
QMS014 | QMS | Quality Reinspection Plan. Open
QMS015 | QMS | Quality Plan Item Warehouse. Open
QMS100 | QMS | Test Template. Open
QUS020 | EQM | Quotation Type. Open
QUS150 | EQM | Sales Manager. Open
QUS155 | EQM | Settings - Quotation Permissions
QUS160 | EQM | Target Margin. Open
QUS980 | EQM | Settings - User-Defined EQM Fields
RCS800 | RCP | Settings - RCCP
RGS010 | RGR | User. Open for Report Distribution
RGS900 | RGR | Financial Report. Specify
RGS905 | RGR | Financial Report Group. Specify
RMS010 | RIS | Credit Monitoring Action. Open
RMS900 | RIS | Settings - DSO Calculation
RMS905 | RIS | Settings - Credit Monitoring
RPS030 | MAP | Production Rate. Open
RPS040 | MAP | Safety Stock. Open Time Phased
RPS045 | MAP | Planning Entity. Open
RPS050 | MAP | Material Plan Vsn. Open
RPS070 | MAP | Material Plan Database. Open
RPS090 | WHM | Item. Define Sourcing Rules
RPS120 | MAP | Demand Order Type. Open
RPS180 | MAP | Planning Template. Open
RPS185 | MAP | Planning Template Rules. Open
RPS195 | MAP | Priority Rules. Open
RPS380 | MAP | Upstream Rules. Open
RPS670 | MAP | Inventory Leveling. Open
RPS800 | MAP | Settings - Macro Order
RPS810 | MAP | Settings - Inventory Planning
RPS820 | MAP | File Settings - Inventory Sharing. Open
RSS005 | CDS | Default Sales Facility. Define
RSS010 | CDS | Delivery Schedule Type. Open
RSS015 | CDS | Settings - Partners
RSS020 | CDS | Delivery Schedule Deviation Model. Open
RSS025 | CDS | Delivery Pattern. Open | Customer Exp | No | OIS002 |  |  |  | NA | NA | NA | NA
RSS040 | CDS | Customer Address. Connect Replacing
RSS055 | CDS | Delivery Split Model. Open
RSS060 | CDS | JIT Call-off Method. Open
SAS480 | SAG | Settings - User-def Service Agr Fields
SES003 | SEC | Function. Connect Authority
SES005 | SEC | Function. Connect API Authority
SES010 | SEC | Field Group. Connect Authority
SES100 | SEC | Field Security Group. Open
SES300 | SEC | Keystore. Open
SES400 | SEC | Function. Connect Authority by Role
SES405 | SEC | API Transaction. Connect Security Option
SHS030 | MJS | Job Schedule Function. Open
SHS031 | MJS | Job Schedule Program. Open
SHS050 | MJS | Job Schedule Category. Open
SHS060 | MJS | Job Schedule Calendar. Open
SOS460 | SEP | Settings - User-def Service Fields
MMS035 | WHM | Stock Location Type. Open | Distribution | Yes |  | Migrated values | Olivier | Kyle Brown | Sprint 1 |  | HJ Task WIP
MMS036 | WHM | Location Group. Open | Distribution | Yes |  | Migrated values | Olivier | Kyle Brown | Sprint 1 |  | HJ Task WIP
SOS461 | SEP | Settings - User-def SO Address Fields
MMS040 | WHM | Stock Zone. Open | Distribution | Yes |  | Migrated values | Olivier | Kyle Brown | Sprint 1 |  | HJ Task WIP
SOS590 | SEP | Settings - Warranty
SOS973 | SEP | Settings - e-mail Messages
SOS974 | SEP | Settings - GSM Text Messages
SOS975 | SEP | Settings - Auto Technician Allocation
SPS010 | SCP | Node Type. Open
SPS020 | SCP | Node. Open
SPS025 | SCP | Sales Node. Open
SPS030 | SCP | SCP Item Group. Open
SPS701 | SCP | Settings - Supply Chain Planner
STS480 | STR | Settings - User-Def Rental Agrmnt Fields
STS660 | STR | Settings - Service Day Calculation
STS699 | STR | Settings - Rental Agreements
TAS001 | TAC | TAC Project. Open
TAS002 | TAC | TAC Project Activity. Open
TAS005 | TAC | Labor Code. Open
TAS010 | TAC | Price List. Open
TAS015 | TAC | Labor Code Template. Open
TAS020 | TAC | Labor Code Group. Open
TAS025 | TAC | TAC Employee Group. Open
TAS030 | TAC | Labor Code Type. Open
TAS040 | TAC | Project Area. Open
TAS055 | TAC | Column Template - Time Trans Bal. Open
TAS900 | TAC | Settings - Time Accounting
TAS901 | TAC | Settings - TA Invoice Level per Customer
TMS950 | TIM | Settings - Time & Attendance
TMS955 | TIM | Settings - Manual Reporting
TXS035 | TAX | Taxation Reporting. Open Report Fields
TXS050 | TAX | Sales Tax Exemption. Open
TXS060 | TAX | Sales Tax Nexus. Open
CRS033 | OUT | Media Profile. Open | Procurement | Yes | CRS620 |  | Olivier | Heather King |  |  | Planned
CRS182 | WHM | User-defined Field 1. Open | Procurement
CRS183 | WHM | User-defined Field 3. Open | Procurement | Yes | CRS620 | Migrated values | Olivier | Heather King | Sprint 2 |  | Planned
CRS042 | GBD | Work with County. Open | Procurement | Yes | CRS620 |  | Olivier | Heather King |  |  | Planned
CRS300 | GBD | Ship-Via Address. Open | Procurement | Yes | CRS620 |  | Olivier | Heather King |  |  | Planned
CRS150 | GBD | Supplier Group. Open | Procurement | Yes | CRS620 | Migrated values | Olivier | Heather King |  |  | Planned
PPS020 | POP | Quality Class. Open | Procurement | Yes |  | Migrated values | Olivier | Heather King |  |  | Planned
CRS055 | POP | Currency.Open | Procurement | Yes | CRS620 | Standard / Default values | Olivier | Heather King |  |  | Planned
CRS056 | POP | Exchange Rate Type.Open | Procurement | Yes | CRS620 | Standard / Default values | Olivier | Heather King |  |  | Planned
CRS075 | POP | Payment Term.Open | Procurement | Yes |  | Standard / Default values | Olivier | Heather King |  |  | Planned
CRS071 | POP | AP Payment Method.Open | Procurement | Yes |  | Migrated values | Olivier | Heather King |  |  | Planned
CRS065 | POP | Delivery Term.Open | Procurement | Yes |  | Standard / Default values | Olivier | Heather King |  |  | Planned
CRS070 | POP | Delivery Method.Open | Procurement | Yes |  | Standard / Default values | Olivier | Heather King |  |  | Planned
CRS125 | POP | Packaging Term.Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS126 | POP | Freight Term.Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS035 | POP | Monitoring Activity List. Open | Procurement | Yes |  | Migrated values | Olivier | Heather King |  |  | Planned
PPS050 | POP | Monitoring Class. Open | Procurement | Yes |  | Migrated values | Olivier | Heather King |  |  | Planned
CRS130 | POP | Tax Code.Open | Procurement | Yes |  | Standard / Default values | Olivier | Heather King |  |  | Planned
APS010 | POP | Trade Code.Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
RPS080 | POP | Point of Time Table. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
MMS002 | POP | Item. Connect Warehouse | Procurement | Yes |  |  | Olivier | Heather King, Kyle | Sprint 2 |  | Planned |  |  |  | 2/12 : cross workstream discussion in progresss
CRS620 | POP | Supplier. Open | Procurement | Yes |  | Migrated values | Olivier | Heather King |  |  | Planned
CRS622 | POP | Supplier. Connect Address | Procurement | Yes |  | Migrated values | Olivier | Heather King |  |  | Planned
CRS623 | POP | Supplier. Connect Reference | Procurement | Yes |  | Migrated values | Olivier | Heather King |  |  | Planned
CRS624 | POP | Supplier. Define Purchase & Financial | Procurement | Yes |  | Migrated values | Olivier | Heather King |  |  | Planned
PPS130 | POP | Request for Quotation. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS133 | POP | Request for Quotation. Open Lines | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS100 | POP | Purchase Agreement. Open | Procurement | Yes |  |  | Olivier | Heather King | Sprint 2 |  | Planned
PPS170 | POP | Planned Purchase Order. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS180 | POP | Purchase Requisition. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS200 | POP | Purchase Order. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS220 | POP | Purchase Order. Display Lines | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS250 | POP | Purchase Order. Confirm | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS260 | POP | Purchase Order. Advise Shipment | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS300 | POP | Purchase Order. Receive Goods | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS360 | POP | Supplier Delivery Note. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS310 | POP | Purchase Order. Inspect Goods | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS320 | POP | Purchase Order. Put away Goods | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS390 | POP | Return To Supplier. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS040 | POP | Supplier. Connect Item | Procurement | Yes |  |  | Olivier | Heather King | Sprint 2 |  | Planned
CRS706 | POP | Settings - Packing | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS721 | POP | Settings - Deliveries | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS734 | POP | Settings - Initial Supply Order | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS723 | POP | Settings - Acquisition | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS783 | POP | Settings - Location Replenishment | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS709 | POP | Supply Chain Policy. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS717 | POP | Settings - Physical Inventory | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS727 | POP | Route Selection Field. Enter | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS701 | POP | Settings - Warehouse & Planning Control | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
MMS015 | POP | Item. Connect Alternate U/M | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
RPS090 | POP | Item. Define Sourcing Rules | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
PPS095 | POP | Purchase Order Type. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS746 | POP | Purchase Agreement Selection Field. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
MMS002 | WHM | Item. Connect Warehouse | Distribution | Yes | Meeting scheduled |  | Olivier | Kyle Brown | Sprint 2 |  | HJ Task WIP
MWS410 | WHM | Delivery. Open Toolbox | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
MWS420 | WHM | Picking List. Report | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
MMS050 | WHM | Packaging. Open | Distribution | Yes |  |  | Olivier | Kyle Brown | Sprint 2 |  | HJ Task WIP
DRS080 | WHM | Packaging Type. Open | Distribution | Yes |  |  | Olivier | Kyle Brown | Sprint 2 |  | HJ Task WIP
MWS135 | WHM | Packaging Charges Selection Table. Open | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
CRS200 | WHM | Req/Distr Order Type. Open | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
MMS053 | WHM | Item. Connect Packaging | Distribution | Yes |  |  | Olivier | Kyle Brown | Sprint 2 |  | HJ Task WIP
MMS047 | WHM | Packaging Group. Open | Distribution | Yes |  |  | Olivier | Kyle Brown | Sprint 2 |  | HJ Task WIP
MWS423 | WHM | Delivery. Connect Packages | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
CRS706 | WHM | Settings - Packing | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
DRS100 | WHM | Shipment. Open Toolbox | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
DRS102 | WHM | Additional Transportation Info. Open | Distribution | Yes |  |  | Olivier | Kyle Brown |  |  | Planned
PPS019 | POP | PO Consolidation Group. Open | Procurement | Yes |  |  | Olivier | Heather King |  |  | Planned
CRS025 |  | Item Group | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 1 |  | Completed
CRS035 |  | Product Group | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 1 |  | Completed
CRS040 |  | Item type | Manufacturing | Yes |  |  | Will Bolin |  | Sprint 1 |  | Completed
MWS010 |  | Dispatch Policy | Distribution, Manufacturing | Yes | Completed for Mfg |  | Will, OLivier |  | Sprint 2 |  | Config WIP
PPS101 |  |  | Procurement | Yes |  |  | Olivier |  | Sprint 2 |  | Planned

## Pivot Table 2
COUNTA of In scope |  | TST <200> (Config & UT)
SPRINT | Workstream (multiple section option) | Completed | Config WIP | HJ Task WIP | NA | Planned | (blank) | Grand Total
NA |  |  |  |  | 45 |  |  | 45
Sprint 1 |  | 45 | 1 | 9 |  | 1 |  | 56
Sprint 2 |  | 41 | 6 | 13 | 1 | 32 |  | 93
Sprint 3 |  | 7 |  |  | 14 | 98 |  | 119
Sprint 4 | [5 empty] | 24 |  | 24
Sprint 5 | [5 empty] | 10 |  | 10
Sprint 6 | [5 empty] | 15 |  | 15
(blank) | [5 empty] | 89 | 2 | 91
Grand Total |  | 93 | 7 | 22 | 60 | 269 | 2 | 453